## Direction
Things to Consider Prior to Starting Workbook
This workbook is meant to support both TIP and TAP development. Differences between the two will be notated within each sheet/tab. The workbook serves as planning tool to assist you when filling out the form link for the TAP/TIP turn in. Modify the cells as needed - the workbook attempts to follow the form logic as closely as possible. During the submision, you will complete one submission per strategy and then complete additional submissions as needed until all TIPs, and TAPs are complete. Please note that student outcome goals, for all indivdual campuses, and closure/reassignment, for all indivdual campuses, will be on different forms.
Directions
1. Fill out the workbook PRIOR to the official link (or choose your own draft tool).
2. If there is criteria for success, it will be posted at the top.
3. Note that not all tabs need to be filled out - this depends on the strategy selected.
4. Items highlighted yellow indicate they only apply to certain strategies so read carefully.
5. Read each tab/sheet carefully.
* UPDATES THAT CAUSED CHANGES ARE OUTLINED IN RED

## Plan Type
Question/Prompt | Please select the type of plan you are submitting
Additional Instructions | Targeted Improvement Plan (TIP) or Turn Around Plan (TAP)
Answer | Targeted Improvement Plan (TIP)

## School System Information
Question/Prompt | List (select) campuses to which this strategy will apply | Name of the staff member employed by the school system completing this plan submission | Email | What role applies to the person completing this submission?
Additional Instructions | May be asked to provide CDCN if not listed |  |  | Please select/type one of the following: Superintendent, District Coordinator of School Improvement (DCSI), Other (if other, please specify)
Answer | IDEA La Joya Academy IDEA Achieve Academy IDEA Eastside College Prep IDEA Najim Academy IDEA Spears Academy IDEA Spears College Prep | Jacklyn Verdin | jacklyn.verdin@ideapublicschools.org | Other - Chief of Staff

## NA and Stakeholder Engmt
Criteria for Success
Did the LEA meet statutory requirements for stakeholder engagement, and has the board approved the plan? -The district assures that the Campus Intervention Team (CIT) conducted a public meeting at each campus identified for school improvement with the campus principal, the members of the campus-level planning and decision-making committee, parents of students attending the campus, and community members residing in the school district to review the campus performance rating and solicit input for the development of the targeted improvement plan. -The district assures that written notice of all public meetings was provided to parents and students of each impacted campus, notice of the meeting was posted on each campus website, and this notice included the date, time, and place of the meeting. -The board conducted a hearing regarding the plans for each campus identified for school improvement. -The board posted the plan on the district website prior to the hearing. -The plan is approved by the board. -Written comments from stakeholders, if any, are attached.
ASSURANCES ARE THE SAME FOR BOTH TIP/TAP
Question | List or copy and paste all SI - identified campuses below | I assure that all campuses named in this plan have conducted an on-site needs assessment that meets the requirements in Section 39A.053 of the Texas Education Code. (For example: Texas Strategic Leadership Landscape Analysis, Effective Schools Framework Diagnostic, or a local needs assessment.) | I assure that all locally conducted needs assessments met the requirements in Section 39A.053 of the Texas Education Code, and the results of the local needs assessment are available upon request. | I assure that the Campus Intervention Team (CIT) conducted a public meeting at each campus required to submit a Targeted Improvement Plan with the campus principal, the members of the campus-level planning and decision-making committee, parents of students attending the campus, and community members residing in the school district to review the campus performance rating and solicit input for the development of the plan. | I assure that written notice of all public meetings was provided to parents and students of each impacted campus, notice of the meeting was posted on each campus website, and this notice included the date, time, and place of the meeting. | I assure that the board conducted a hearing regarding the plans for each campus identified for school improvement to notify the public of the insufficient performance of the campus, the improvements in performance expected by the agency, and the intervention measures or sanctions that may be imposed if the performance does not improve within a designated period, the board solicited public comment on each targeted improvement plan, and the board posted the plan(s) on the district website prior to the hearing. | Board approval date with optional upload of public comments
Additional Instructions | List all SI campuses in the district | Choose one of the following: ESF Diagnostic and Local Classroom Review, Locally Conducted Needs Assessment, Texas Strategic Leadership Landscape Analysis | For locally conducted assessments only | Yes or No | Yes or No | Yes or No | Record the board approval date for each campus
Answer(s) | IDEA Achieve Academy | You will give this assurance at the time of submission through the Qualtrics Survey. | You will give this assurance at the time of submission through the Qualtrics Survey. | You will give this assurance at the time of submission through the Qualtrics Survey. | You will give this assurance at the time of submission through the Qualtrics Survey. | You will give this assurance at the time of submission through the Qualtrics Survey. | 2026-01-20
IDEA La Joya Academy
IDEA Eastside College Prep
IDEA Najim Academy
IDEA Spears Academy
IDEA Spears College Prep

## Student Outcome Goals
Question | List or copy and paste all SI - identified campuses below | I assure that all campuses included in this plan have set campus-wide goals for ELA/Reading and Math STAAR performance rates and scaled score goals for Domain III components (Academic Achievement, Growth Status, ELP Status, and Student Success Status) for the 2025–2026 school year.
Additional Instructions | List all SI campuses in the district | Yes or No
Answer(s) | IDEA Achieve Academy | You will give this assurance at the time of submission through the Qualtrics Survey.
IDEA La Joya Academy
IDEA Eastside College Prep
IDEA Najim Academy
IDEA Spears Academy
IDEA Spears College Prep
YOU WILL FILL OUT A SEPARATE SURVEY TO INPUT YOUR STUDENT OUTCOME GOALS for each campus required to submit a TIP or TAP. THE QUESTIONS YOU WILL BE ASKED IN THAT SURVEY ARE LISTED BELOW.
Question | Please select campus you are reporting Student Outcome Goals for. | If the campus you are reporting Student Outcome Goals for is not available in the list above, please enter the campus(es) CDCN number in the field below. | Enter the campus-wide goal for the All Grades ELA/Reading Meets Grade Level or Above STAAR Performance rate for the 2025-2026 school year. | Enter the campus-wide goal for the All Grades Math Meets Grade Level or Above STAAR Performance rate for the 2025-2026 school year. | Enter the 2025-2026 Component Points campus goal for the Academic Achievement Component of Domain III. | Enter the 2025-2026 Component Points campus goal for the Growth Status Component of Domain III. | Enter the 2025-2026 Component Points campus goal for the ELP Status Component of Domain III. | Enter the 2025-2026 Component Points campus goal for the Student Success Status Component of Domain III.
Additional Instructions | List all SI campuses in the district | Please, ensure the CDCN number is complete with leading zeros when applicable. Example: Campus 235467 should be entered as 00235467 | (Please enter a percentage, for example if the goal is 85%, please enter 85). | (Please enter a percentage, for example if the goal is 85%, please enter 85). | (Please enter a percentage, for example if the goal is 85%, please enter 85). | (Please enter a percentage, for example if the goal is 85%, please enter 85). | (Please enter a percentage, for example if the goal is 85%, please enter 85). | (Please enter a percentage, for example if the goal is 85%, please enter 85).
Answer(s) | IDEA Achieve Academy |  | 46% | 49% | 56 | RLA: 50 Math: 75 | 75 | 50
| IDEA La Joya Academy |  | 39% | 28% | RLA: 58 Math: 25 | RLA: 75 Math: 50 | 75 | 42
| IDEA Eastside College Prep |  | 46% | 36% | 50 | 30 | 100 | 80
| IDEA Najim Academy |  | 40% | 40% | 30 | 30 | 30 | 30
| IDEA Spears Academy |  | 46% | 49% | 50 | RLA: 58 Math: 75 | 50 | 50
| IDEA Spears College Prep |  | 44% | 38% | RLA: 69 Math: 50 | RLA: 50 Math: 62 | 100 | 50

## School Improvement Strategy
Criteria for Success
Is the proposed strategy likely to move the campus to a C or better OR CSI exit in two years or less? -The school improvement strategy selected would reasonably improve student outcomes quickly enough that the campus would not be escalated to a sanction under Texas Education Code (TEC), Section 39A.111. -There is appropriate support dedicated to strategy implementation and capacity building: +There is a team/organization with a track record of success in systems building and rapidly improving student outcomes dedicated to supporting the campus in strategy implementation (an ESC, SAPL vendor, program-vetted vendor, etc.); OR +If district or campus staff members are named as the capacity builder, there is evidence that these staff members: -Have a track record of success in school turnaround -At least 50% of their role is dedicated to the implementation of the strategy on the campus (cannot be current principal or AP, unless role was added specifically to support SI)
Question | To which campus or campuses does this strategy apply? | Please select the option that best describes your overall school improvement strategy for this campus/these campuses for the 2025-2026 school year. | Which, if any, grants has your school system been awarded to support this strategy? | Which, if any, grants has your school system applied for (or intends to apply for) to support this strategy? | Please name any organizations you are currently working with to build capacity and support strategy implementation. | How many district staff members will you be reporting capacity building information for? | What are the names and roles of district and campus staff members responsible for capacity building, and what percent of their role is dedicated to supporting implementation of the school improvement strategy? | 5.5 Please describe the organization's or staff member's experience and track record in school turnaround (moving a campus from failing to meet standards to meeting and/or exceeding standards).
Additional Instructions | List all SI campuses in the district | Please write one of the following: Accelerating Campus Excellence (ACE) Model Closure/reassign Improve Graduation Rate Intensive Curriculum & Instruction Improvements School Model Change (excluding ACE) Turnaround Partnership (SB 1882) | Strong Foundations Implementation (LASO 3), Strong Foundations Implementation School Improvmeent PLC (LASO 3), Instructional Leadership (LASO 3), ESF- focus Support Grant 24-26, School Action Fund Planning (Restart), School Action Fund Implementation (Restart), School Action Fund Planning (Reassign), School Action Fund Implementation (Reassign), School Action Fund Implementation (Redesign), School Action Fund Planning (Create New), School Action Fund Implementation (Create New), Our school system does not intend to apply for a grant to support this strategy, Other (must enter grant into text box) | LIFT, LIFT PLC Support, School Improvement Curriculum and Instruction Support Grant, School Action Fund Planning (Restart), School Action Fund Implementation (Restart), School Action Fund Planning (Reassign), School Action Fund Implementation (Reassign), School Action Fund Implementation (Redesign), School Action Fund Planning (Create New), School Action Fund Implementation (Create New), Effective Schools Framework Focsued Support Grant 24-26, Our school system does not intend to apply for a grant to support this strategy, Other (must enter grant into text box) | SAPL list, ESCs, District Staff, Other (must include name) | You can report up to 15 district staff members. | ONLY COMPLETE IF DISTRICT STAFF NAMED (column F on this page) | ONLY COMPLETE IF THE ORGANIZATION NAMED (column F on this page) IS NOT AN ESC OR ON THE STATE APPROVED PROVIDER LIST (SAPL).
Answer(s) | IDEA Achieve Academy | Intensive Curriculum & Instruction Improvements | Our school system does not intend to apply for a grant to support this strategy | Our school system does not intend to apply for a grant to support this strategy | Alex Anzaldua, District Staff Wendy Simpson, District Staff Patricia Rodriguez, District Staff Alecia Bell, District Staff |  | In this role, approximately 80% of the Vice President of School Improvements responsibilities are devoted to executing the district’s school improvement strategy. As VPSI, Wendy Simpson's work includes guiding campuses through the Effective Schools Framework (ESF), addressing identified needs within school improvement plans, and coordinating regional and national supports to ensure aligned execution. Ms. Simpson provides direct coaching and professional developement to campus and district leaders to strengthen leadership planning and build effective systems for instruction, data use, and operational excellence. Wendy Simpson offers ongoing feedback, collaborates closely with executive directors, regional superintendents, and Vice Presidents of Schools, and plays a critical role in ensuring continuous improvement across priority campuses. | Wendy Simpson is an accomplished K-12 executive leader with a decade of success leading rapid, measurable school turnaround across multiple Texas districts. Her leadership has consistently elevated campuses from Improvement Required or F ratings to Meeting or Exceeding Standards (A–C ratings) by establishing data-driven systems, coaching leaders for instructional excellence, and aligning practice to the TEA Effective Schools Framework (ESF). Track Record of Results: Mansfield ISD ¦ School Improvement Officer / DCSI (2022–2024) Led improvement planning and coaching for nine campuses, including Comprehensive, Targeted, and High-Priority Schools. Kenneth Davis Elementary: F (56) → A (90) in one year; +19 overall gain ¦ Student Achievement +8 ¦ School Progress +13 ¦ Closing the Gaps +32 Erma Nash Elementary: D (64) → C (75) in one year; +11 overall gain ¦ Student Achievement +7 ¦ School Progress +10 ¦ Closing the Gaps +14 Harmon Elementary: D (65) → projected C (76) in one year; implemented retention-based stipend model amid high turnover. Cross Timbers Intermediate: 69 → 77 (C) in one year (+8 overall); sustained performance Year 2. Summit High School: C (73) → B (82) in one year; Closing the Gaps 57 → 85 (+28). System Impact: Built districtwide TIP protocols, aligned ESF Levers 1 & 5 coaching, and executed calibration walks that raised quality of Tier 1 instruction and leader feedback cycles. DeSoto ISD ¦ Executive Director of Core Curriculum & Grants (2021–2022) Directed academic turnaround across 10 schools, moving the district from C (79) to B (83) overall. KJ Elementary: D (61) → A (92) (+31); RY Elementary: F (57) → B (82) (+25); WES Elementary: D (65) → B (85) (+20); CHE Elementary: D (67) → B (82) (+15) Everman ISD ¦ Principal (2015–2018) Promoted mid-year to lead a campus rated Improvement Required (2015); achieved Met Standard in 90 days, sustaining success for three consecutive years. 2015–2016: Met Standard; earned Distinction for Top 25% Student Progress. 2016–2017: Earned 2 Distinctions (ELA/Reading & Postsecondary Readiness). AA Math +22 pts ¦ Writing +19 pts ¦ ELL Writing +18 pts. 2017–2018: Met Standard third year; earned 3 Distinctions (Reading, Math, Postsecondary Readiness). 3rd Grade Reading 53% → 74% (+19); 4th Grade Math 68% → 73%. System Impact: Built sustainable data-driven PLC systems and leadership pipelines; over 85% of her ILT advanced to higher-level roles; reduced racial achievement gaps by 20+ points. Her work demonstrates that with stable leadership, disciplined systems, and high-expectation culture, turnaround can move from short-term recovery to long-term excellence.
[7 empty] | "In this role, approximately 80% of the Vice President of School Improvement’s responsibilities focus on executing the district’s comprehensive school improvement strategy. Key duties include guiding campuses through the Effective Schools Framework (ESF), addressing critical needs identified in turnaround plans, and coordinating regional and national resources to ensure cohesive implementation. The Vice President of School Improvement provides direct coaching and professional development to campus and district leaders, strengthening leadership capacity and building robust systems for instruction, data-driven decision-making, and operational excellence. Additionally, the role involves delivering actionable feedback, fostering collaboration with executive directors, regional superintendents, and Vice Presidents of Schools, and driving continuous improvement efforts across priority campuses." "In this role, approximately 70% of the Vice President of School responsibilities are dedicated to executing the district’s comprehensive school improvement strategy. This includes serving as the direct coach and manager for campus principals and leadership teams, providing targeted guidance to strengthen instructional leadership and operational effectiveness. The Vice President collaborates closely with campus staff to design and deliver developmental opportunities that build capacity and drive sustainable improvement. A critical aspect of the role involves fostering partnerships and assembling regional and national support teams to address campus-specific needs. These efforts ensure alignment with district priorities and leverage best practices to accelerate student achievement and organizational excellence." | Alex Anzaldua brings 29 years of experience in education, with the last 13 years dedicated to supporting campuses in need of targeted improvement, including turnaround efforts. His work has included guiding schools initially projected to receive D or F accountability ratings to achieve A and B ratings through strategic leadership and system development. Alex specializes in empowering campus leaders and leadership teams by deepening their understanding of effective school administration. He supports the creation and implementation of high-impact systems aligned with the Texas Education Agency (TEA) improvement model, ensuring sustainable academic growth. A key component of his approach includes recruiting high-quality educators and providing them with ongoing support through a tight-loop coaching model focused on instructional excellence. His efforts have helped campuses transition from a culture of compliance to one of academic rigor and excellence, fostering environments where student achievement is prioritized and continuously improved.
[7 empty] | "Patricia Rodriguez, Vice President of School Improvement, dedicates 90% of her efforts to the executive oversight and implementation of the district-wide turnaround strategy, ensuring all D and F rated schools receive the necessary resources, support and systems to achieve accelerated growth within one school year. Mrs. Rodriguez is dedicated and focused on a portfolio of 6 schools, all with either a D or F-campus rating. Her scope of work strategically guides campuses through the Effective Schools Framework (ESF), addressing key needs within turnaround plans, and coordinating regional and national expertise to coach, strengthen leadership capacity and ensure execution is consistently aligned across all initiatives. Mrs. Rodriguez delivers direct coaching and training to both campus and district leaders, fostering effective systems for instruction, data use, and operational excellence, while ensuring alignment through close collaboration with Executive Directors, Area Superintendents, and Vice Presidents of Schools. " | Patricia Rodriguez-VP Of School Improvement- Over 10 years of experience in the school turnaround space. As a principal Mrs. Rodriguez led the campus out of failing status (F) within one school year and drove sustainable growth gains the following year. The campus earned 4 distinctions with 15% student growth of special populations ( Emergent Bilingual, African American and Economically Disadvantaged). As a School Support Officer for 4 years, Mrs. Rodriguez supervised a portfolio of 14 turnaround schools directing the turnaround efforts that successfully moved 3 campuses out of failing status within a single academic year and supported school gains across all 14 campuses in her school portfolio. Lastly, as an Assistant Superintendent of Schools, Mrs. Rodriguez supervised two failing elementary campuses and strategically adopted and implemented the ACE (Accelerating Campus Excellence ) model. The model provided the structural framework to drive rapid instructional changes leading to both campuses moving from an F rating to a C and B rating within one school year. Both campuses sustained a B rating for subsequent years. Additionally, Mrs. Rodriguez led the development of leadership frameworks and leadership definitions for the district to support turnaround work.
[7 empty] | In this role, approximately 80% of the Vice President of School Improvements responsibilities are devoted to executing the district’s school improvement strategy. Her work includes guiding campuses through the Effective Schools Framework (ESF), addressing identified needs within turnaround plans, and coordinating regional and national supports to ensure aligned execution. She provides direct coaching and training to campus and district leaders to strengthen leadership planning and build effective systems for instruction, data use, and operational excellence. Mrs. Bell offers ongoing feedback, collaborates closely with executive directors, regional superintendents, and Vice Presidents of Schools, and plays a critical role in ensuring continuous improvement across priority campuses. | "The Vice President of School Improvement brings extensive, proven experience in leading and supporting school improvement across multiple leadership roles. As a principal, she successfully turned around two historically underserved and underperforming campuses in the Houston Independent School District, Hartsfield ES and Gregory-Lincoln K-8. In her work she moved both campuses from Improvement Required to Met Standard and earning distinctions. As a School Support Officer (principal supervisor) and Executive Director of Instruction, she supported 14 campuses over six years, guiding them out of school improvement status and ensuring they met all turnaround requirements, this portfolio also includes one alternative education campus who had not met standard in over 6 years moved from F to C (High School Ahead Academy). Additionally, she supported the work of moving Fleming MS from a rating of F to B. In her role as Executive Director of School Improvement, serving as the DCSI, Ms. Bell supported multiple campuses within a single district in achieving and sustaining their turnaround goals. She has deep expertise in implementing the Effective Schools Framework (ESF) across all roles and contexts, including direct support of campus leadership of Patrick Henry Middle School (located 1 block from Hardy Academy), a campus identified under SB 1365, successfully moving a campus from an F to a C and avoiding state sanctions. Turnaround Experience Overview : 5 Years – Teacher 5 Years – Assistant Principal 6 Years – Principal 7 Years – Principal Manager (School Support Officer / Executive Director) 2 Years – District School Improvement Leadership"
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slight change in wording of options
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed campus staff as an option

## Curriculum and Instruction
Criteria for Success
Does the plan increase the quality of instructional materials to be used at the campus and provide adequate time and support for teachers to internalize materials and reflect on student performance? -The campus will increase the quality of the instructional materials to be used at the campus (if not already implementing SBOE-approved HQIM or OER). -The district has allocated sufficient instructional time for delivery of HQIM and has a calendar with a minimum of 165 instructional days. -The campus will have weekly (at a minimum) high-quality PLCs to support instructional delivery and respond to student outcomes -The PLC protocol includes time for lesson internalization and student work analysis.
ONLY COMPLETE THIS SECTION IF YOU NAMED INTENSIVE CURRICULUM AND INSTRUCTION SUPPORTS AS YOUR SCHOOL IMPROVEMENT STRATEGY
Question | List or copy and paste all SI - identified campuses below | Please select the adopted curriculum | Is this the curriculum that will be implemented for the duration of the plan?l | How many instructional minutes per week are required/recommended for implementation of this curriculum? | How many instructional minutes per week are in master schedule for curriculum delivery, and does this amount of minutes meet the required/recommended number of minutes? | How many instructional days are included in the 2025-2026 calendar? | Please describe the assessment plan for the impacted campus(es) | Will the campus(es) implement a PLC structure? | How will PLCs be organized (by grade level, content area, etc.)? | How frequently will PLCs occur? | Who will facilitate PLCs? | Who is requried to attend PLCs? | Please describe the PLC protocol to be used
Additional Instructions | List all SI campuses in the district excluding Texas Partnership schools | This question will be asked by grade bands: K-5 Math, K-5 RLA, 6-8 Math, 6-8 RLA, 9-12 Math (Algebra 1, Algebra 2, Geometry), 9-12 RLA | Yes or No Select yes, go to column G Select no, go to column E
Answer(s) | IDEA Achieve Academy | K - 5 Bluebonnent Math , K - 5 Wit & Wisdom | Yes | 300 | 75 | 180 | Bluebonnet Math includes Mid-Module and End-of-Module assessments for each unit, with assessment windows varying by grade level according to module length. In addition, campuses will administer bi-weekly spiral assessments to monitor ongoing mastery. Standards in which students do not demonstrate proficiency will be identified, retaught through spiraled review, and reassessed to ensure growth and retention. Blue Bonnet Math has a Mid Module assessment for each module, as well as an End-of-Module assessment. Wit and Wisdom has two Literacy Assessments per modules and and End of Unit Module. Days vary by grade level acccording to the length of the unit. | Yes - weekly | PLC's will be two times a week for grades 3rd-5th in the content areas of RLA and Math for a total of 120 minutes per week. Kinder-2nd grade will have bi-weekly PLC's for 60 minutes bi-weekly. | PLC's will occur in grades 3rd-5th for 120 minutes per week twice a week. | Instructional leaders inclusive of Assistant Principals of Instruction, VP of Schools, and VP of School Improvement. | 3rd-5th all content area teachers including SPED teacher and EB testing coordinator. | Looking Back PLC's focused on data, will begin by identifying the highest leverage data for the week inluding exit tickets, student work analysis and reteach lessons. Looking Forward PLC's focused on upcoming instruction Teachers will unpack student expectations and build exemplars. Script out direct instruction for I Do portion of the lesson including rehearsal for lesson. Address anticipated misconceptions for the lesson. Academic Monitoring laps will be planned out.
| IDEA La Joya Academy | K - 5 Bluebonnent Math , K - 5 Wit & Wisdom | Yes | Math: 350 RLA: 450 | 80 | 173 | "Daily exit tickets will be completed at the end of each instructional block. Teachers will record student performance and participate in exit ticket huddles to develop targeted reteach plans. Furthermore, teachers will engage in student work analysis meetings to examine the quality of student responses and address misconceptions. Bluebonnet Math includes Mid-Module and End-of-Module assessments for each unit, with assessment windows varying by grade level according to module length. In addition, campuses will administer bi-weekly spiral assessments to monitor ongoing mastery. Standards in which students do not demonstrate proficiency will be identified, retaught through spiraled review, and reassessed to ensure growth and retention. To measure broader progress, campuses will also administer two Interim Assessments (IA) for both Math and ELAR, providing data to inform instructional adjustments and intervention planning." | Yes - weekly | PLCs will be organized by Grade-level | Weekly | Principal & Assistant Principal | Principals, Assistant Principals, Teachers | Purpose: The PLC protocol is designed to ensure consistent, high-quality collaboration that drives instructional improvement and accelerates student achievement and growth. Given our CSI status, weekly PLCs serve as a critical structure to address student learning gaps, align instruction to standards, and ensure equity and access for all scholars—particularly Emergent Bilinguals, students with foundational gaps, and those receiving Special Education services. PLC Agenda Template (Weekly) Each PLC follows a consistent agenda to ensure focus, alignment, and accountability: 1. Student Work/Data Review – Analyze student outcomes and identify trends or misconceptions. 2. Standard Deconstruction – Clarify what mastery looks like and identify key skills embedded in the TEKS. 3. Instructional Planning – Plan instructional moves, scaffolds, and exemplars that support mastery for all students. 4. Exit Ticket Alignment – Ensure daily checks for understanding align tightly to the learning objective and rigor of the standard. 5. Next Steps & Accountability – Capture commitments, determine next steps, and identify who will monitor follow-through. CSI Lens on PLCs PLCs are equity-driven structures that prioritize the needs of: • Emergent Bilinguals • Students with Foundational Gaps • Special Education Scholars Through intentional collaboration, PLCs ensure access to grade-level content and strategies that promote language and conceptual development for all learners.
| IDEA Eastside College Prep | 6 - 8 RLA - Wit & Wisdom 9th - 10th RLA - Springboard 11th - 12th RLA - AP 6 - 10th Math - District Curriculum Redesign | Yes | 450 | 450 | 173 | The Eastside assessment plan for math utilizes the curriculum's built in topic quizzes and unit assessments, which feature varied administration windows based on grade-level module length for each unit. These module assessments will provide detailed and timely information on student learning to precisely diagnose learning gaps. Furthermore, these unit assessments also function as a quality assurance mechanism, providing leaders with data-driven evidence of curriculum fidelity and instructional effectiveness to inform targeted interventions with teachers and support staff. To measure broader progress, of Texas standards, the campus will administer two aligned Interim Assessments (IA) one in the fall for ELAR and one in the spring for mathematics, which provide high level data necessary for strategic instructional adjustments, precise intervention planning and validating the rigor and alignment of Tier 1 instruction. Daily student exit tickets will be completed at the end of each instructional block to allow teachers to quickly and accurately assess current learning. The performance data is captured in a centralized platform and is used to inform Exit Ticket Huddles, a campus operational mechanism used to inform teaching and learning progress each day. The Exit Ticket Huddle is a critical daily structure where teachers and leaders collaboratively review student responses to new learning or standards mastery. The Principal and API over their assigned contents facilitate real-time coaching and support in the diagnosis of learning barriers. The core outcome is the development of targeted reteach plans and next steps typically implemented within the same week-which ensures continuous progress monitoring and proactively address learning gaps before they widen. | Yes - weekly | Yes, the campus will implement a structured PLC process. Teachers plan by grade level; therefore, each PLC consists of the grade-level content teacher, the campus instructional leader, the Regional content leader, and, when accessible, a National content leader. Teachers are required to submit lesson internalization plans each Friday after reviewing the scripted curriculum and unpacking the unit. Feedback on lesson internalization plans are provided by the add day when due) Assistant Principals of Instruction (API) by Monday afternoon Assistant Principals of Instruction (APIs) provide feedback to teachers, and Regional content coaches review the quality of this feedback to ensure alignment with instructional expectations. Teachers also participate in lesson rehearsals weekly with APIs and when available, regional coaches to receive immediate feedback on specific Tier 1 components of the lesson begore teachers go live with students. During lesson rehearsals, leaders model expectations, provide actionable next steps, and allow teachers to practice and receive feedback. As a follow up, any challenges or adjustments made during lesson rehearsal are observed by the API or regional content coach to ensure the next teach is effective. Lastly, teachers participate in Exit Ticket huddles, during which they analyze student performance and submit next instructional steps based on Exit Ticket data. PLCs include student work analysis to identify misconceptions, plan targeted reteach strategies, and refine instructional delivery. Priority teachers which also include new teachers or teachers new to their content area, receive side-by-side planning support with their content APIs, including lesson rehearsals before delivering Tier 1 instruction. Campus leaders meet with regional leaders at the end of the week on Friday to review upcoming lessons, feedback and support that leaders will turnkey the following week during real time coaching and lesson plan feedback. | PLCs occur weekly, and each component of the PLC process is implemented on a weekly basis. | PLCs are facilitated weekly by campus Assistant Principals of Instruction (APIs), in collaboration with regional content coaches. When additional support is needed, national content leaders are engaged as side-by-side collaborators. | Teachers and Assistant Principals of Instruction are required to attend PLCs. Additionally, tutors, long term substitutes and intervention support teachers acquired through school improvement funds are also required to attend PLCs. The campus principal attends for coaching support and feedback. | The campus will utilize a structured PLC protocol focused on lesson internalization, data analysis, and instructional planning. Each weekly PLCs will follow a consistent cycle: 1. Lesson Internalization: This process isa structured collaborative session essential for deep intellectual preparation before teachers go live with students. This process also guarantees fidelity to the curriculum and a strong first teach during Tier One. During this time, teachers collectively deconstruct upcoming standards and lesson blueprints, with a sharp focus on the required rigor and intended learning. Teachers strategically identify high leverage moves and proactively anticipate potential student misconceptions. APIs facilitate the process with support from Regional Content Coaches. Leaders provide targeted coaching and strategic pushes to ensure the implementation of researched based instructional practices (RBIS) within the lesson. 2. Student Work Analysis: Teachers and leaders participate in this collaborative and rigorous protocol. Student work is reviewed and examined for quality against the intended learning and rigor of the standard. This analysis is leveraged to quickly identify common misconceptions and learning trends, enabling teachers to immediately plan instructional adjustments. these immediate adjustments focus on refining questioning, maintaining grade-level rigor and providing opportunities for productive struggle. Leaders and teachers proactively collaborate to address learning gaps. The protocol is facilitated by APIs,and supported by regional content coaches. 3. Lesson Rehearsal: During this interactive session, teachers present student work exemplars and identify the specific standard being taught. Teachers practice a predetermined, high leverage segment of the lesson-often a critical instructional move, questioning sequence or misconception work-while actively being coached by the Principal or API. This practice involves the teacher scaffolding and asking questions or working through problems, and anticipating student misconceptions. This weekly structure allows the teacher to receive real time, focus feedback from the Principal or API, enabling them to make immediate instructional adjustments before lesson delivery to students. 4. Exit Ticket Huddle: This is critical daily structure where teachers and leaders collaboratively review student responses to new learning or standards mastery. The Principal and API over their assigned contents facilitate real-time coaching and support in the diagnosis of learning barriers. The core outcome is the development of targeted reteach plans and next steps typically implemented within the same week-which ensures continuous progress monitoring and proactively address learning gaps before they widen.
| IDEA Najim Academy | K - 5 Bluebonnent Math , K - 5 Wit & Wisdom | Yes | 450 | 450 | 173 | The Najim Academy assessment plan for math utilizes the Bluebonnet curriculum's built in Mid-Module and End-of-Module assessments, which feature varied administration windows based on grade-level module length for each unit. These module assessments will provide detailed and timely information on student learning to precisely diagnose learning gaps. Furthermore, these module assessments also function as a quality assurance mechanism, providing leaders with data-driven evidence of curriculum fidelity and instructional effectiveness to inform targeted interventions with teachers and support staff. To measure broader progress, of Texas standards, the campus will administer two aligned Interim Assessments (IA) one in the fall for ELAR and one in the spring for mathematics, which provide high level data necessary for strategic instructional adjustments, precise intervention planning and validating the rigor and alignment of Tier 1 instruction. Daily student exit tickets will be completed at the end of each instructional block to allow teachers to quickly and accurately assess current learning. The performance data is captured in a centralized platform and is used to inform Exit Ticket Huddles, a campus operational mechanism used to inform teaching and learning progress each day. The Exit Ticket Huddle is a critical daily structure where teachers and leaders collaboratively review student responses to new learning or standards mastery. The Principal and API over their assigned contents facilitate real-time coaching and support in the diagnosis of learning barriers. The core outcome is the development of targeted reteach plans and next steps typically implemented within the same week-which ensures continuous progress monitoring and proactively address learning gaps before they widen. | Yes - weekly | Yes, the campus will implement a structured PLC process. Teachers plan by grade level; therefore, each PLC consists of the grade-level content teacher, the campus instructional leader, the Regional content leader, and, when accessible, a National content leader. Teachers are required to submit lesson internalization plans each Friday after reviewing the scripted curriculum and unpacking the unit. Feedback on lesson internalization plans are provided by the add day when due) Assistant Principals of Instruction (API) by Monday afternoon Assistant Principals of Instruction (APIs) provide feedback to teachers, and Regional content coaches review the quality of this feedback to ensure alignment with instructional expectations. Teachers also participate in lesson rehearsals weekly with APIs and when available, regional coaches to receive immediate feedback on specific Tier 1 components of the lesson begore teachers go live with students. During lesson rehearsals, leaders model expectations, provide actionable next steps, and allow teachers to practice and receive feedback. As a follow up, any challenges or adjustments made during lesson rehearsal are observed by the API or regional content coach to ensure the next teach is effective. Lastly, teachers participate in Exit Ticket huddles, during which they analyze student performance and submit next instructional steps based on Exit Ticket data. PLCs include student work analysis to identify misconceptions, plan targeted reteach strategies, and refine instructional delivery. Priority teachers which also include new teachers or teachers new to their content area, receive side-by-side planning support with their content APIs, including lesson rehearsals before delivering Tier 1 instruction. Campus leaders conduct daily classroom observations and deliver real-time coaching to reinforce effective instructional practices and ensure fidelity of implementation. Lesson Rehearsals: Monday-Wednesday 7:00-7:40 a.m. | PLCs occur weekly, and each component of the PLC process is implemented on a weekly basis. | PLCs are facilitated weekly by campus Assistant Principals of Instruction (APIs), in collaboration with regional content coaches. When additional support is needed, national content leaders are engaged as side-by-side collaborators. | Teachers and Assistant Principals of Instruction are required to attend PLCs. Additionally, tutors, long term substitutes and intervention support teachers acquired through school improvement funds are also required to attend PLCs. The campus principal attends for coaching support and feedback. | The campus will utilize a structured PLC protocol focused on lesson internalization, data analysis, and instructional planning. Each weekly PLCs will follow a consistent cycle: 1. Lesson Internalization: This process isa structured collaborative session essential for deep intellectual preparation before teachers go live with students. This process also guarantees fidelity to the curriculum and a strong first teach during Tier One. During this time, teachers collectively deconstruct upcoming standards and lesson blueprints, with a sharp focus on the required rigor and intended learning. Teachers strategically identify high leverage moves and proactively anticipate potential student misconceptions. APIs facilitate the process with support from Regional Content Coaches. Leaders provide targeted coaching and strategic pushes to ensure the implementation of researched based instructional practices (RBIS) within the lesson. 2. Student Work Analysis: Teachers and leaders participate in this collaborative and rigorous protocol. Student work is reviewed and examined for quality against the intended learning and rigor of the standard. This analysis is leveraged to quickly identify common misconceptions and learning trends, enabling teachers to immediately plan instructional adjustments. these immediate adjustments focus on refining questioning, maintaining grade-level rigor and providing opportunities for productive struggle. Leaders and teachers proactively collaborate to address learning gaps. The protocol is facilitated by APIs,and supported by regional content coaches. 3. Lesson Rehearsal: During this interactive session, teachers present student work exemplars and identify the specific standard being taught. Teachers practice a predetermined, high leverage segment of the lesson-often a critical instructional move, questioning sequence or misconception work-while actively being coached by the Principal or API. This practice involves the teacher scaffolding and asking questions or working through problems, and anticipating student misconceptions. This weekly structure allows the teacher to receive real time, focus feedback from the Principal or API, enabling them to make immediate instructional adjustments before lesson delivery to students. 4. Exit Ticket Huddle: This is critical daily structure where teachers and leaders collaboratively review student responses to new learning or standards mastery. The Principal and API over their assigned contents facilitate real-time coaching and support in the diagnosis of learning barriers. The core outcome is the development of targeted reteach plans and next steps typically implemented within the same week-which ensures continuous progress monitoring and proactively address learning gaps before they widen.
| IDEA Spears Academy | K - 5 Bluebonnent Math , K - 5 Wit & Wisdom | Yes | Math: 350 RLA: 450 | 80 | 173 | Bluebonnet Math includes Mid-Module and End-of-Module assessments for each unit, with assessment windows varying by grade level according to module length. In addition, campuses will administer bi-weekly spiral assessments to monitor ongoing mastery. Standards in which students do not demonstrate proficiency will be identified, retaught through spiraled review, and reassessed to ensure growth and retention. Daily exit tickets will be completed at the end of each instructional block. Teachers will record student performance and participate in exit ticket huddles to develop targeted reteach plans. Furthermore, teachers will engage in student work analysis meetings to examine the quality of student responses and address misconceptions. To measure broader progress, campuses will also administer two Interim Assessments (IA) one fall for ELAR and one spring for mathematics, providing data to inform instructional adjustments and intervention planning. | Yes - weekly | The campus has the following PLC structure: Tuesdays leaders and teachers meet for lesson planning and alignment. Thursdays and Fridays leaders facilitate lesson rehearsals with teachers to allow practice and coaching before lesson implementation. Priority math and Reading teachers also have morning lesson rehearsals three days each week that emcompass the lesson they will implement that day. "Faculty professional development occurs each Tuesday for one hour based on campus needs and data. Team, we hold PD and staff meetings after school on Tuesdays. Today we will work on PLC norms and the PD schedule. 1st Tuesday, 4:30 – 5:30 = Content PD 2nd Tuesday, 4:30 – 5:30 = Special Pops/ or data 3rd Tuesday, 4:30 – 5:30 = Practice Clinics 4th Tuesday, 4:30 – 5:30 = Lesson and Unit Unpacking " | PLCs occur weekly, and each component of the PLC process is implemented on a weekly basis. Lesson planning PLCs occur weekly on Tuesdays. For priority teachers, lesson rehearsals happen at least 4 days each week. For non-priority teachers, rehersals happen 1-2 days each week. Campus professional development sessions occur weekly on Tuesdays. | PLCs are facilitated weekly by campus Assistant Principals of Instruction (APIs), in collaboration with regional content coaches. When additional support is needed, national content leaders are engaged as side-by-side collaborators. Assistant Principals facilitate the planning sesions. Assistant Principals facilitate the rehearsals. Professional development sessions are either led by Princpal, Assistant Principal and/or teacher leaders. | Teachers and Assistant Princpals of Instruction are required to attend PLCs. Additionally, tutors and intervention support teachers aquired through school improvement funds are also required to attend PLCs. The campus principal attends for coaching support and feedback. Teachers and AssistantLead teachers, counselors, Assistant Principals and the Princpal are required to attend 100% of the sessions, Co-Teachers are chosen for certain sessions that are relative to the scope of their positions. Princpals are required to attend PLCs. The Principal also attends and Regional Math Coaches occassionally attend. Teachers and Assistant Princpals are required to attend PLCs. The Principal also attends. National and Regional Math Coach occassionally attend. | The campus will utilize a structured PLC protocol focused on lesson internalization, data analysis, and instructional planning. Each weekly PLC will follow a consistent cycle: Lesson Internalization: Teachers review upcoming lessons, identify key instructional moves, and anticipate areas of student misunderstanding. APIs and regional content coaches provide feedback to ensure alignment to curriculum and rigor. Exit Ticket and Data Analysis: Teachers analyze Exit Ticket results and student work to determine mastery levels, identify trends, and plan targeted reteach or extension strategies. Student Work Analysis: Teachers collaboratively examine samples of student work to identify misconceptions and plan adjustments to instruction, including questioning techniques and opportunities for productive struggle. Rehearsal and Practice: Priority teachers engage in lesson rehearsals, during which leaders model, provide feedback, and allow teachers to practice delivery before implementing Tier 1 instruction. The protocol is facilitated by APIs, supported by regional content coaches, and, when needed, national content leaders to ensure instructional consistency, data-driven decisions, and alignment to ESF expectations.
| IDEA Spears College Prep | K - 5 Bluebonnent Math , K - 5 Wit & Wisdom | Yes | Math: 350 RLA: 450 | 80 | 173 | Bluebonnet Math includes Mid-Module and End-of-Module assessments for each unit, with assessment windows varying by grade level according to module length. In addition, campuses will administer bi-weekly spiral assessments to monitor ongoing mastery. Standards in which students do not demonstrate proficiency will be identified, retaught through spiraled review, and reassessed to ensure growth and retention. Daily exit tickets will be completed at the end of each instructional block. Teachers will record student performance and participate in exit ticket huddles to develop targeted reteach plans. Furthermore, teachers will engage in student work analysis meetings to examine the quality of student responses and address misconceptions. To measure broader progress, campuses will also administer two Interim Assessments (IA) one fall for ELAR and one spring for mathematics, providing data to inform instructional adjustments and intervention planning. | yes - weekly | The campus has the following PLC structure: Tuesdays leaders and teachers meet for lesson planning and alignment. Thursdays and Fridays leaders facilitate lesson rehearsals with teachers to allow practice and coaching before lesson implementation. Priority math and Reading teachers also have morning lesson rehearsals three days each week that emcompass the lesson they will implement that day. "Faculty professional development occurs each Tuesday for one hour based on campus needs and data. Team, we hold PD and staff meetings after school on Tuesdays. Today we will work on PLC norms and the PD schedule. 1st Tuesday, 4:30 – 5:30 = Content PD 2nd Tuesday, 4:30 – 5:30 = Special Pops/ or data 3rd Tuesday, 4:30 – 5:30 = Practice Clinics 4th Tuesday, 4:30 – 5:30 = Lesson and Unit Unpacking " | PLCs occur weekly, and each component of the PLC process is implemented on a weekly basis. Lesson planning PLCs occur weekly on Tuesdays. For priority teachers, lesson rehearsals happen at least 4 days each week. For non-priority teachers, rehersals happen 1-2 days each week. Campus professional development sessions occur weekly on Tuesdays. | PLCs are facilitated weekly by campus Assistant Principals of Instruction (APIs), in collaboration with regional content coaches. When additional support is needed, national content leaders are engaged as side-by-side collaborators. Assistant Principals facilitate the planning sesions. Assistant Principals facilitate the rehearsals. Professional development sessions are either led by Princpal, Assistant Principal and/or teacher leaders. | Teachers and Assistant Princpals of Instruction are required to attend PLCs. Additionally, tutors and intervention support teachers aquired through school improvement funds are also required to attend PLCs. The campus principal attends for coaching support and feedback. Teachers and AssistantLead teachers, counselors, Assistant Principals and the Princpal are required to attend 100% of the sessions, Co-Teachers are chosen for certain sessions that are relative to the scope of their positions. Princpals are required to attend PLCs. The Principal also attends and Regional Math Coaches occassionally attend. Teachers and Assistant Princpals are required to attend PLCs. The Principal also attends. National and Regional Math Coach occassionally attend. | The campus will utilize a structured PLC protocol focused on lesson internalization, data analysis, and instructional planning. Each weekly PLC will follow a consistent cycle: Lesson Internalization: Teachers review upcoming lessons, identify key instructional moves, and anticipate areas of student misunderstanding. APIs and regional content coaches provide feedback to ensure alignment to curriculum and rigor. Exit Ticket and Data Analysis: Teachers analyze Exit Ticket results and student work to determine mastery levels, identify trends, and plan targeted reteach or extension strategies. Student Work Analysis: Teachers collaboratively examine samples of student work to identify misconceptions and plan adjustments to instruction, including questioning techniques and opportunities for productive struggle. Rehearsal and Practice: Priority teachers engage in lesson rehearsals, during which leaders model, provide feedback, and allow teachers to practice delivery before implementing Tier 1 instruction. The protocol is facilitated by APIs, supported by regional content coaches, and, when needed, national content leaders to ensure instructional consistency, data-driven decisions, and alignment to ESF expectations.

## Capacity Building
Criteria for Success
Does the plan ensure that administrators and teachers receive appropriate job-embedded training? -Administrators responsible for the campus (including the principal and principal manager) receive upfront/initial training on key elements of the school improvement strategy. -Teachers receive upfront/initial training on key elements of the school improvement strategy. -Teachers receive an observation and feedback round from an instructional leader or coach at least biweekly. -The observation tool includes research-based instructional strategies (RBIS) look fors. -The observation tool includes look fors related to implementation of approved curriculum. -The capacity building/professional development (PD) plan matches the current state of talent at the campus. +There is a plan to differentiate and/or increase support for teachers, administrators, and principal managers that are new (in their first two years) to their role. +There is a plan to differentiate and/or increase support for teachers, administrators, and principal managers that do not have a demonstrated track record of success. +There is a plan to differentiate and/or increase support for uncertified teachers.
ONLY COMPLETE IF YOU CHOSE INTENSIVE C&I SUPPORTS AS A SCHOOL IMPROVEMENT STRATEGY OR NAMED DISTRICT STAFF AS BUILDING CAPACITY OR SUPPORTING STRATEGY IMPLEMENTATION ON THE SI STRATEGY TAB
Question | List or copy and paste all SI - identified campuses below | Removed several columns | Please describe your planned training/PD sessions (and who delivers and attends) for: -Principal manager -Principal -Other campus admin (assistant principals, instructional coaches) -Teachers | How will you differentiate training for inexperienced (less than 2 years in role) and/or ineffective teachers/leaders ? | What tool will be used to evaluate implementation of the training (for example, classroom walkthrough tool, leadership coaching tools)? What look fors will be included in this tool? | How frequently will each teacher receive an observation from an instructional leader or coach, and receive feedback? | What capacity building supports related to supporting students in special populations will teachers and administrators receive?
Additional Instructions | List all SI campuses in the district excluding Texas Partnership, ACE, or Graduation Rate
Answer(s) |  |  | "RBIS – Research-Based Instructional Strategies Provider: Region 11 Education Service Center Audience: Principals, Assistant Principals of Instruction (APIs), Regional Content Coaches Session Timeline: Description Principals, Assistant Principals of Instruction, and Regional Content Coaches will receive training from Region 1 Education Service Center on Research-Based Instructional Strategies (RBIS) in Reading and Math. This training focuses on improving instructional delivery through evidence-based practices that enhance clarity, modeling, scaffolding, and student engagement. Regional Coaches will attend alongside campus leaders to ensure alignment in coaching language, modeling expectations, and walkthrough feedback. APIs will use RBIS strategies during lesson internalization meetings, side-by-side coaching, lesson rehersals, and ongoing teacher coaching. Teachers will not attend the initial training directly but will receive the strategies through leadership-led coaching, rehearsal, and feedback cycles. RBIS will serve as a support to the Guidepost of Effective Teaching (GET) foundation for classroom expectations, strengthening lesson design, instructional delivery, and student outcomes across campuses. Batch Coaching Provider: VP of Schools & Regional Coaches Audience: Principals and Assistant Principals of Instruction (APIs) Session Timeline: Sept 2025 Description: Batch Coaching sessions are facilitated by the Vice President of Schools and Regional Coaches to strengthen instructional leadership capacity among Principals and Assistant Principals of Instruction. These sessions focus on core coaching strands such as lesson internalization, Know-Do chart development, and real-time coaching, Leaders engage in practice-based learning rather than passive training, rehearsing how to deliver high-quality feedback, co-plan with teachers, and correct instructional misconceptions during live lessons. Batch Coaching provides a collaborative, small-group environment where leaders observe modeling, practice coaching moves, and receive direct feedback to sharpen their instructional leadership execution. The intent is to ensure every campus leader can coach teachers with precision, clarity, and urgency."The Vice President of School Improvement (VPSI) will provide ongoing professional development to principals, assistant principals of instruction, instructional coaches, and campus leadership teams on ESF-aligned instructional systems, including DDI, PLC facilitation, observation and feedback, MTSS implementation, and STAAR-aligned lesson planning. Sessions will include Research-Based Instructional Strategies (RBIS) training delivered in partnership with the Education Service Center, Batch Coaching delivered by the VPSI and Regional Coaches, and MTSS leadership training delivered by the Regional MTSS team. Teachers will receive the instructional strategies through leader-led planning meetings, lesson internalization sessions, rehearsals, and feedback cycles to ensure alignment between leadership development and classroom practice. "MTSS Leadership Training Provider: DFW Regional Team & Region Education Service Center (Region Service Center) Audience: Principals, APIs, Counselors, MTSS/Student Support Teams, Teachers Session Timeline: July 16, Sept 11 (Org. Priority) - June 2027 Description Multi-Tiered Systems of Support (MTSS) training was initially delivered by the Regional Team to establish foundational systems for identifying, monitoring, and responding to students’ academic, behavioral, and social-emotional needs. This initial phase focuses on building campus leadership competency in Tier 1 instructional supports, Tier 2 intervention protocols, and Tier 3 individualized planning. Following the Regional Team’s training, the Education Service Center reinforces and deepens campus capacity through ongoing sessions, calibration support, and technical assistance. These follow-up trainings emphasize data-driven decision-making, progress monitoring tools, intervention scheduling, and consistent documentation practices. Principals, APIs, and student support leaders apply MTSS frameworks when leading intervention meetings, collaborating with special education and counseling teams, and coaching teachers on differentiation and progress tracking. The goal is to build a sustainable, aligned intervention system that supports student growth and reduces disproportionality across campuses." | "Differentiation of RBIS Training for Inexperienced and/or Ineffective Teachers & Leaders Inexperienced and ineffective leaders/teachers will receive layered support in RBIS through additional modeling, scaffolded planning templates, and guided practice on core instructional strategies such as modeling, checking for understanding, and scaffolding. These leaders will participate in small-group coaching sessions with Regional Content Coaches and will rehearse RBIS moves before implementing them with teachers. Increased observation and feedback cycles will be provided to reinforce RBIS application during lesson internalization, PLC facilitation, and classroom walkthroughs. Batch Coaching Inexperienced Leaders (Less than 2 Years in Role) These leaders will receive enhanced scaffolding and foundational guidance during Batch Coaching sessions, including: Pre-Work Orientation: Introduction to core coaching tools such as Know-Do Charts, lesson internalization protocols, and feedback frameworks. Model & Imitate Cycles: Direct modeling by Regional Coaches followed by structured practice with scripts. Side-by-side Coaching: Step-by-step coaching rehearsals before implementing with teachers. Ineffective or Developing Leaders Leaders who have demonstrated gaps in implementation or performance will receive high-touch, corrective support: Real-Time Coaching: Immediate feedback during practice with opportunities to retry on the spot. Micro-Coaching Cycles: Focused on one strand at a time (e.g., feedback delivery, rigor checks) until mastery is demonstrated. Accountability Checkpoints: Specific growth goals built into individual coaching logs and leadership development plans." Training for inexperienced or ineffective leaders will be differentiated through increased modeling, scaffolded planning tools, guided practice, and targeted coaching. The VPSI will provide small-group leadership rehearsals, model-and-imitate cycles, and step-by-step coaching support to build foundational skills in DDI, observation and feedback, lesson internalization, and PLC facilitation. Leaders demonstrating limited progress will receive intensified support, including real-time coaching, micro-coaching cycles focused on one leadership competency at a time, and heightened accountability checkpoints documented through coaching logs and leadership development plans. "MTSS Training Inexperienced leaders and leaders identified as needing additional support will receive enhanced MTSS coaching through smaller cohort training, targeted intervention planning sessions, and side-by-side support from Regional MTSS specialists. These leaders will be guided through model intervention meetings and progress monitoring protocols with additional time allocated for practice and feedback. The VP of School Improvement and Regional Team members will provide individualized coaching on Tier 1–3 systems, documentation procedures, and intervention referrals to ensure readiness and accurate execution of MTSS responsibilities." | tools used to assess whether training practices are being implemented with fidelity: G-E-T Rubric Input (School Status) Leadership Quick Check Reports Feedback from Lesson Internalization Feedback from Student Work Analysis Protocol Implementation Implementation of the training will be evaluated using TEA-aligned classroom walkthrough tools, leadership coaching logs, the GET rubric, SchoolStatus observation data, student work analysis protocols, and PLC documentation. These tools will allow the VPSI to measure the fidelity of RBIS, HQIM alignment, MTSS expectations, DDI practices, and observation and feedback execution. Evidence from each tool will be used during weekly leadership meetings, PTG reviews, and tactical sessions to assess whether leaders are applying the training consistently and to determine whether additional support or corrective action is required. Implementation of MTSS practices will be evaluated using intervention tracking tools, campus MTSS implementation rubrics, and leadership coaching logs. Key look-fors will include evidence of scheduled intervention meetings, use of progress monitoring data, proper documentation of Tier 2 and Tier 3 supports, and alignment of services for House Bill 1416 students. Observers will also monitor academic block placement and reassignment decisions based on student need or improvement, ensuring that intervention time is data-driven and responsive. Fidelity to intervention referral processes, collaboration with counselors, SPED, and EB teams, and follow-up actions for student support plans will also be reviewed. | Each teacher will receive ongoing observation and feedback through a layered system of daily, weekly, and formal coaching structures. The frequency and intensity of support will increase based on teacher need and priority status. Standard Frequency for All Teachers Daily Informal Power Walks with a focus on specific instructional strategies (e.g., engagement, questioning, lesson execution) Weekly Informal Observations with actionable feedback Increased Frequency for Priority Teachers (Inexperienced or Ineffective) Three observations per week (minimum), each with targeted instructional feedback Daily Real-Time Coaching using live correction, modeling, and rehearsal Increased touchpoints through lesson rehersals to reinforce strategy execution Each teacher will receive a weekly informal observation with actionable feedback tied to RBIS, lesson execution, TEKS alignment, and student engagement. Priority, inexperienced, or ineffective teachers will receive up to three observations per week, including real-time coaching and pre-lesson rehearsal to correct misconceptions before instruction occurs. Instructional leaders will reinforce feedback through weekly PLCs, planning meetings, and side-by-side coaching to ensure improvements are implemented with fidelity and monitored through ongoing walkthrough cycles. Leaders will receive weekly check-ins focused on MTSS implementation, with priority leaders receiving up to two to three monitoring sessions per week. During campus visits, the VP of School Improvement and Regional MTSS specialists will review intervention logs, academic block rosters, and reassignment decisions based on student need or improvement. Daily informal walkthroughs will be used to monitor Tier 1 instructional supports, including the application of lesson internalization feedback, scripting of student groupings, and scaffolds built for EB, SPED, and struggling learners. Teacher execution will also be tracked through engagement monitoring labs to ensure interventions are being applied consistently in classrooms. | To build capacity in supporting students within special populations, designated school leaders will participate in specialized Point-Person Webinars focused on EB, CSI, 504, and PBIS responsibilities. These sessions provide critical updates on compliance requirements, intervention protocols, and case management practices. Leaders receive guidance on progress monitoring expectations and referral processes, including Intervention Requests, ARD procedures, and RTI documentation, ensuring accurate and timely support for students. In addition to these webinars, administrators and instructional leaders will engage in MTSS and intervention training delivered by the Regional Team and the Education Service Center. This training develops a strong understanding of tiered intervention systems for both academic and behavioral needs, emphasizing data-based decision-making through the use of progress monitoring tools. Leaders also receive support in establishing effective collaboration structures with counselors, interventionists, and SPED case managers to ensure students receive coordinated and comprehensive services Teachers and administrators will receive targeted capacity building on supporting special populations through EB/ELPS-aligned instructional routines, SPED accommodations, 504 supports, and MTSS Tier 1–3 intervention structures. The VPSI and Regional MTSS specialists will provide coaching on designing Tier 1 scaffolds, grouping students for Tier 2 and Tier 3 interventions, analyzing progress monitoring data, and integrating language development practices into daily instruction. Administrators will also receive guidance on using intervention logs, HB 1416 documentation, and student work protocols to make data-driven instructional adjustments for EB, SPED, 504, and struggling learners
|  |  | "RELAY Effective Teacher Coaching: Observation Feedback Workshop for School Leaders Provider: Relay Graduate School of Education Audience: Principal Supervisors, Principals, Assistant Principals of Instruction (APIs) Session Date: Implementation Timeline: October 2025 -May 2026 Description: Exceptional school leaders succeed because of how they use their time, what they do, and how and when they do it. Observation and Feedback will emphasize this principle and demonstrate the most effective ways to coach every teacher to improve student learning on a frequent basis. You will learn the four keys to effective observation and feedback, including locking in frequent and regular observations, identifying the one or two most important areas for growth, giving direct face-to-face feedback that practices specific action steps for improvement, and creating systems to ensure feedback translates to practice. In addition, you will have opportunities to practice skills you learn by participating in two simulations and ongoing video reviews for self-reflection. " Visible Learning For Teachers- Maximizing Impact Learning Book Study with Campus Leaders Provider: Sabrina Franco, Vice President of Schools Audience: Principal and Assistant Principals of Instruction Session Timeline: Implementation Timeline: Description: The Visible Learning for Teachers book study will help Texas educators strengthen instructional practices aligned to evidence-based strategies proven to improve student learning. By exploring John Hattie’s research on what has the greatest impact on achievement, teachers will deepen their understanding of how to make learning visible—clarifying learning intentions, using success criteria, and providing effective feedback that accelerates growth. Through collaborative discussion and application, teachers will learn to prioritize high-impact practices, such as formative assessment, explicit teaching, and student self-reflection. These practices directly align with Texas school improvement priorities, including improving student outcomes on the State of Texas Assessments of Academic Readiness (STAAR) and closing achievement gaps. Ultimately, this book study supports a culture of continuous improvement across campuses by equipping teachers with research-driven tools to plan, teach, and reflect with greater precision and intentionality—driving stronger results for all students. | Leaders with fewer than two years of experience, or those identified as needing additional support, will receive intensified, side-by-side coaching directly from the Vice President of Schools. These leaders will take part in extended Relay practice labs that include modeling, rehearsal, and targeted feedback. They will also participate in shadow coaching sessions to observe live examples of corrective feedback in action. To accelerate their growth, they will have more frequent observation and coaching touchpoints,up to two or three times per week, focused on mastering Relay competencies such as delivering precise feedback, addressing instructional misconceptions, and leading rehearsal-based development sessions. | The implementation of Relay coaching practices will be monitored through leadership coaching logs, PLC and internalization observation forms, real-time coaching rubrics, and the use of SchoolStatus Boost, the platform used to share teacher ratings. Leaders will document observation notes and GET ratings within the platform. In addition, leaders will be evaluated using district-created Quick Checks, which serve as formative tools to coach and develop leadership skills. Evidence of success will include consistent use of Relay coaching language (e.g., probe, praise, correct), delivery of live corrective feedback, use of rehearsal-based coaching structures, and clear alignment between leader feedback and teacher instructional practice. | Teachers will engage in weekly informal observations with focused feedback aligned to Relay coaching protocols. Priority or developing teachers will participate in Tight Loop Coaching, a strategy that incorporates real-time feedback and increased observation frequency—up to three times per week—to accelerate growth and strengthen instructional practices. Daily power walks will be used to reinforce targeted strategies, with coaching corrections provided in the moment to ensure immediate application of Relay techniques. Leaders will also receive feedback on the impact of their coaching, using evidence from classroom trends, teacher performance data, and observed improvements in instructional execution to refine their own coaching effectiveness | Leaders will receive training on how to apply Relay coaching protocols when supporting special populations, including students receiving special education services and Emergent Bilingual learners. During coaching sessions, leaders will model how to integrate instructional scaffolds, language supports, and behavior interventions into feedback and rehearsal practices. Both administrators and teachers will be guided on delivering corrective feedback that helps adjust instruction to meet diverse learner needs. Additionally, they will collaborate closely with intervention teams to ensure coaching practices are aligned with individual student support plans.
|  |  | RBIS – Research-Based Instructional Strategies Provider: Region 1 Education Service Center Audience: Principals, Assistant Principals of Instruction (APIs), Regional Content Coaches, and Teacerhs Session Timeline: RLA Oct 28, 2025 and Math Nov 5, 2025 Description Principals, Assistant Principals of Instruction, and Regional Content Coaches, and Teachers will receive training from Region 1 Education Service Center on Research-Based Instructional Strategies (RBIS) in Reading and Math. This training focuses on improving instructional delivery through evidence-based practices that enhance clarity, modeling, scaffolding, and student engagement. Regional Coaches will attend alongside campus leaders to ensure alignment in coaching language, modeling expectations, and walkthrough feedback. APIs will use RBIS strategies during lesson internalization meetings, side-by-side coaching, lesson rehersals, and ongoing teacher coaching. Teachers will not attend the initial training directly but will receive the strategies through leadership-led coaching, rehearsal, and feedback cycles. RBIS will serve as a support to the Guidepost of Effective Teaching (GET) foundation for classroom expectations, strengthening lesson design, instructional delivery, and student outcomes across campuses. | Differentiation of RBIS Training for Inexperienced and/or Ineffective Teachers & Leaders Inexperienced and ineffective leaders/teachers will receive layered support in RBIS through additional modeling, scaffolded planning templates, and guided practice on core instructional strategies such as modeling, checking for understanding, and scaffolding. These leaders will participate in small-group coaching sessions with Regional Content Coaches and will rehearse RBIS moves before implementing them with teachers. Increased observation and feedback cycles will be provided to reinforce RBIS application during lesson internalization, PLC facilitation, and classroom walkthroughs. | Implementation of RBIS will be evaluated using classroom walkthrough tools, data extracted from School Status, leadership coaching logs, and student work analysis protocols. Key look-fors will include the use of modeling and guided practice, checks for understanding, scaffolding strategies, and alignment of instructional delivery to lesson objectives. Evidence of teacher adjustment based on student responses and the use of corrective feedback will also be monitored. | Teachers will receive weekly informal walkthroughs with feedback focused on RBIS implementation, including modeling, CFUs, and scaffolding. Priority or developing teachers will be observed up to three times per week to ensure consistent use of RBIS strategies in instruction. Real-time coaching and corrective feedback will be provided during planning meetings, PLCs, and classroom practice to reinforce RBIS routines and teacher execution. In addition, Assistant Principals of Instruction (APIs) will receive coaching from Regional Team members trained in RBIS to ensure continuity of practice from leader development to classroom implementation across all content areas. | Teachers and leaders will receive support in applying RBIS strategies to instruction for special populations, including EB, SPED, and 504 students. Training will include how to scaffold instruction, adjust questioning, and provide language supports within core lessons. Regional Coaches will model how to use RBIS strategies during intervention planning and student work analysis to ensure instruction is responsive to diverse learning needs. APIs and teachers will also receive guidance on integrating RBIS with MTSS interventions to strengthen support for students requiring additional academic or behavioral assistance.
|  |  | IDEA Teacher Collaboration Provider: Regional Team Members and Expert Teachers Audience: Teachers, Assistant Principals of Instruction, and Principals Session Timeline: Description: The Teacher Collaboration Professional Development is designed to empower educators through teacher-driven, collaborative problem-solving that strengthens instructional excellence and accelerates student learning. This professional learning series cultivates shared ownership, deep content knowledge, and innovative instructional practice. Each collaboration cycle—held in October, January, and March—creates structured opportunities for teachers to analyze data, align instruction to standards, and plan responsive reteach lessons that meet the needs of all learners. Guided by the key tenets of effective collaboration, these sessions emphasize that collaboration is core, not extra; embedded in practice, content-driven, continuous, and focused on building a culture of growth and collective efficacy. Through this professional development, teachers and leaders engage as partners in learning, ensuring that collaboration directly translates to stronger classroom instruction, higher student achievement, and a sustained culture of excellence across the district. | Training will be differentiated by providing targeted scaffolds and coaching supports for inexperienced or developing teachers and leaders. Participants with less than two years in the role will engage in guided application sessions where concepts from Visible Learning for Teachers—such as learning intentions, success criteria, and feedback—are modeled and practiced with real-time coaching. For ineffective or struggling practitioners, support will include Tight Loop Coaching with increased observation frequency, focused feedback, and opportunities for rehearsal-based practice to build confidence and skill mastery. Experienced and effective participants will engage in collaborative problem-solving and peer facilitation during PLCs, applying Visible Learning strategies to complex instructional challenges and mentoring peers. | Implementation of key learnings from the Visible Learning for Teachers book study will be evaluated using a classroom walkthrough tool and leadership coaching logs aligned to Hattie’s high-impact strategies. These tools will capture evidence of how effectively teachers and leaders apply Visible Learning principles in daily practice. Look-Fors: Clear learning intentions and success criteria communicated to students Evidence of feedback that moves learning forward (specific, timely, and actionable) Use of formative assessment to adjust instruction in real time Opportunities for student self-assessment and reflection Visible alignment between teacher clarity, student engagement, and learning outcomes Leaders providing coaching and feedback focused on the impact of instruction rather than compliance This approach ensures that implementation is monitored through both instructional and leadership lenses, promoting consistent use of evidence-based practices that improve student achievement and support ongoing school improvement | Each teacher will receive weekly informal observations from an instructional leader or coach, followed by timely feedback within 24 to 48 hours. Teachers identified as priority or developing will participate in Tight Loop Coaching, receiving observations and feedback two to three times per week to accelerate growth and ensure consistent application of Visible Learning for Teachers strategies. Feedback will focus on implementation of high-impact practices such as communicating clear learning intentions and success criteria, using formative assessment to guide instruction, and providing feedback that moves learning forward. This consistent observation and coaching cadence will reinforce transfer of book study concepts into daily classroom practice. | Teachers and administrators will receive targeted training and coaching to apply Visible Learning for Teachers strategies in support of special populations, including SPED and Emergent Bilingual students. Professional learning will focus on differentiating learning intentions and success criteria, integrating scaffolds and language supports, using formative assessment and feedback to adjust instruction, collaborating with SPED and intervention teams to align with IEP and LPAC goals, and engaging in modeling and rehearsal-based coaching to embed supports within daily instruction. These efforts will ensure equitable access, accelerate growth, and close achievement gaps for all learners.
|  |  | IDEA Principal Collab (Leadership Alignment Sessions) Provider: VP of Schools and Regional Team Members Audience: Principals Session Timeline: Sept. 18 Description: Principal Collaborations are monthly leadership alignment sessions designed exclusively for Principals to receive focused coaching, professional development, and strategic problem-solving support. Facilitated by the VP of Schools and Regional Leadership Teams, these sessions ensure principals are equipped to lead instructional implementation, manage upcoming priorities, and drive campus performance goals with clarity and coherence. Each region determines the content focus based on need, but sessions consistently include: Time to complete required Roadmaps Unpacking upcoming priorities in the Principal Playbook Previewing what’s approaching in API trainings to ensure alignment and coherence across leadership teams In addition to planning and alignment, Principal Collaborations provide space for principals to: Analyze campus data and address leadership challenges Calibrate expectations and share best practices Rehearse leadership moves such as PLC facilitation, culture resets, and feedback practices Regions are encouraged to incorporate targeted sessions, especially for new or developing principals such as: Setting Priorities and aligning master calendars Preparing Professional Development for staff Planning Schoolwide Culture Resets to reinforce expectations and climate By design, Principal Collaborations build a unified approach to instructional leadership, accountability, and campus readiness—ensuring that principals lead proactively rather than reactively as organizational priorities unfold. | Training will be differentiated through tiered coaching and modeling supports. Inexperienced or developing teachers and leaders will participate in guided practice sessions where facilitators model each phase of the Weekly Data Meeting process—data analysis, identifying misconceptions, and planning reteach lessons. They will also receive Tight Loop Coaching, including increased observation frequency, real-time feedback, and rehearsal opportunities to build skill and confidence. Experienced leaders will engage in peer collaboration and case study analysis, applying the protocols to complex instructional scenarios and coaching others toward mastery. | Implementation will be monitored through the PLC Observation Tool and Leadership Coaching Logs. These tools will measure how effectively teams are applying RELAY data meeting structures. Key Look-Fors include: Alignment of discussion to standards and student work samples Identification of root causes of misconceptions Clear and actionable reteach plans aligned to student needs Evidence of teacher ownership of data analysis and next steps Leaders using RELAY coaching protocols to guide and deepen reflection | Each teacher will receive weekly informal observations with follow-up feedback focused on the execution of reteach plans and use of data in instruction. Teachers identified as priority or developing will engage in Tight Loop Coaching, receiving feedback two to three times per week to strengthen data-driven decision-making and classroom implementation of reteach lessons. | Teachers and leaders will receive training and coaching on how to apply data-driven decision-making to support special populations, including students receiving SPED and Emergent Bilingual services. Supports will focus on: Analyzing data disaggregated by student group to identify performance trends. Differentiating reteach plans using scaffolds, language supports, and accommodations. Collaborating with SPED and intervention teams to align reteach actions with IEP and LPAC goals. Modeling how to embed supports during PLC discussions and lesson planning.
|  |  | IDEA VPS Collaborations (Executive-Level Leadership Development) Provider: National Vice President of Schools Audience: Vice Presidents of Schools (VPS) Session Timeline: July 2025-June 2025 Description: VPS Collaborations are high-level executive leadership sessions facilitated by the National Vice President of Schools. These sessions focus on strategic leadership priorities such as Path to an A and Rigor Threats, equipping Vice Presidents of Schools with the tools to drive consistent performance across regions. The collaborative format provides space for structured problem-solving, data analysis, leadership scenario planning, and accountability alignment. VPS participants engage in reflective dialogue, share implementation challenges, and refine strategies for supporting principals and APIs. Unlike technical coaching, VPS Collaborations emphasize executive decision-making, system alignment, and large-scale instructional leadership execution. These sessions ensure a united leadership vision across the organization. | Training will be differentiated through tiered collaboration structures and coaching supports. Inexperienced or developing teachers/leaders (less than two years in role) will receive guided practice, modeling, and rehearsal opportunities during Teacher Collaboration sessions to strengthen facilitation and data analysis skills. They will also participate in Tight Loop Coaching cycles with Regional Content Coaches. They will recieve frequent observation and feedback focused on planning, questioning, and reteach design. Experienced and proficient participants will engage in peer facilitation, case studies, and reflective protocols, supporting leadership development by modeling effective collaboration and mentoring colleagues. | Implementation will be measured through the District Classroom Observation Tool and Leadership Coaching Logs, which capture the quality and consistency of collaboration practices across teams. Look-Fors include: Alignment of discussions to content standards and student data Evidence of collective problem-solving and teacher-driven decision-making Clear reteach plans that address identified misconceptions Use of effective facilitation protocols that promote equitable participation Leaders providing action-oriented feedback linked to improved instruction These tools will ensure fidelity to the Teacher Collaboration model and provide data for continuous improvement at the campus and regional levels. | Each teacher will receive weekly formative observations from an instructional leader or coach, with feedback provided within 24–48 hours. Teachers identified as priority or developing will participate in Tight Loop Coaching with campus leaders and regional content coaches, receiving two to three observations per week focused on implementing strategies discussed during Teacher Collaboration sessions. This cadence ensures that professional learning translates into visible improvements in classroom instruction and student learning outcomes. | Teachers and leaders will receive targeted supports to ensure collaboration practices address the needs of all learners, including students receiving SPED, Emergent Bilingual, and intervention services. Training will focus on: Analyzing disaggregated student data to identify gaps for special populations Embedding instructional scaffolds, accommodations, and language supports within reteach planning Collaborating with SPED, EB, and intervention teams to align instructional adjustments with IEP and LPAC goals Using Visible Learning and Relay coaching principles to strengthen feedback and differentiation
|  |  | Professional Learning Communites (Grade-Level) Provider: Regional Content Coaches, Principals, Assistant Principals of Instruction, VP of Schools Audience: Teachers and Co-Teachers Session Timeline: October 2025-May 2026 Description: Weekly Professional Learning Community (PLC) sessions will serve as the primary professional development structure to improve instructional effectiveness and student achievement. PLCs will be facilitated by the Assistant Principal of Instruction (API) with coaching support from the Principal and Principal Manager. Principal Manager: Provides coaching and feedback to the Principal on PLC facilitation and alignment to the Criteria for Success (CFS). Principal: Oversees the implementation of the PLC protocol and ensures data, planning, and accountability structures are in place. Assistant Principals/Instructional Coaches: Facilitate content-specific PLCs weekly using the district PLC agenda template (data review, standard deconstruction, instructional planning, exit ticket alignment, next steps). Teachers: Engage in data analysis, collaborative planning, and commit to actionable next steps for reteach and extension. | Inexperienced principals (less than two years in role) and principals identified as needing additional support will receive intensified and tiered coaching during Principal Collaborations. These leaders will engage in side-by-side coaching with the VP of Schools, as well as Regional and National Leaders, to rehearse core leadership practices such as PLC facilitation, culture resets, and Roadmap execution. As an additional layer of support, they will work directly with the VP of School Improvement under a scripted plan of improvement to address specific leadership gaps. These principals will also attend Principal Academy sessions and receive targeted breakout support, leadership modeling, and scenario-based practice to build foundational readiness and ensure consistent execution. | Implementation of leadership practices from Principal Collaborations will be evaluated using leadership coaching logs, principal progress monitoring tools, and leadership observation rubrics. Key look-fors will include evidence of strategic planning through completed Roadmaps, facilitation of effective PLCs, execution of culture reset plans, data-driven leadership decisions, and the application of collaboration practices discussed during sessions. Fidelity to follow-up actions and leadership reflection will also be monitored. | Principals will engage in weekly leadership check-ins with the VP of Schools. During these sessions, the VP of Schools will monitor progress and determine whether additional support is needed from regional or national content leads. Principals identified as needing intensified support or placed on a plan of improvement will receive up to two to three coaching sessions per week, including real-time leadership feedback during PLCs, walkthroughs, and culture implementation. Daily informal leadership walkthroughs will also occur to monitor application of strategies introduced during Principal Collaborations. | Principals will receive leadership guidance on supporting special populations through targeted collaboration with regional MTSS, EB, SPED, and 504 point leads. During Principal Collaborations, leaders will participate in sessions focused on designing and monitoring intervention systems, including required intervention and acceleration supports for House Bill 1416 students. Implementation of these supports will be closely monitored by the VP of School Improvement through campus visits conducted at least twice per week, ensuring principals are applying feedback and effectively leading intervention structures. Additional assistance may be allocated from regional or national specialists to strengthen intervention planning, progress monitoring, and data review protocols for diverse learners.
|  |  |  | New or developing Vice Presidents of Schools will receive differentiated support during VPS Collaborations through smaller executive breakout sessions, strategic leadership case studies, and targeted coaching. These VPS leaders will receive direct coaching and support from the National Vice President of Schools and, when necessary, from the Regional Executive Director. This additional layer of support will focus on strengthening executive decision-making, system alignment, performance management, and the execution of regional priorities such as Path to an A and Rigor Threats. Follow-up executive coaching will be provided to reinforce readiness and improve leadership outcomes across regions. | Implementation of executive leadership strategies from VPS Collaborations will be evaluated using executive coaching logs, regional performance dashboards, and leadership alignment trackers. Key look-fors will include clarity of regional priorities, consistency in leadership messaging, progress toward Path to an A goals, response to rigor threats, and alignment between VPS directives and campus execution. Evidence of strategic decision-making, escalation protocols, and follow-through on leadership commitments will also be monitored. | Vice Presidents of Schools will receive executive feedback through bi-weekly strategic check-ins with the National Vice President of Schools or the Regional Executive Director. VPS leaders requiring additional support may receive weekly coaching sessions focused on leadership alignment, regional performance risks, and escalation decisions. Informal leadership touchpoints will occur during national leadership meetings and data reviews to ensure timely calibration and follow-through on organizational priorities such as Path to an A and Rigor Threats. | Vice Presidents of Schools will receive support on overseeing services for special populations through collaboration with national and regional specialists in MTSS, EB, SPED, and 504. During VPS Collaborations, leaders will analyze disproportionality data, review intervention acceleration plans for House Bill 1416 students, and align regional expectations for inclusive instructional practices. VPS leaders will be equipped to hold principals accountable for intervention implementation, progress monitoring, and the allocation of resources necessary to meet the needs of diverse learners across campuses.
|  |  |  | Training will be differentiated through tiered professional learning structures and coaching supports that meet teachers and leaders where they are in their development. Inexperienced (less than 2 years in role) teachers and leaders will participate in guided learning sessions that include modeling, practice, and scaffolded planning support to strengthen foundational instructional skills and classroom management. Ineffective or developing teachers/leaders will receive Tight Loop Coaching with campus leaders. They will have increased observation frequency, real-time feedback, and follow-up modeling designed to accelerate growth and ensure transfer of learning to classroom practice. Proficient and highly effective educators will engage in peer collaboration and facilitation, leading portions of PD, sharing exemplars, and supporting colleagues through coaching and reflection. | Implementation of Early Release PD will be evaluated using the Classroom Walkthrough Tool, Leadership Coaching Logs, and PLC Observation Forms to monitor how professional learning translates into classroom instruction. Key Look-Fors include: Evidence of standards-aligned, rigorous instruction connected to PD topics Use of instructional strategies modeled during PD (e.g., checks for understanding, student discourse, scaffolding) Clear lesson alignment to data-informed reteach plans Student engagement and active learning aligned to learning objectives Leaders providing actionable feedback that drives continuous improvement These tools ensure consistent monitoring of instructional practices, provide actionable data for leader coaching, and inform future PD cycles. | Training will be differentiated through tiered professional learning structures and coaching supports that meet teachers and leaders where they are in their development. Inexperienced (less than 2 years in role) teachers and leaders will participate in guided learning sessions that include modeling, practice, and scaffolded planning support to strengthen foundational instructional skills and classroom management. Ineffective or developing teachers/leaders will receive Tight Loop Coaching with campus leaders. They will have increased observation frequency, real-time feedback, and follow-up modeling designed to accelerate growth and ensure transfer of learning to classroom practice. Proficient and highly effective educators will engage in peer collaboration and facilitation, leading portions of PD, sharing exemplars, and supporting colleagues through coaching and reflection. | Teachers and administrators will receive targeted capacity-building supports focused on meeting the needs of special populations, including SPED, Emergent Bilingual, 504, and Tier 2/3 students. Training will emphasize: Differentiating instruction and scaffolding to ensure access to grade-level content Using formative assessment data to identify and address learning gaps Collaborating with SPED, EB, and intervention teams to align instructional practices with IEP and LPAC goals Embedding language supports and behavior interventions into core instruction Modeling inclusive practices during PD sessions and follow-up coaching cycles These supports ensure all students, regardless of learning profile, receive high-quality, differentiated instruction that promotes equity and accelerates growth.
|  |  |  | Inexperienced and developing teachers will receive additional support through Tiered PLC participation and coaching cycles. Novice teachers will have pre-PLC prep sessions with the API to review data and exemplars in advance. Ineffective or developing teachers will participate in real-time coaching and modeling during PLCs and subsequent classroom follow-ups. Leaders with less than two years in role will receive weekly PLC feedback from the Principal and will co-facilitate PLCs to build skill in data analysis and instructional planning. | Implementation will be evaluated using the PLC Criteria for Success and the Classroom Walkthrough Tool. Look-fors include: Data drives instructional decisions and reteach plans. Team discussions focus on student learning, not logistics. Teachers leave with a concrete plan for reteach or extension. Exit tickets are aligned to the rigor of the standard. Commitments are tracked and reviewed in subsequent PLCs. | Every teacher will be observed weekly with feedback delivered within 24–48 hours using the “See It, Name It, Do It” coaching model. Follow-up support will connect directly to PLC commitments and instructional next steps. | Capacity building will emphasize equitable access and differentiation through PLC discussions and PD sessions. Teachers will plan scaffolds and accommodations during the Instructional Planning step of PLCs for Emergent Bilinguals, students with foundational gaps, and Special Education scholars. Administrators will receive targeted coaching on data disaggregation by student group and on ensuring IEP and LPAC accommodations are embedded in lesson design. The CSI Lens on PLCs will be used weekly to ensure instruction meets the needs of all special populations.

## Milestones
Criteria for Success
How will the strategy be implemented? -Milestones include all activities needed to fully implement the program or strategy, covering planning and implementation stages. -Milestones include all upfront capacity building, implementation action steps, and ongoing support and coaching touchpoints, and student assessment cycles. -Milestones cover, at a minimum, the two school years that the campus is required to implement the plan.
Question | List or copy and paste all SI - identified campuses below | Please share the key milestones for this strategy through August 2026 for TIP, and keymilestones through August 2027 for TAP. Be sure to include milestones related to capacity building efforts, resources/tool deployment, implementation checkpoints, coaching touchpoints, and assessment cycles.
Additional Instructions | List all SI campuses in the district | Timeframe is, at minimum, through end of SY 26-27 for TIP and through end of SY 27-28 for TAP.
Answer(s) | IDEA Achieve Academy | Achieve Academy Milestones
| IDEA La Joya Academy | La Joya Academy Milestones 25-26-CSI
| IDEA Eastside College Prep | Milestones-Eastside CP .docx
| IDEA Najim Academy | Milestones Najim TIP 2025.docx
| IDEA Spears Academy | NewSpears TAP Milestone Document Draft10.17.25.docx
| IDEA Spears College Prep | NewSpears TAP Milestone Document Draft10.17.25.docx

## Performance Management
Criteria for Success
Has the district outlined a performance management plan that ensures the strategy will be implemented with fidelity? -There is a plan for plan performance management, including superintendent and other key leadership review of metrics and progress at a semesterly cadence. -The response describes: +Who will review progress towards milestones, +How frequently progress is reviewed, +How progress data will be collected, and +How it is shared with district leadership and other relevant stakeholders
Question | List or copy and paste all SI - identified campuses below | Please describe how district and campus leaders will monitor the successful implementation of this plan. | Who will be responsible for reviewing progress towards the milestones described in the previous section? | How frequently will progress toward milestones be reviewed? | How will milestone progress data be collected? | How will milestone progress data be shared with district leadership and other relevant stakeholders?
Additional Instructions | List all SI campuses in the district
Answer(s) |  | During the “Just a Goal ‘G’ Meetings,” campus principals, assistant principals of instruction, counselors, and assistant principals of operations presented their school improvement goals, strategies, and progress monitoring milestones to the Regional Superintendent, Vice President of School Improvement, Regional Executive Director, Vice President of Schools, Regional Director, and regional instructional coaches. The purpose of these meetings was to receive targeted feedback on the quality and alignment of goals and strategies. | Stakeholders responsible for reviewing progress toward milestones through this mechanism include the Regional Superintendent, Vice President of School Improvement, Regional Executive Director, Vice President of Schools, Regional Director, and regional instructional coaches. | Through this annual mechanism, milestones are presented and reviewed as part of the goal and strategy presentation process. | Milestone progress data will be collected through multiple monitoring systems, including observation and feedback trackers, coaching logs, PLC documentation, interim assessment results, and MTSS intervention progress reports. The principal will follow up with each lead team member during weekly check-ins and tactical meetings to ensure action plans are being implemented with fidelity. Progress Toward Goal (PTG) meetings will be held after Quarter 2 and Quarter 3 to review collected data, evaluate milestones, and adjust plans based on evidence of progress and student outcomes. | Milestone progress and data will be shared during Progress Toward Goal Meetings, where campus leaders and regional/national leadership teams reconvene to review data aligned to the campus’s academic and cultural goals. Progress toward goals, milestones, and milestone checkpoints will serve as key indicators of progress and success.
|  | On October 1, 2025, the campus participated in an IDEA School Review that met the requirements of TEC 39A.053 for a comprehensive local diagnostic. This annual School Review, conducted for priority campuses, serves as a formal quality audit and is used as the local diagnostic process in the 2025–2026 school year. Findings from the School Review established the baseline for school improvement and directly informed milestone development in the targeted improvement plan. | Progress toward milestones will be reviewed by the School Review team, which includes the Regional Superintendent, Vice President of School Improvement (VPSI), Vice President of Schools, Regional Executive Director, and regional instructional coaches. These district and regional leaders collectively analyze findings from the School Review to determine whether the campus is making sufficient progress toward its turnaround milestones. Campus principals and Assistant Principals of Instruction (APIs) are also responsible for responding to feedback and adjusting campus action steps based on the priorities identified during the review. This joint accountability between campus and regional leadership ensures that milestone progress is continuously aligned to the expectations established through the local diagnostic process. | Progress toward milestones identified in the School Review will be formally reviewed on an annual basis during the comprehensive School Review cycle, with follow-up monitoring occurring during scheduled leadership check-ins and quarterly data meetings. While the School Review establishes the baseline and priorities for the year, district and regional leaders revisit these priorities throughout the year to ensure that corrective actions are being implemented and that milestones remain on track. | Milestone progress data will be collected through the evidence gathered during the School Review process, including classroom observations, teacher and leader interviews, lesson internalization artifacts, Leadership Core Calendars, coaching and feedback documentation, and student culture systems. Review teams analyze instructional delivery, planning practices, culture implementation, and leadership systems against the priorities identified in the local diagnostic. This evidence is used to assess the extent to which the campus is implementing strategies tied to turnaround milestones and to determine whether progress is on track, stalled, or in need of targeted intervention. | Milestone progress data gathered through the School Review will be shared with district leadership and stakeholders through multiple communication and accountability structures. Formal feedback is delivered during post-review debrief sessions with campus and regional leadership, where findings and priority actions are documented and aligned to turnaround milestones. Progress updates are then revisited in leadership tacticals and principal check-ins, where action steps and implementation evidence are monitored. For broader stakeholder engagement, data will also be shared during family engagement events and campus data conferences to ensure transparency around academic and cultural goals. In addition, milestones tied to instructional practice are reinforced through ongoing teacher coaching cycles, ensuring that classroom-level implementation remains aligned to expectations set during the School Review. This layered approach ensures that progress toward milestones is communicated clearly, owned collectively, and acted upon consistently across all levels of the campus community.
|  | District and campus leaders will monitor the successful implementation of this plan through structured Progress Toward Goal (PTG) meetings. During the PTG meeting, leaders and campus teams engage in a consultancy-style protocol where they present outcome data, receive feedback, and are asked probing questions to deepen their analysis and refine their strategies. | Progress toward milestones will be jointly reviewed during Progress Toward Goal (PTG) meetings by the Executive Director (ED), Vice President of School Improvement (VPSI), Vice President of Schools, campus principals, and Assistant Principals of Instruction (APIs), with oversight and support from regional and national leadership teams. | Progress toward milestones will be formally reviewed during Progress Toward Goal (PTG) meetings held after Quarter 2 and Quarter 3. These mid-year and spring reviews allow district and campus leaders to assess the effectiveness of implemented strategies, analyze outcome trends, and determine whether current action steps are sufficient to meet end-of-year goals. | Milestone progress data will be collected through the PTG pre-work and Outcomes–Causes–Solutions (OCS) analysis completed by each campus leader prior to the meeting. Leaders will gather and submit key evidence, including formative assessment results, interim data, coaching and observation logs, PLC artifacts, and implementation progress toward action steps. During PTG sessions, this data is presented, analyzed, and refined through feedback and questioning, ensuring that milestone progress is grounded in both quantitative outcomes and qualitative implementation evidence. | Milestone progress data will be shared through collaborative discussion and documentation during Progress Toward Goal (PTG) meetings, where campus and district leaders engage in a consultancy process to review Outcomes–Causes–Solutions analyses and agreed-upon next steps. Following each PTG, updated action plans and milestone adjustments will be entered into shared tactical documents and progress trackers, which are accessible to regional and national support teams. Key insights, progress updates, and required interventions will be communicated to district leadership through follow-up check-ins and tactical meetings, ensuring transparency, accountability, and ongoing support for successful plan implementation.
|  | Successful implementation of the plan will be monitored through weekly Campus Tactical Meetings, led by the principal and attended by all Assistant Principals of Instruction (APIs) and the Assistant Principal of Operations (APO). These tacticals are structured, results-focused leadership meetings that review progress toward academic and operational milestones identified in the turnaround plan. During each tactical, campus leaders analyze instructional implementation, review student performance trends, and assess the status of action steps related to curriculum delivery, culture systems, and intervention supports. The principal facilitates problem-solving and alignment, ensuring that APIs and the APO are held accountable for executing their assigned priorities. Any barriers identified are assigned immediate action steps, and follow-up is monitored in subsequent tacticals, creating a continuous cycle of review, adjustment, and support. This campus-based monitoring structure ensures real-time oversight and shared ownership among all members of the leadership team. | Progress toward milestones will be reviewed by the campus leadership team during weekly Campus Tactical Meetings. This team is led by the principal and includes all Assistant Principals of Instruction (APIs) and the Assistant Principal of Operations (APO). The principal is responsible for facilitating the review of milestone progress and ensuring alignment to the turnaround plan, while APIs provide updates on instructional implementation and student performance, and the APO reports on operational supports that impact execution. Together, this team collaboratively assesses whether milestones are being met, identifies barriers to progress, and determines if adjustments or additional support are needed. This shared responsibility ensures that every member of the leadership team remains accountable for driving progress toward campus goals. | Progress toward milestones will be reviewed weekly during Campus Tactical Meetings. These meetings are embedded in the campus leadership calendar to ensure a consistent cadence of monitoring and accountability. The weekly frequency allows the principal, APIs, and APO to track implementation in real time, respond quickly to emerging challenges, and adjust strategies before gaps widen. By reviewing milestones every week—rather than waiting for quarterly checkpoints—the campus leadership team maintains an active oversight cycle that supports continuous improvement and timely intervention. | Milestone progress data will be collected through a combination of instructional and operational evidence reviewed during Campus Tactical Meetings. This includes observation and feedback trackers, coaching logs, PLC documentation, interim assessment data, attendance and culture reports, and MTSS intervention progress. APIs and the APO bring updated metrics and implementation artifacts to each tactical, ensuring that discussions are grounded in current performance data rather than anecdotal input. Data dashboards that capture real-time progress toward goals are also referenced to validate milestone status. This structured evidence collection process allows campus leadership to make informed decisions, monitor the impact of strategies, and identify areas requiring additional support or adjustment. | Milestone progress data will be shared with district leadership and relevant stakeholders through the documentation and follow-up of Campus Tactical Meetings. Key action items, progress updates, and emerging barriers discussed during tacticals are recorded in shared leadership trackers and escalated to regional leadership through principal check-ins and Portfolio Tactical meetings. Internally, the principal communicates updates to teacher teams during PLCs and staff huddles to ensure alignment between leadership decisions and classroom execution. When appropriate, high-level progress and adjustments are also communicated during family engagement events and data conferences to maintain transparency around academic and cultural goals. This layered communication structure ensures that milestone monitoring at the campus level is consistently connected to district oversight and stakeholder awareness.
|  | The successful implementation of this plan will be monitored through weekly leadership check-ins between the Executive Director and the Vice President of Schools, as well as with the Vice President of School Improvement when turnaround needs require intensified oversight. These check-ins are intentionally scheduled to review progress toward milestones, address challenges impacting instructional and cultural initiatives, and ensure leadership actions remain aligned to the turnaround priorities. Prior to each check-in, the VP prepares updates using a structured leadership template that includes current outcomes, barriers, and proposed solutions. During the meeting, the Executive Director provides coaching, strategic direction, and clarification of expectations to ensure that corrective actions are taken when progress is off track. This leadership monitoring structure creates a continuous accountability loop, ensuring that milestone implementation is actively managed at the executive level and immediately supported when intervention or escalation is needed. | Progress toward milestones will be reviewed by the Executive Director, who serves as the direct supervisor of the Vice President of Schools and collaborates closely with the Vice President of School Improvement. During weekly check-ins, the Vice President of Schools provides updates on campus execution, instructional leadership, and progress toward turnaround milestones, while the Vice President of School Improvement offers insight on the implementation of school improvement strategies and supports. The Executive Director evaluates this information, identifies areas requiring intervention or resource allocation, and ensures alignment between regional leadership actions and the expectations of the turnaround plan. This joint leadership review process ensures that milestone accountability is anchored at the executive level, with direct supervision and support tied to campus performance outcomes. | Progress toward milestones will be reviewed weekly through scheduled check-ins between the Executive Director and the Vice President of Schools, with the Vice President of School Improvement joining as needed to address turnaround-specific priorities. These weekly sessions ensure that progress is not monitored only at formal checkpoints, but consistently assessed in real time. When emerging challenges are identified, the Executive Director may increase the frequency of check-ins to provide intensified oversight or targeted support. This regular cadence allows leadership to make timely adjustments, deploy interventions, and ensure continuous forward momentum toward campus improvement goals. | Milestone progress data will be collected through leadership documentation and evidence reviewed during weekly check-ins between the Executive Director and the Vice President of Schools, with input from the Vice President of School Improvement when turnaround priorities are discussed. Prior to each check-in, campus and regional data are consolidated into leadership templates, which include outcome trends, implementation updates, root cause reflections, and proposed next steps. These updates draw from observation and feedback trackers, assessment data, instructional coaching logs, and campus milestone dashboards. By requiring leaders to prepare data-informed summaries in advance, the Executive Director ensures that milestone progress is evaluated using verified evidence rather than anecdotal reporting, allowing decisions to be based on current performance and fidelity of implementation. | Milestone progress data discussed during Executive Director check-ins will be shared with district leadership and key stakeholders through established leadership communication and escalation protocols. Following each check-in, key findings, risks, and next steps are documented in leadership trackers and communicated to regional teams through tactical meetings, and, when necessary, elevated to senior district leadership for resource allocation or strategic intervention. The Vice President of Schools communicates aligned expectations to principals, while the Vice President of School Improvement coordinates additional support or coaching for campuses requiring targeted assistance. This top-down and bottom-up communication structure ensures that progress toward milestones is transparent at all levels, executive, regional, and campus, allowing stakeholders to remain informed, aligned, and accountable to the successful implementation of the turnaround plan.
|  | The successful implementation of this plan will be monitored through weekly leadership check-ins between the Regional Superintendent and either the Executive Director or the Vice President of School Improvement. These check-ins are embedded in the regional core calendar and serve as a dedicated space to review progress toward milestones, assess the effectiveness of current strategies, and problem-solve any barriers hindering implementation. Prior to the meeting, the Executive Director or VPSI prepares updates using the check-in document, including current outcomes, identified gaps, and proposed solutions. During the conversation, the Regional Superintendent provides coaching, analyzes milestone alignment, and ensures that action steps remain focused on achieving turnaround goals. This consistent one-on-one accountability structure enables real-time adjustments, timely allocation of support, and continuous oversight of the plan’s execution at the leadership level. | Progress toward milestones will be reviewed by the Area Superintendent in collaboration with the Executive Director or Vice President of School Improvement during regularly scheduled weekly check-ins. As the supervisor, the Regional Superintendent is responsible for holding the Executive Director or VPSI accountable for implementation progress across campuses, including adherence to milestone timelines and intervention strategies. During these sessions, the Executive Director or VPSI presents milestone status, implementation challenges, and leadership actions taken at the campus level. The Regional Superintendent provides guidance, determines whether progress is on or off track, and initiates additional support or escalation when necessary. This shared responsibility ensures that milestone monitoring is led by regional leadership with direct authority to adjust strategy, deploy resources, and reinforce accountability. | Progress toward milestones will be reviewed weekly through structured check-ins between the Area Superintendent and the Executive Director or Vice President of School Improvement. Because these check-ins are built into the leadership core calendar, they provide a consistent cadence for monitoring implementation progress, assessing the impact of current strategies, and identifying emerging barriers. The weekly frequency ensures that milestone progress is not left to quarterly review, but instead monitored continuously, allowing swift intervention, adjustment of action steps, and timely deployment of support when progress is not on track. | Milestone progress data will be collected through leadership evidence reviewed during weekly check-ins between the Area Superintendent and the Executive Director or Vice President of School Improvement. Prior to each check-in, the Executive Director or VPSI completes a structured check-in document that includes updated outcome data, progress toward specific milestones, and an analysis of root causes for any implementation gaps. This information is supported by observation and feedback trackers, coaching logs, PLC artifacts, and interim assessment data gathered from campuses. During the check-in, milestone progress is discussed using a results-based framework, ensuring that both outcome data and implementation evidence are reviewed. This systematic collection process ensures that progress monitoring is grounded in verified data rather than anecdotal reporting. | Milestone progress data gathered during weekly check-ins will be shared with district leadership and relevant stakeholders through established reporting and communication structures. Following each check-in, key updates, identified risks, and agreed-upon next steps are documented in shared leadership trackers and communicated during regional tactical meetings and executive leadership huddles. When additional resources or intervention are required, the Regional Superintendent escalates needs to senior district leadership or national support teams. Information is also cascaded to campus principals and leadership teams through coaching sessions and follow-up directives, ensuring clear alignment between regional decision-making and on-campus execution. This communication loop ensures transparency, reinforces accountability, and supports timely action toward achieving turnaround milestones.
|  | The successful implementation of this plan will be monitored through weekly manager–direct report check-ins, which are built into the core calendar between the Deputy Superintendent and the Regional Superintendent. These check-ins provide a structured space to review progress toward goals, discuss barriers, and align on next steps. Prior to each meeting, the Regional Superintendent prepares outcome updates and root cause reflections using the check-in document. During the conversation, both leaders engage in two-way feedback, analyze current implementation status, and problem-solve around any obstacles impacting milestone attainment. Because these check-ins are recurring and intentionally focused on results, they ensure continuous oversight, timely adjustment of strategies, and accountable follow-through on the commitments outlined in the turnaround plan. | Progress toward milestones will be reviewed jointly by the Deputy Superintendent and the Regional Superintendent during their scheduled weekly check-ins. As the direct manager, the Deputy Superintendent is responsible for ensuring that the Regional Superintendent maintains clear progress toward the goals and actions outlined in the turnaround plan. During these sessions, the Regional Superintendent presents current milestone status, implementation evidence, and any emerging challenges from the campuses. The Deputy Superintendent provides coaching, guidance, and escalation support when additional regional or district resources are required. This shared accountability ensures that milestone monitoring remains anchored in leadership oversight and directly tied to decision-making and support at the executive level. | Progress toward milestones will be reviewed weekly through scheduled manager–direct report check-ins between the Deputy Superintendent and the Regional Superintendent. These recurring sessions, embedded into the core calendar, ensure that leadership maintains continuous visibility into implementation status, allowing for real-time adjustments rather than delayed, end-of-quarter interventions. The weekly cadence creates a consistent accountability loop, ensuring that progress toward milestones is actively monitored, corrective action is taken promptly, and support is deployed when needed to keep turnaround efforts on track. | Milestone progress data will be collected through the structured check-in process using pre-meeting submission and review of leadership artifacts. Prior to each check-in, the Regional Superintendent completes a check-in document that includes current outcomes, identified root causes for any gaps, and proposed solutions. This data is supported by campus-level evidence such as observation and feedback trackers, PLC documentation, interim assessment results, and MTSS intervention reports. During the check-in, the Deputy Superintendent reviews this data alongside the Regional Superintendent, using the Outcomes–Causes–Solutions (OCS) framework to ensure accuracy and clarity. This systematic documentation process ensures that milestone monitoring is grounded in real-time implementation evidence rather than anecdotal reporting. | Milestone progress data reviewed during weekly check-ins will be shared with district leadership and relevant stakeholders through established communication and accountability mechanisms. Following each check-in, key updates, identified challenges, and next steps are documented in leadership trackers and cascaded into regional tactical meetings and principal supervision forums. When additional resources or interventions are required, the Deputy Superintendent escalates needs to executive leadership or national support teams. This transparent flow of information ensures that milestone progress is not only monitored at the executive level, but also translated into actionable support for campus leaders, reinforcing alignment across all tiers of the organization.
|  | District and campus leaders will monitor the successful implementation of this plan through bi-weekly Portfolio Tacticals, facilitated by the Regional Superintendent. These meetings bring together the Vice President of School Improvement, Regional Executive Director, Vice President of Schools, and the assigned National Content Specialist to review the campus’s instructional status, milestone progress, and implementation of key strategies. During each Tactical, the Vice President of Schools (principal supervisor) and Regional Executive Director assess whether the campus is on track, identify barriers, and request any necessary instructional supports or resources. This continuous monitoring structure ensures that district leaders remain actively engaged in progress oversight and are positioned to make timely adjustments to sustain campus improvement efforts. | Progress toward milestones will be reviewed through the bi-weekly Portfolio Tacticals, led by the Regional Superintendent and attended by the Vice President of School Improvement, Regional Executive Director, Vice President of Schools, and the assigned National Content Specialist. This bi-weekly mechanism is specifically leveraged to monitor the milestones identified in the turnaround plan, requiring active input from each of these district leaders. During these sessions, the Vice President of Schools reports on campus implementation, while the Executive Director provides leadership oversight. Based on the level of progress and implementation observed, district resources are deployed as needed, ranging from instructional materials and strategic support to direct human capital through national coaching or specialized intervention teams. This ensures that progress monitoring is immediately connected to action and accountability. | Progress toward milestones will be reviewed on a bi-weekly basis through Portfolio Tactical meetings. This consistent cadence ensures that district and campus leaders are able to frequently assess implementation progress, identify emerging barriers, and make timely adjustments to strategies. By reviewing milestones every two weeks, leadership maintains a proactive stance, allowing for rapid deployment of additional support, resources, or coaching when progress toward key outcomes is at risk. | Milestone progress data will be collected through multiple evidence streams reviewed during Portfolio Tactical meetings. Data sources will include principal reports, observation and feedback trackers, coaching logs, PLC documentation, interim assessment results, and MTSS intervention progress reports. Each of these tracking methods is supported by a real-time data dashboard, ensuring continuous visibility into implementation and student outcomes. National, regional, and campus leaders all have access to these dashboards and reports, allowing for transparent monitoring and collaborative problem-solving. In addition, Quick Check results will be used to verify the fidelity of leadership and instructional execution, further strengthening the accuracy of milestone monitoring. | Milestone progress data will be shared through collaborative discussion and documentation during Portfolio Tacticals. Insights, progress updates, and required interventions are recorded in shared tactical trackers and communicated back to campus leadership during follow-up check-ins and coaching sessions. When regional or national support is required, requests and action steps are formally escalated during these meetings. This layered communication structure ensures that milestone progress is transparent, action-oriented, and aligned across all leadership levels.
|  | The successful implementation of this plan will be monitored through weekly supervisor–direct report check-ins between the Deputy Superintendent and the Chief of Staff. These sessions are built into the core leadership calendar and provide a structured space to review progress toward goals, examine barriers, and align on next steps. Prior to each meeting, the Chief of Staff prepares outcome updates and root cause reflections using the check-in document. During the conversation, both leaders engage in two-way feedback, analyze current implementation status, and problem-solve around any challenges impacting milestone attainment. Because these check-ins are recurring and results-focused, they ensure continuous oversight, timely strategic adjustments, and accountable follow-through on turnaround commitments. | Progress toward milestones will be reviewed jointly by the Deputy Superintendent and the Chief of Staff during their scheduled weekly check-ins. As the direct supervisor, the Deputy Superintendent is responsible for ensuring that the Chief of Staff, as a direct support to the Vice President of School Improvement, maintains clear progress toward the goals and actions outlined in the turnaround plan. During these sessions, the Chief of Staff presents current milestone status, implementation evidence, and any emerging challenges from across departments. The Deputy Superintendent provides coaching, guidance, and escalation support when additional regional or district resources are required. This shared accountability ensures that milestone monitoring remains anchored in executive leadership oversight and directly tied to decision-making at the highest level. | Progress toward milestones will be reviewed weekly through scheduled supervisor–direct report check-ins between the Deputy Superintendent and the Chief of Staff. These recurring sessions, embedded within the core calendar, ensure sustained visibility into implementation status and allow for real-time adjustments rather than delayed, end-of-cycle interventions. The weekly cadence creates a consistent accountability loop, ensuring that progress is actively monitored, corrective action is taken promptly, and targeted support is deployed to keep turnaround efforts on track. | Milestone progress data will be collected through the structured check-in process using pre-meeting submission and review of leadership artifacts. Prior to each session, the Chief of Staff completes a check-in document that includes current outcomes, identified root causes for gaps, and proposed solutions. This data is supported by organization-wide evidence such as observation and feedback trackers, PLC documentation, interim assessment results, and MTSS intervention reports. During the check-in, the Deputy Superintendent reviews this data alongside the Chief of Staff using the Outcomes–Causes–Solutions (OCS) framework to ensure accuracy and clarity. This systematic documentation process ensures that milestone monitoring is grounded in real-time implementation evidence rather than anecdotal reporting. | Milestone progress data reviewed during weekly check-ins will be shared with district leadership and relevant stakeholders through established communication and accountability mechanisms. Following each check-in, key updates, identified challenges, and next steps are documented in leadership trackers and cascaded into tactical meetings and principal supervision forums. When additional resources or interventions are needed, the Deputy Superintendent escalates requests to executive leadership or national support teams. This transparent flow of information ensures that milestone progress is not only monitored at the executive level, but also translated into actionable support for campus and departmental leaders—reinforcing alignment across all tiers of the organization.
|  | The successful implementation of this plan will be monitored through bi-weekly supervisor–direct report check-ins between the Superintendent and the Deputy Superintendent. These sessions, embedded in the core executive calendar, provide a structured forum to review progress toward goals, examine barriers, and align on next steps. Prior to each meeting, the Deputy Superintendent prepares outcome updates and root cause reflections using the designated check-in document. During the conversation, both leaders engage in two-way feedback, analyze current implementation status, and address challenges affecting milestone attainment. Because these check-ins are recurring and results-focused, they ensure continuous oversight, timely strategic adjustments, and accountable follow-through on turnaround commitments. | Progress toward milestones will be reviewed jointly by the Superintendent and the Deputy Superintendent during their bi-weekly check-ins. As the direct supervisor, the Superintendent is responsible for ensuring that the Deputy Superintendent maintains clear progress toward the goals and actions outlined in the turnaround plan. During these sessions, the Deputy Superintendent presents current milestone status, implementation evidence, and any emerging challenges from across regions or departments. The Superintendent provides coaching, guidance, and escalation support when additional district or national resources are required. This shared accountability ensures that milestone monitoring remains anchored in executive oversight and directly tied to leadership-level decision-making. | Progress toward milestones will be reviewed bi-weekly through scheduled supervisor–direct report check-ins between the Superintendent and the Deputy Superintendent. These sessions ensure sustained visibility into implementation status and enable real-time adjustments rather than delayed, end-of-cycle interventions. The bi-weekly cadence creates a consistent accountability loop, ensuring that progress is actively monitored, corrective action is taken promptly, and targeted support is deployed to keep turnaround efforts aligned and on track. | Milestone progress data will be collected through the structured bi-weekly check-in process using pre-meeting submission and review of leadership artifacts. Prior to each session, the Deputy Superintendent completes a check-in document outlining current outcomes, identified root causes for gaps, and proposed solutions. This data is supported by organizational evidence such as observation and feedback trackers, PLC documentation, interim assessment results, and MTSS intervention reports. During the check-in, the Superintendent reviews this data with the Deputy Superintendent using the Outcomes–Causes–Solutions (OCS) framework to ensure accuracy and clarity. This systematic documentation process ensures milestone monitoring is anchored in real-time implementation evidence rather than anecdotal reporting. | Milestone progress data reviewed during bi-weekly check-ins will be shared with district leadership and, as appropriate, communicated to the School Board to ensure transparency and alignment at the governance level. When additional actions are required at the regional or campus level, the Deputy Superintendent will provide targeted next steps and strategic feedback to the Regional Superintendent. The Regional Superintendent is then responsible for disseminating this guidance across the region to support campus turnaround efforts and ensure consistent execution of the improvement plan. This structured communication flow ensures that progress monitoring at the executive level is directly translated into actionable leadership support, reinforcing coherence and urgency across all tiers of the organization.
|  | Implementation of the school improvement plan will be monitored through quarterly maintenance audits — executive site visits conducted by the Superintendent, Deputy Superintendent, Chief of Staff, and Curriculum Officers. These progress audits allow senior leadership to directly assess the fidelity of implementation and confirm that strategies are producing measurable impact. During each visit, leaders gather both quantitative data and qualitative evidence through classroom observations, leadership team discussions, and review of instructional and intervention artifacts. These executive audits function as a high-level accountability measure to ensure alignment with district turnaround expectations. | The Superintendent, in collaboration with the Deputy Superintendent, will lead the review of milestone progress during quarterly progress audits. The Superintendent’s participation ensures governance-level oversight, while the Deputy Superintendent, Chief of Staff, and Curriculum Officers provide executive analysis of implementation status. Following the visit, strategic feedback is communicated to the Regional Superintendent, Vice President of Schools, Vice President of School Improvement, and Executive Director to direct necessary action at the regional and campus levels. | Progress toward milestones will be reviewed quarterly through formal maintenance or progress audits conducted on-site. These visits serve as scheduled executive checkpoints designed to evaluate sustained execution of turnaround strategies and recalibrate support where progress is stalled or inconsistent. The quarterly cadence ensures districts receive a comprehensive and objective assessment every nine weeks. | Progress data will be collected during quarterly audits through structured evidence protocols, including classroom walkthroughs, PLC reviews, interim assessment analysis, MTSS documentation, and leadership artifact review. Executive leadership applies an Outcomes–Causes–Solutions (OCS) framework to organize findings, ensuring that root causes are identified and tied to specific corrective actions. Data collected is objective, implementation-based, and validated through direct observation rather than self-reporting. | Following each quarterly audit, a comprehensive executive summary will be developed outlining strengths, gaps, and required next steps. Audit outcomes will be shared with district leadership, and when appropriate, reported to the School Board to ensure transparency at the governance level. The Deputy Superintendent will provide regional feedback and follow-up actions to the Regional Superintendent for dissemination to school leaders, ensuring that insights from executive audits are operationalized to drive continuous improvement across campuses.

## Resources
Criteria for Success
Has the district identified all resources needed to implement the SI strategy? -The description lists all additional costs associated with implementing the school improvement strategy (e.g., stipends, instructional materials, training/professional development costs, costs for additional staff positions created to implement the strategy, etc.) -Each cost described includes the source of funds.
Question | List or copy and paste all SI - identified campuses below | Please share the required costs to implement plan and source of funds | If the strategy is contingent on a grant funding source, what is your alternative funding or implementation plan if you do not receive the grant? How would your district still support and execute this strategy?
Additional Instructions | List all SI campuses in the district
Answer(s) | IDEA Achieve Academy | All-In-learning - $13,750 | All-in-learning supports school wide data practices that will allow for strategic campus data monitoring including targeting students to ensure campus is able to monitor and meet accountability goals and is added AI support to SCR and ECR components
| IDEA La Joya Academy | "Strategy / Resource/Amount: - After School Turorials/Saturday School - 45,000 Focus: HB 1416 accelerated instruction and priority MTSS students. Also, bubble meets students. - Flex Teachers (4) to cover FMLA and provide additional support - 100,000 Focus: To continue instruction for 1st, 2nd 4th and 5th grades to cover upcoming FMLAs. - Read 180 - additional licenses/materials - 4,465 Focus: 2nd grade students identified as being 2 or more years behind in reading. -Countdown to STAAR - RLA, Math and Writing (Booklets and Online) - 8,000 Focus: 3rd - 5th STAAR aligned practice. - IXL Learing - 10,000 Focus: 2nd - 5th for all students. -Teach Big - Writing Training - 5,000 Focus: 2nd - 5th STAAR based, STAAR ready Reading/Writing Inservices " | To implement the school improvement plan, District allocated School Improvement Funds have been strategically aligned to support targeted interventions, staffing, instructional capacity, and student engagement. These investments are aligned to the Effective Schools Framework (ESF), specifically: Lever 1 – Effective Leadership and Planning Lever 2 – Strategic Staffing Lever 3 – Positive School Culture Lever 5 – Effective Instruction
| IDEA Eastside College Prep | "Strategy / Resource/Amount: - After School Turorials/Saturday School Focus: HB 1416 accelerated instruction and priority MTSS students. -RBIS Training for Campus Leadership and Regional Support -$3,500" - Regional Support - 2 Regional PIRs and 3 Regional APIs - $174, 200 & $261,3000
| IDEA Najim Academy | "Strategy / Resource/Amount: - After School Turorials/Saturday School Focus: HB 1416 accelerated instruction and priority MTSS students. Also, bubble meets students. $50,000 - Flex Teachers to cover vacancies and utilized for trainings or provide additional support - $100,000 - Read 180 - additional licenses/materials - $5,000 -RBIS Training for Campus Leadership and Regional Support -$3,500"
| IDEA Spears Academy | "To implement the school improvement plan, District allocated School Improvement Funds have been strategically aligned to support targeted interventions, staffing, instructional capacity, and student engagement. These investments are aligned to the Effective Schools Framework (ESF), specifically: Lever 1 – Effective Leadership and Planning Lever 2 – Strategic Staffing Lever 3 – Positive School Culture Lever 5 – Effective Instruction Strategy / Resource/Amount - Additional 5th Grade Math Academy Teacher (strategic staffing to reduce class size and increase intervention capacity) o $75,000 - Math Flex Teacher – Small group intervention for 3rd–5th Math (strategic staffing for intervention blocks) o $75,000 - Sylvan Tutoring (3rd–5th ELA & Math) – 3 tutors, serving 75+ scholars, Monday–Friday, 4:1 ratio, 40 sessions o $100,000 - Region ESC Support – Special Education (IEPs, Services, Accountability), Content Training & Research-Based Professional Development for Teachers and Leaders o $3,000 - General Instructional Supplies – 3rd–5th Math, Science, and ELA (foldables, study guides, binders with visuals, manipulatives) o $2,000 - Kagan Academic Engagement Strategies – Professional Development (K–5) o $2,000 Justification: These investments strengthen leadership planning, ensure strategic staffing, enhance instructional quality, and support a positive school culture and the key conditions necessary to meet the campus' growth and achievement goals under Domain III." | To implement the School Improvement Plan with fidelity at IDEA Spears Academy and IDEA Spears College Preparatory, School Improvement Funds have been strategically allocated to strengthen three core SI strategies: Intensive Instruction, High-Quality Observation and Feedback, and Effective PLCs/Lesson Internalization. Investments in Sylvan tutoring at both campuses provide high-dosage, small-group ELA and Math intervention with a 4:1 teacher-student ratio, directly supporting growth goals and ensuring scholars receive targeted instruction aligned to gaps identified during PLCs. The additional 7th Grade ELA Flex Teacher at Spears CP increases instructional capacity, reduces class size, and creates more opportunities for leaders to observe, coach, and support high-quality instructional execution. ESC professional development builds teacher and leader capacity in SPED services, research-based instructional practices, and content-specific strategies, ensuring alignment between coaching expectations, classroom practices, and student needs. Kagan Academic Engagement Strategies training equips teachers with high-engagement structures that leaders can reinforce through observation and feedback cycles while also supporting PLCs as teachers plan for rigorous, student-centered instructional delivery. General instructional supplies—including manipulatives, foldables, guided binders, and visual supports—ensure that teachers can internalize lessons with the necessary content tools and support differentiated instruction, especially for scholars in Special Education. These funds do not operate in isolation. Instead, they create a tightly aligned system where adult learning, instructional execution, and student intervention reinforce one another—accelerating both proficiency and growth outcomes across both Spears campuses. Funding Source Note: The district is not relying on grant funds to support this plan but is instead utilizing local, federal, and other funding sources to sustain implementation and build long-term capacity.
| IDEA Spears College Prep | "To implement the school improvement plan, District allocated School Improvement Funds have been strategically aligned to support targeted interventions, staffing, instructional capacity, and student engagement. These investments are aligned to the Effective Schools Framework (ESF), specifically: Lever 1 – Effective Leadership and Planning Lever 2 – Strategic Staffing Lever 3 – Positive School Culture Lever 5 – Effective Instruction Strategy / Resource/Amount - Additional 5th Grade Math Academy Teacher (strategic staffing to reduce class size and increase intervention capacity) o $75,000 - Math Flex Teacher – Small group intervention for 3rd–5th Math (strategic staffing for intervention blocks) o $75,000 - Sylvan Tutoring (3rd–5th ELA & Math) – 3 tutors, serving 75+ scholars, Monday–Friday, 4:1 ratio, 40 sessions o $100,000 - Region ESC Support – Special Education (IEPs, Services, Accountability), Content Training & Research-Based Professional Development for Teachers and Leaders o $3,000 - General Instructional Supplies – 3rd–5th Math, Science, and ELA (foldables, study guides, binders with visuals, manipulatives) o $2,000 - Kagan Academic Engagement Strategies – Professional Development (K–5) o $2,000 Justification: These investments strengthen leadership planning, ensure strategic staffing, enhance instructional quality, and support a positive school culture and the key conditions necessary to meet the campus' growth and achievement goals under Domain III." | To implement the School Improvement Plan with fidelity at IDEA Spears Academy and IDEA Spears College Preparatory, School Improvement Funds have been strategically allocated to strengthen three core SI strategies: Intensive Instruction, High-Quality Observation and Feedback, and Effective PLCs/Lesson Internalization. Investments in Sylvan tutoring at both campuses provide high-dosage, small-group ELA and Math intervention with a 4:1 teacher-student ratio, directly supporting growth goals and ensuring scholars receive targeted instruction aligned to gaps identified during PLCs. The additional 7th Grade ELA Flex Teacher at Spears CP increases instructional capacity, reduces class size, and creates more opportunities for leaders to observe, coach, and support high-quality instructional execution. ESC professional development builds teacher and leader capacity in SPED services, research-based instructional practices, and content-specific strategies, ensuring alignment between coaching expectations, classroom practices, and student needs. Kagan Academic Engagement Strategies training equips teachers with high-engagement structures that leaders can reinforce through observation and feedback cycles while also supporting PLCs as teachers plan for rigorous, student-centered instructional delivery. General instructional supplies—including manipulatives, foldables, guided binders, and visual supports—ensure that teachers can internalize lessons with the necessary content tools and support differentiated instruction, especially for scholars in Special Education. These funds do not operate in isolation. Instead, they create a tightly aligned system where adult learning, instructional execution, and student intervention reinforce one another—accelerating both proficiency and growth outcomes across both Spears campuses. Funding Source Note: The district is not relying on grant funds to support this plan but is instead utilizing local, federal, and other funding sources to sustain implementation and build long-term capacity.

## Additional Info
Question | List or copy and paste all SI - identified campuses below | (Optional) Please share any additional information about your strategy that was not included in the prior sections. You may also upload documents.
Additional Instructions | List all SI campuses in the district
Answer(s)