## Direction
Things to Consider Prior to Starting Workbook
This workbook is meant to support both TIP and TAP development. Differences between the two will be notated within each sheet/tab. The workbook serves as planning tool to assist you when filling out the survey link for the TAP/TIP turn in. Modify the cells as needed - the workbook attempts to follow the survey logic as closely as possible. When filling out this workbook, having an idea of what you will do similar across certain campuses allows you to merge cells to apply one strategy, tactic, etc to a group of campuses. During the submision, you will complete one submission per strategy and have an option at the end to complete an additional submission for additional TIPs, TAPs, strategies, etc.
Directions
1. Fill out the workbook PRIOR to the official link (or choose your own draft tool).
2. If there is criteria for success, it will be posted at the top.
3. Note that not all tabs need to be filled out - this depends on the strategy selected.
4. Items highlighted yellow indicate they only apply to certain strategies so read carefully.
5. Read each tab/sheet carefully.

## Plan Type
Question/Prompt | Please select the type of plan you are submitting
Additional Instructions | Targeted Improvement Plan for one or more campuses; Turnaround Plan for one or more campuses
Answer | Targeted Improvement Plan - One Campus

## School System Information
Question/Prompt | School System Name | Name of the staff member employed by the school system completing this plan submission | Email | What role applies to the person completing this submission?
Additional Instructions |  |  |  | Please select/type one of the following: Superintendent, District Coordinator of School Improvement (DCSI), Other (if other, please specify)
Answer | IDEA Public Schools - Travis Academy | Alecia Bell | alecia.bell@ideapublicschools.org | District Coordinaotor of School Improvement (DCSI)

## NA and Stakeholder Engmt
Criteria for Success
Did the LEA meet statutory requirements for stakeholder engagement, and has the board approved the plan? -The district assures that the Campus Intervention Team (CIT) conducted a public meeting at each campus identified for school improvement with the campus principal, the members of the campus-level planning and decision-making committee, parents of students attending the campus, and community members residing in the school district to review the campus performance rating and solicit input for the development of the targeted improvement plan. -The district assures that written notice of all public meetings was provided to parents and students of each impacted campus, notice of the meeting was posted on each campus website, and this notice included the date, time, and place of the meeting. -The board conducted a hearing regarding the plans for each campus identified for school improvement. -The board posted the plan on the district website prior to the hearing. -The plan is approved by the board. -Written comments from stakeholders, if any, are attached.
ASSURANCES ARE THE SAME FOR BOTH TIP/TAP
Question | List or copy and paste all SI - identified campuses below | Please indicate the type of needs assessment conducted for each SI-identified campus in the school system following the release of 2025 preliminary state and federal ratings. | I assure that all locally conducted needs assessments met the requirements in Section 39A.053 of the Texas Education Code, and the results of the local needs assessment are available upon request. | I assure that the Campus Intervention Team (CIT) conducted a public meeting at each campus required to submit a Targeted Improvement Plan with the campus principal, the members of the campus-level planning and decision-making committee, parents of students attending the campus, and community members residing in the school district to review the campus performance rating and solicit input for the development of the plan. | I assure that written notice of all public meetings was provided to parents and students of each impacted campus, notice of the meeting was posted on each campus website, and this notice included the date, time, and place of the meeting. | I assure that the board conducted a hearing regarding the plans for each campus identified for school improvement to notify the public of the insufficient performance of the campus, the improvements in performance expected by the agency, and the intervention measures or sanctions that may be imposed if the performance does not improve within a designated period, the board solicited public comment on each targeted improvement plan, and the board posted the plan(s) on the district website prior to the hearing. | Board approval date
Additional Instructions | List all SI campuses in the district | Choose one of the following: ESF Diagnostic and Local Classroom Review, Locally Conducted Needs Assessment, Texas Strategic Leadership Landscape Analysis | Yes | Yes (11/4/25) | Yes | Yes | 2025-11-18
| IDEA Travis Academy (PK-5th) | On September 30, 2025, IDEA Travis Academy participated in an IDEA School Review (Locally Conducted Needs Assessment) that met the requirements of TEC 39A.053 for a comprehensive school diagnostic. The review identified three guiding priorities essential to strengthening instructional and cultural systems: (1) Systems for culture and instructional practices, including safety procedures, academic block structures, and the frequency and quality of lesson rehearsals with clear “what/how” expectations; (2) Consistent classroom observations with Real Time Coaching (RTC) using the See It, Name It, Do It model for all instructional staff; and (3) Intentional planning for student thinking, academic discourse, and productive struggle within lessons. The review was conducted by regional and district-level executive leaders and aligned to the Effective Schools Framework (ESF), specifically Lever 1 – Effective Leadership and Planning, Lever 3 – Positive School Culture, and Lever 5 – Effective Instruction. Evidence was gathered through examination of lesson internalization practices and feedback, instructional delivery, culture systems, Leadership Core Calendars used to schedule key practices such as lesson rehearsals and classroom observations, leadership development protocols, and classroom walk-through observations. School Review Findings: The Travis School Review revealed that while teachers are teaching from submitted lesson plans and campus culture remains positive and ready for learning, misalignment between lesson internalization ratings and observed practice indicates a need for stronger curricular fidelity and instructional feedback. Math and Science teams submitted plans consistently but lacked daily annotations and rigor-aligned objectives, with limited opportunities for student release during instruction. Leadership protocols for feedback exist but require greater consistency, depth, and connection to classroom outcomes. To address these findings, the campus will prioritize (1) Realignment to Lesson Internalization and Curricular Alignment by resetting and clarifying instructional expectations, modeling weekly internalization meetings and rehearsal protocols, conducting weekly walkthroughs focused on rigor and alignment, providing feedback within 24 hours, and calibrating feedback with campus leaders. Additionally, (2) Fidelity and Consistency of Instructional Coaching will be strengthened through reset coaching cadences with weekly 1:1s and real-time feedback, implementation of structured coaching cycles aligned to GET and deliberate practice, shadowing of leader coaching conversations for fidelity, and monthly calibration sessions to ensure consistency of coaching practices and improved instructional delivery.
| IDEA Travis Academy (6th-11th) | On October 1, 2025, IDEA Travis Academy participated in an IDEA School Review (Locally Conducted Needs Assessment) that met the requirements of TEC 39A.053 for a comprehensive school diagnostic. The review identified three guiding priorities essential to strengthening instructional and cultural systems: (1) Systems for culture and instructional practices, including safety procedures, academic block structures, and the frequency and quality of lesson rehearsals with clear “what/how” expectations; (2) Consistent classroom observations with Real Time Coaching (RTC) using the See It, Name It, Do It model for all instructional staff; and (3) Intentional planning for student thinking, academic discourse, and productive struggle within lessons. The review was conducted by regional and district-level executive leaders and aligned to the Effective Schools Framework (ESF), specifically Lever 1 – Effective Leadership and Planning, Lever 3 – Positive School Culture, and Lever 5 – Effective Instruction. Evidence was gathered through examination of lesson internalization practices and feedback, instructional delivery, culture systems, Leadership Core Calendars used to schedule key practices such as lesson rehearsals and classroom observations, leadership development protocols, and classroom walk-through observations. School Review Findings: The Travis College Prep School Review surfaced strong instructional foundations, including teacher alignment to the scope and sequence in ELA/SS, high levels of student engagement in Math, consistent use of academic vocabulary supports, and smooth campus-wide transitions supported by proactive leadership. Teachers demonstrated proficiency in key GET indicators, and leaders effectively identified the Most Important Action (MPP) and coached teachers toward manageable next steps. However, key gaps exist that drive the campus priorities. In ELA/SS, teachers were not consistently using the provided curriculum nor internalizing the lessons they submitted. In Math, teachers missed opportunities to reteach low-mastery concepts, and internalization processes and materials were inconsistent across classrooms. Additionally, PBIS systems were not evident during observations and Culture of Joy practices—such as positive narration, shoutouts, and celebrations—were inconsistently applied. Therefore, campus priorities will focus on: (1) Strengthening alignment to lesson internalization expectations and ensuring full fidelity to the adopted curriculum; (2) Deepening instructional leadership coaching through deliberate planning, side-by-side coaching, and stronger use of GET-aligned feedback cycles; and (3) Implementing a robust PBIS system that uses positive behavior supports and incentives to reinforce a joyful, predictable, and safe school culture.

## School Improvement Strategy
Criteria for Success
Is the proposed strategy likely to move the campus to a C or better OR CSI exit in two years or less? -The school improvement strategy selected would reasonably improve student outcomes quickly enough that the campus would not be escalated to a sanction under Texas Education Code (TEC), Section 39A.111. -There is appropriate support dedicated to strategy implementation and capacity building: +There is a team/organization with a track record of success in systems building and rapidly improving student outcomes dedicated to supporting the campus in strategy implementation (an ESC, SAPL vendor, program-vetted vendor, etc.); OR +If district or campus staff members are named as the capacity builder, there is evidence that these staff members: -Have a track record of success in school turnaround -At least 50% of their role is dedicated to the implementation of the strategy on the campus (cannot be current principal or AP, unless role was added specifically to support SI)
Question | To which campus or campuses does this strategy apply? | Please select the strategy or strategies you will implement for this campus/these campuses | Which, if any, grants has your school system been awarded to support this strategy? | Which, if any, grants has your school system applied for (or intends to apply for) to support this strategy? | Please name any organizations you are currently working with to build capacity and support strategy implementation. | How many district staff members will you be reporting capacity building information for? | What are the names and roles of district and campus staff members responsible for capacity building, and what percent of their role is dedicated to supporting implementation of the school improvement strategy? | 5.5 Please describe the organization's or staff member's experience and track record in school turnaround (moving a campus from failing to meet standards to meeting and/or exceeding standards).
Additional Instructions | List all SI campuses in the district | Please write one of the following: Accelerating Campus Excellence (ACE) Model Closure/reassign Improve Graduation Rate Intensive Curriculum & Instruction Improvements School Model Change (excluding ACE) Turnaround Partnership (SB 1882) | Strong Foundations Implementation, SFI PLC Support, Instructional Leadership Pathways, School Action Fund Planning (Restart),School Action Fund Implementation (Restart), School Action Fund Planning (Reassign), School Action Fund Implementation (Reassign), School Action Fund Planning (Redesign), School Action Fund Implementation (Redesign), School Action Fund Planning (Create New), School Action Fund Implementation (Create New), Effective Schools Framework Focused Support Grant 24-26, Our school system has not been awarded a grant to support this strategy, Other (must enter grant into text box) | LIFT, LIFT PLC Support, School Improvement Curriculum and Instruction Support Grant, School Action Fund Planning (Restart), School Action Fund Implementation (Restart), School Action Fund Planning (Reassign), School Action Fund Implementation (Reassign), School Action Fund Implementation (Redesign), School Action Fund Planning (Create New), School Action Fund Implementation (Create New), Effective Schools Framework Focused Support Grant 24-26, Our school system has not been awarded a grant to support this strategy, Other (must enter grant into text box) | SAPL list, ESCs, District Staff, Campus Staff, Other (must include name) | You can report up to 15 district staff members. | ONLY COMPLETE IF DISTRICT OR CAMPUS STAFF NAMED (column F on this page) | ONLY COMPLETE IF THE ORGANIZATION NAMED (column F on this page) IS NOT AN ESC OR ON THE STATE APPROVED PROVIDER LIST (SAPL).
Answer(s) | IDEA Travis Academy | Intensive Curriculum & Instruction Improvements and the SB 1882 Partnership: Each capacity-building activity outlined in the plan aligns with one or both of these strategic priorities. Activities related to Effective Observation, Feedback, and Coaching strengthen leader and teacher capacity through consistent observation cycles, targeted feedback, and real-time coaching support. Activities tied to Effective PLC and Lesson Internalization enhance instructional planning and teacher collaboration by deepening lesson understanding, ensuring alignment to standards, and promoting student-centered instructional practices. Together, these focus areas build the foundation for sustained instructional excellence and continuous improvement across the campus. | Our school system has not been awarded a grant to support this strategy | Our school system has not been awarded a grant to support this strategy | Alecia Bell, District Staff | 1 | In this role, approximately 80% of the Vice President of School Improvements responsibilities are devoted to executing the district’s school improvement strategy. Her work includes guiding campuses through the Effective Schools Framework (ESF), addressing identified needs within turnaround plans, and coordinating regional and national supports to ensure aligned execution. She provides direct coaching and training to campus and district leaders to strengthen leadership planning and build effective systems for instruction, data use, and operational excellence. Mrs. Bell offers ongoing feedback, collaborates closely with executive directors, regional superintendents, and Vice Presidents of Schools, and plays a critical role in ensuring continuous improvement across priority campuses. | The Vice President of School Improvement brings extensive, proven experience in leading and supporting school improvement across multiple leadership roles. As a principal, she successfully turned around two historically underserved and underperforming campuses in the Houston Independent School District, Hartsfield ES and Gregory-Lincoln K-8. In her work she moved both campuses from Improvement Required to Met Standard and earning distinctions. As a School Support Officer (principal supervisor) and Executive Director of Instruction, she supported 14 campuses over six years, guiding them out of school improvement status and ensuring they met all turnaround requirements, this portfolio also includes one alternative education campus who had not met standard in over 6 years moved from F to C (High School Ahead Academy). Additionally, she supported the work of moving Fleming MS from a rating of F to B. In her role as Executive Director of School Improvement, serving as the DCSI, Ms. Bell supported multiple campuses within a single district in achieving and sustaining their turnaround goals. She has deep expertise in implementing the Effective Schools Framework (ESF) across all roles and contexts, including direct support of campus leadership of Patrick Henry Middle School (located 1 block from Hardy Academy), a campus identified under SB 1365, successfully moving a campus from an F to a C and avoiding state sanctions. Turnaround Experience Overview : 5 Years – Teacher 5 Years – Assistant Principal 6 Years – Principal 7 Years – Principal Manager (School Support Officer / Executive Director) 2 Years – District School Improvement Leadership

## Student Outcome Goals
Question | List or copy and paste all SI - identified campuses below | Enter the campus-wide goal for the All Grades ELA/Reading Meets Grade Level or Above STAAR Performance rate for the 2025-2026 school year. | Enter the campus-wide goal for the All Grades Math Meets Grade Level or Above STAAR Performance rate for the 2025-2026 school year. | Enter the 2025-2026 Component Points campus goal for the Academic Achievement Component of Domain III. | Enter the 2025-2026 Component Points campus goal for the Growth Status Component of Domain III. | Enter the 2025-2026 Component Points campus goal for the ELP Status Component of Domain III. | Enter the 2025-2026 Component Points campus goal for the Student Success Status Component of Domain III.
Additional Instructions | List all SI campuses in the district
Answer(s) | IDEA Travis Academy (Pk-11) | By the end of the 2025–2026 school year, IDEA Travis Academy will achieve 50% Meets Grade Level or Above in All Grades ELA/Reading STAAR/EOC Performance. | By the end of the 2025–2026 school year, IDEA Travis Academy will achieve 50% Meets Grade Level or Above in All Grades Math STAAR/EOC Performance. | ELA/Reading: The campus will earn 75% (12/16) Component Points in Academic Achievement for Domain III in 2025–2026. Math: The campus will earn 63% (10/16) Component Points in Academic Achievement for Domain III in 2025–2026. | ELA/Reading: The campus will earn 50% (8/16) Component Points in Growth Status for Domain III in 2025–2026. Math: The campus will earn 69% (11/16) Component Points in Growth Status for Domain III in 2025–2026. | The campus will earn 100% (4/4) Component Points toward the ELP Status Component in Domain III for the 2025–2026 school year. | The campus will earn 50% (8/16) Component Points for the Student Success Status Component in Domain III during the 2025–2026 school year.

## Curriculum and Instruction
Criteria for Success
Does the plan increase the quality of instructional materials to be used at the campus and provide adequate time and support for teachers to internalize materials and reflect on student performance? -The campus will increase the quality of the instructional materials to be used at the campus (if not already implementing SBOE-approved HQIM or OER). -The district has allocated sufficient instructional time for delivery of HQIM and has a calendar with a minimum of 165 instructional days. -The campus will have weekly (at a minimum) high-quality PLCs to support instructional delivery and respond to student outcomes -The PLC protocol includes time for lesson internalization and student work analysis.
ONLY IF YOU SELECTED C&I, ACE, SCHOOL MODEL CHANGE, OR 1882 AS YOUR SCHOOL IMPROVEMENT STRATEGY
Question | List or copy and paste all SI - identified campuses below | Please select the adopted curriculum | Is this the curriculum that will be implemented for the duration of the plan? | What new curriculum will be adopted? | When will the district adopt the new curriculum? | How many instructional minutes per week are required/recommended for implementation of this curriculum? | How many instructional minutes per week are in master schedule for curriculum delivery, and does this amount of minutes meet the required/recommended number of minutes? | How many instructional days are included in the 2025-2026 calendar? | If there are fewer than 165 instructional days in the 2025-2026 calendar, what steps will the district take to ensure a 165-day calendar is adopted and implemented in 2026-2027? | Please describe the assessment plan for the impacted campus(es) | Will the campus(es) implement a PLC structure? | How will PLCs be organized (by grade level, content area, etc.)? | How frequently will PLCs occur? | Who will facilitate PLCs? | Who is requried to attend PLCs? | Please describe the PLC protocol to be used
Additional Instructions | List all SI campuses in the district excluding Texas Partnership schools |  | Yes or No Select yes, go to column G Select no, go to column E
Answer(s) | IDEA Travis Academy | The adopted math curriculum is Bluebonnet Math, and the adopted ELAR curriculum is Wit & Wisdom. | Yes, the math curriculum will continue to be implemented throughout the duration of the plan; however, research is underway to explore potential ELAR curriculum changes for the second year (2026–2027) of the school improvement strategy. | N/A | The HQIM was adopted during the Spring of 2025. | Math: The curriculum is recommended to be implemented with 350 instructional minutes per week. ELAR: The curriculum is recommended to be implemented with 450 instructional minutes per week. | Class periods are 75 minutes each day. This allows sufficient time to implement the curriculum. | The 2025–2026 calendar includes 174 instructional days. | N/A | Bluebonnet Math includes Mid-Module and End-of-Module assessments for each unit, with assessment windows varying by grade level according to module length. In addition, campuses will administer bi-weekly spiral assessments to monitor ongoing mastery. Standards in which students do not demonstrate proficiency will be identified, retaught through spiraled review, and reassessed to ensure growth and retention. Daily exit tickets will be completed at the end of each instructional block. Teachers will record student performance and participate in exit ticket huddles to develop targeted reteach plans. Furthermore, teachers will engage in student work analysis meetings to examine the quality of student responses and address misconceptions. To measure broader progress, campuses will also administer two Interim Assessments (IA) one fall for ELAR and one spring for mathematics, providing data to inform instructional adjustments and intervention planning. | Yes, the campus will implement a weekly PLC structure. | Yes, the campus will implement a structured PLC process. Teachers plan by grade level; therefore, each PLC consists of the grade-level content teacher, the campus instructional leader, the Regional content leader, and, when accessible, a National content leader. Teachers are required to submit lesson internalization plans each Monday after reviewing the scripted curriculum and units. By Wednesday, Assistant Principals of Instruction (APIs) provide feedback to teachers, and Regional content coaches review the quality of this feedback to ensure alignment with instructional expectations. Teachers also participate in Exit Ticket huddles, during which they analyze student performance and submit next instructional steps based on Exit Ticket data. PLCs include student work analysis to identify misconceptions, plan targeted reteach strategies, and refine instructional delivery. Priority teachers receive side-by-side planning support with their content APIs, including lesson rehearsals before delivering Tier 1 instruction. During rehearsals, leaders model expectations, provide actionable next steps, and allow teachers to practice and receive feedback. Campus leaders conduct daily classroom observations and deliver real-time coaching to reinforce effective instructional practices and ensure fidelity of implementation. | PLCs occur weekly, and each component of the PLC process is implemented on a weekly basis. | PLCs are facilitated weekly by campus Assistant Principals of Instruction (APIs), in collaboration with regional content coaches. When additional support is needed, national content leaders are engaged as side-by-side collaborators. | Teachers and Assistant Principals of Instruction are required to attend PLCs. Additionally, tutors and intervention support teachers acquired through school improvement funds are also required to attend PLCs. The campus principal attends for coaching support and feedback. | The campus will utilize a structured PLC protocol focused on lesson internalization, data analysis, and instructional planning. Each weekly PLC will follow a consistent cycle: Lesson Internalization: Teachers review upcoming lessons, identify key instructional moves, and anticipate areas of student misunderstanding. APIs and regional content coaches provide feedback to ensure alignment to curriculum and rigor. Exit Ticket and Data Analysis: Teachers analyze Exit Ticket results and student work to determine mastery levels, identify trends, and plan targeted reteach or extension strategies. Student Work Analysis: Teachers collaboratively examine samples of student work to identify misconceptions and plan adjustments to instruction, including questioning techniques and opportunities for productive struggle. Rehearsal and Practice: Priority teachers engage in lesson rehearsals, during which leaders model, provide feedback, and allow teachers to practice delivery before implementing Tier 1 instruction. The protocol is facilitated by APIs, supported by regional content coaches, and, when needed, national content leaders to ensure instructional consistency, data-driven decisions, and alignment to ESF expectations.
[9 empty] | N/A | Blue Bonnet Math and Wit and Wisdom have a Mid Module assessment for each module, as well as an End-of-Module assessment. Assessment days vary by grade level according to the length of the unit. | The campus has the following Deliberate Practice structure. | PLC's are organized by grade level and are held during teachers' planning. | Lesson planning PLCs occur weekly on Tuesdays. | Assistant Principals facilitate the planning sessions. | Teachers and Assistant Principals are required to attend PLCs. The Principal also attends and Regional Math Coaches occasionally attend. | The campus currently utilizes the Guidepost for Excellent Teaching (GET)—the district’s teacher appraisal and development system—as the foundation for side-by-side planning and instructional coaching. The GET is a rubric used to determine the level of proficiency in lesson planning, student engagement, and instructional delivery. This protocol ensures that lesson planning, execution, and feedback are aligned to high-quality instructional expectations. Pre-Work Completed Prior to Side-by-Side Planning: Teachers and leaders routinely: Identify the upcoming week’s lessons using the teacher’s scope and sequence. Identify lesson objectives and corresponding state standards from the Module/Unit Addendum in Curriculum Corner. Complete exemplar student responses for lesson assessments. Review the accommodations snapshot for the class to ensure supports for all learners. During the Side-by-Side Planning Meeting (Aligned to GET 1B – Lesson Internalization): See It: The leader walks the teacher through the lesson internalization protocol and models the priority strand of GET 1B. Name It: The leader prompts the teacher to identify and stamp the action step aligned to the prioritized GET 1B strand. Do It – Plan: The teacher revises or plans the lesson action step with guidance from the leader. Do It – Practice (Optional): The leader and teacher rehearse instructional delivery focused on the GET 1B strand. Close & Follow-Up: The leader sets a lesson resubmission deadline and schedules an observation aligned to instructional delivery.
[11 empty] | Thursdays and Fridays leaders facilitate lesson rehearsals with teachers to allow practice and coaching before lesson implementation. Priority math and Reading teachers also have morning lesson rehearsals three days each week that encompass the lesson they will implement that day. | Lesson rehearsals include the one math or reading teacher on each grade level and the Assistant Principal. | For priority teachers, lesson rehearsals happen at least 4 days each week. For non-priority teachers, rehearsals happen 1-2 days each week. | Assistant Principals facilitate the rehearsals. | Teachers and Assistant Principals are required to attend PLCs. The Principal also attends. National and Regional Math Coach occasionally attend. | Leaders names the most pressing problem/trend and the focus of the rehearsal. Teacher rehearses the “I Do” section (or another key lesson component) of the lesson. · Leader models the skill · Leader pauses at the point of error to provide real time coaching as needed. Teacher restates the feedback that was provided and thinks about how to implement the feedback in the 2nd round of practice.· Leader informs teacher of what follow up will look like during observations.
[11 empty] | Faculty professional development occurs each Tuesday for one hour based on campus needs and data. Team, we hold PD and staff meetings after school on Tuesdays. 1st Tuesday, 4:30 – 5:30 = Content DP 2nd Tuesday, 4:30 – 5:30 = Special Pops/ or data 3rd Tuesday, 4:30 – 5:30 = Practice Clinics 4th Tuesday, 4:30 – 5:30 = Lesson and Unit Unpacking | Teachers of all grades and contents attend; however, teachers work with others in the same content. | Campus professional development sessions occur weekly on Tuesdays. | Professional development sessions are either led by Principal, Assistant Principal and/or teacher leaders. | Lead teachers, counselors, Assistant Principals and the Principal are required to attend 100% of the sessions, Co-Teachers are chosen for certain sessions that are relative to the scope of their positions. | Teachers arrive at 4:30 with specified deliverables. Leader will present new learning to teachers and they will either take notes, complete action steps to practice, etc. The last 15-20 minutes is for practical application of the learning where teachers have time to either work independently or with content teachers on planning and implementation.

## ACE (hidden)
Criteria for Success
Does the plan meet the requirements outlined in Texas Education Code, Section 39A.105(b)? -The plan provides for the assignment of a principal to the campus who has demonstrated a history of improvement in student academic growth at campuses in which the principal has previously worked and gives the principal final authority over personnel decisions at the campus. -The plan provides that at least 60 percent of the classroom teachers assigned to the campus are teachers who demonstrated instructional effectiveness during the previous school year, with instructional effectiveness determined by: +for a teacher who taught in the district during the previous school year: `the teacher's impact on student growth as determined using a locally developed valueadded model that measures student performance on at least one assessment selected by the district. `an evaluation of the teacher based on classroom observation. +for a teacher who did not teach in the district during the previous school year, data and other evidence indicating that if the teacher had taught in the district during the previous school year, the teacher would have performed in the top half of teachers in the district. -The plan includes a detailed description of the employment and compensation structures for the principal and classroom teachers, which must include: +significant incentives for a high-performing principal or teacher to remain at the campus. +a three-year commitment by the district to continue incentives for the principal and teachers. -The plan includes policies and procedures for the implementation of best practices on the campus, including: +data-driven instructional practices +a system of observation of and feedback for classroom teachers +positive student culture on the campus +family and community engagement, including partnerships with parent and community groups +extended learning opportunities for students, which may include service or workforce learning opportunities +providing student services before or after the instructional day that improve student performance, which may include tutoring, extracurricular activities, counseling services, and offering breakfast, lunch, and dinner to all students at the campus -The plan includes assistance by a third-party provider that is approved by the commissioner in the development and implementation of the district's plan.
ONLY IF YOU SELECTED ACE AS YOUR SCHOOL IMPROVEMENT STRATEGY
Question | List or copy and paste all SI - identified campuses below | Has this campus (or this set of campuses) completed a planning year for the SAF grant for the ACE model? | (Optional) Upload your school design plan. This plan must meet the criteria in TEC Section 39A.105(b). | Would you like to provide more detail about the implementation of your ACE model? (Select yes if your School Design Plan does not meet the criteria in TEC Section 39A.105(b).) | Please describe the system the district will use to track teacher and administrator effectiveness at campuses implementing the ACE model. | What targets will the district set to identify which teachers and administrators are highly effective? | Please describe the incentives the district will offer to high-performing principal or teacher to remain at the campus. | Has the district made a minimum three-year commitment to continue incentives for the principal and teachers? | How will the district ensure that the principal assigned to each ACE campus has demonstrated a history of improvement in student academic growth at campuses in which the principal has previously worked? | Will the principal have final authority over personnel decisions at each campus implementing the ACE model? | How will the district ensure that at least 60 percent of the classroom teachers assigned to the campus are teachers who demonstrated instructional effectiveness during the previous school year? | Describe how the campus will implement research-based instructional strategies. | Describe how the campus will implement data-driven instructional practices. | Describe how the campus will implement positive student culture on the campus. | Describe how the campus will implement family and community engagement, including any partnerships with parent and community groups. | Describe how the campus will implement extended learning opportunities for students, which may include service or workforce learning opportunities. | Describe how the campus will provide student services before or after the instructional day that improve student performance (for example, tutoring, extracurricular activities, counseling services, and offering breakfast, lunch, and dinner to all students at the campus).
Additional Instructions | List all SI campuses in the district utlizing ACE as their school improvement strategy
Answer(s)

## Closure and Reassignment (hidden)
Criteria for Success
Does the plan ensure that students are assigned to a higher performing campus? -All students from the closing campus are assigned to a campus with an acceptable (C or better) performance rating. -All receiving campuses will increase the quality of the instructional materials to be used at the campus (if not already implementing SBOE-approved HQIM or OER). -All receiving campuses have a capacity building plan that includes upfront training and ongoing coaching for campus leaders and teachers. -The capacity building/professional development (PD) plan for all receiving campuses matches the state of talent at each receiving campus after the reassignment of staff is complete. +There is a plan to differentiate and/or increase support for teachers, administrators, and principal managers that are new (in their first two years) to their role. +There is a plan to differentiate and/or increase support for teachers, administrators, and principal managers that do not have a demonstrated track record of success. +There is a plan to differentiate and/or increase support for uncertified teachers. -Teachers and administrators receive capacity building support related to supporting students in special populations that is aligned with the student population at the campus.
ONLY COMPLETE THIS SECTION IF YOU NAMED CLOSURES/REASSIGNMENT AS YOUR SCHOOL IMPROVEMENT STRATEGY
Reassignment Landscape Analysis |  |  |  |  | Receiving Campuses
Question | Campus #1 | Campus #2 (if applicable) | Campus #3 (if applicable) | Campus #4 (if applicable) | Question | Additional Instructions | Campus #1 | Campus #2 (if applicable) | Campus #3 (if applicable) | Campus #4 (if applicable)
Campus Name |  |  |  |  | Campus Name
Campus CDCN |  |  |  |  | Please select the adopted curriculum for each receiving campus.
Most recent state accountability rating |  |  |  |  | Is this the curriculum that will be implemented for the duration of the plan? | If Yes, skip to row 10 If No, go to next line
Current enrollment of the campus |  |  |  |  | What new curriculum will be adopted?
Maximum enrollment for the campus |  |  |  |  | When will the district adopt the new curriculum?
Distance from the campus to the closing campus |  |  |  |  | How will the district ensure that each campus will meet the minimum instructional minutes required to implement the curriculum?
% of students from the closing campus that will be assigned to this campus |  |  |  |  | Please describe your planned training/PD sessions (and who delivers and attends) for: Principal manager, Principal, Other campus admin (assistant principals, instructional coaches), Teachers
% of teachers from the closing campus that will be assigned to this campus |  |  |  |  | How will you differentiate training for inexperienced (less than 2 years in role) and/or ineffective teachers/leaders ?
% of administrators from the closing campus that will be assigned to this campus |  |  |  |  | What tool will be used to evaluate implementation of the training (for example, classroom walkthrough tool, leadership coaching tools)? What look fors will be included in this tool?
How frequently will each teacher receive an observation from an instructional leader or coach, and receive feedback?
What capacity building supports related to supporting students in special populations will teachers and administrators receive?

## Graduation Rate (hidden)
Criteria for Success
How will the campus provide individualized supports to students at risk of dropping out? -The campus and district track individual, student-level data including, at a minimum, absences, grade retention, and academic outcomes. -Individual, student-level data is reviewed at least once per semester. -Campus staff or mentors assigned to students receive training related to the needs of students who are at risk of dropping out. -The plan includes strategies to improve student attendance.
ONLY COMPLETE THIS SECTION IF YOU NAMED IMPROVE GRADUATION RATE AS YOUR SCHOOL IMPROVEMENT STRATEGY
Question | List or copy and paste all SI - identified campuses using "improve graduation rate" as a school improvement strategy below | Please describe the overall strategy to improve the graduation rate at this campus/these campuses. | What student level data points will the campus track? | How frequently will student level data be reviewed and who will review the data? | What training will campus staff or mentors receive? | What is the attendance rate at the campus? | What strategies will the district implement to improve student attendance?
Additional Instructions | Go to tab 5. School Improvement and list all campuses below that named "improve graduation rate" as a school improvement strategy
Answer(s)

## School Model Change (hidden)
ONLY COMPLETE THIS SECTION IF YOU NAMED SCHOOL MODEL CHANGE AS YOUR SCHOOL IMPROVEMENT STRATEGY
Question | List or copy and paste all SI - identified campuses using "ACE" as a school improvement strategy below | Please provide a brief overview (2-3 sentences) of your school model change.
Additional Instructions | List all campuses below that named "school model change" as a school improvement strategy
Answer(s)

## Texas Partnerships
Criteria for Success
Is the district preparing to engage in quality authorizing? -A representative from the district has attended or is signed up for TEA-approved authorizer training. -The district has adopted a local charter authorizing board policy. -The district is in the process of applying for or has received approval for Texas Partnerships (SB 1882) benefits. -The operating partner of the campus has a track record of successful school turnaround.
ONLY COMPLETE THIS SECTION IF YOU NAMED TEXAS PARTNERSHIPS AS YOUR STRATEGY IN 5.2 FOR A CAMPUS
Question | List or copy and paste all SI - identified campuses using "improve graduation rate" as a school improvement strategy below | Please share the name and role of any district staff members that have completed TEA-approved authorizer training. | Please share the name and role of any district staff members that are signed up for or are currently enrolled in TEA-approved authorizer training. | Has the district adopted a local charter authorizing board policy? | Date the board approved or will vote on approving partnership | Has the district been approved for Texas Partnerships benefits? | Please describe the proposed or approved operating partner's track record of successful school turnaround.
Additional Instructions | Go to tab 5. School Improvement and list all campuses below that named "Texas Partnerships" as a school improvement strategy |  |  |  |  | Options: Application in progress, Application approved, Application denied, Not applying for Texas Partnerships benefits
Answer(s) |  | Geta Mitchell, Director of Student Services | Geta Mitchell, Director of Student Services | YES | The partnership was approved and contract signed by the MISD on March 6, 2019. | YES | IDEA Public Schools has a 25-year track record of successfully improving academic outcomes for students across Texas and the nation. As a nationally recognized, high-performing charter management organization, IDEA operates over 150 schools and has consistently demonstrated strong academic results, particularly in historically underserved communities. IDEA has been repeatedly recognized for high levels of student achievement, high college matriculation and persistence rates, and for maintaining rigorous instructional systems that support rapid improvement on struggling campuses. Prior to the partnership with Midland ISD, IDEA’s turnaround success included lifting multiple campuses from “Improvement Required” or low-performing ratings to meeting or exceeding state accountability standards through strong instructional leadership, data-driven practices, strategic staffing, and systems aligned to the Effective Schools Framework.

## Capacity Building
Criteria for Success
Does the plan ensure that administrators and teachers receive appropriate job-embedded training? -Administrators responsible for the campus (including the principal and principal manager) receive upfront/initial training on key elements of the school improvement strategy. -Teachers receive upfront/initial training on key elements of the school improvement strategy. -Teachers receive an observation and feedback round from an instructional leader or coach at least biweekly. -The observation tool includes research-based instructional strategies (RBIS) look fors. -The observation tool includes look fors related to implementation of approved curriculum. -The capacity building/professional development (PD) plan matches the current state of talent at the campus. +There is a plan to differentiate and/or increase support for teachers, administrators, and principal managers that are new (in their first two years) to their role. +There is a plan to differentiate and/or increase support for teachers, administrators, and principal managers that do not have a demonstrated track record of success. +There is a plan to differentiate and/or increase support for uncertified teachers.
DO NOT INCLUDE TEXAS PARTNERSHIP STRATEGY, ACE, OR GRADUATION RATE STRATEGY CAMPUSES
Question | List or copy and paste all SI - identified campuses below | Please describe your planned training/PD sessions (and who delivers and attends) for: -Principal manager -Principal -Other campus admin (assistant principals, instructional coaches) -Teachers | How will you differentiate training for inexperienced (less than 2 years in role) and/or ineffective teachers/leaders ? | What tool will be used to evaluate implementation of the training (for example, classroom walkthrough tool, leadership coaching tools)? What look fors will be included in this tool? | How frequently will each teacher receive an observation from an instructional leader or coach, and receive feedback? | What capacity building supports related to supporting students in special populations will teachers and administrators receive?
Additional Instructions | List all SI campuses in the district excluding Texas Partnership, ACE, or Graduation Rate | Comprehensive Development and Quality Assurance System The Turnaround Plan is anchored in a Comprehensive Development Plan (CDP) that serves as the annual professional development roadmap for Principals, Assistant Principals of Instruction (APIs), and Vice Presidents of Schools (VPs). The CDP outlines the scope and sequence of leadership development throughout the year, ensuring alignment with district priorities, the Effective Schools Framework, and the leadership competencies essential for school improvement. Each leadership protocol within the plan is supported by a corresponding Quick Check document, designed to serve as both a quality assurance tool and an observation guide. These Quick Checks allow leaders at every level—VPs, Principals, and APIs—to monitor implementation fidelity, provide actionable feedback, and ensure consistency across campuses. The Quick Checks are directly aligned to the district’s Leadership Competencies, ensuring that coaching, reflection, and evaluation processes reinforce the targeted skills and behaviors needed to drive sustained campus improvement. Together, the Comprehensive Development Plan and its aligned Quick Checks establish a cohesive system for leadership growth, accountability, and continuous improvement.
| IDEA Travis Academy | Get Better Faster Coaching & Development Cycle Provider: Regional Executive Director, Director of Leadership Development (DLD), Vice President of School Improvement (VPSI) Audience: Principal Supervisors, Principals, Assistant Principals of Instruction (APIs) Session Timeline: July 2025 - May 2026; June 2026 - June 2027 Year 2 Implementation Description: Principals and Vice President of Schools receive direct training from Get Better Faster Graduate School of Education in the Coaching and Development Cycle. This training focuses on building leader capacity in real-time coaching, practice-based feedback, and the use of structured coaching protocols. Throughout the 2025–26 school year, leaders will continue engagement with Get Better Faster through coaching labs, modeling sessions, and leadership practice. Principals will then cascade this learning to Assistant Principals of Instruction (APIs), who will apply Get Better Faster methods during "PLC" Structures, lesson internalization meetings, real-time feedback conversations, and rehearsal-based coaching with teachers. The Get Better Faster model becomes a foundational approach to leadership coaching, ensuring all instructional leaders coach with clarity, evidence, and practice-based corrections. | Leaders with less than two years of experience or those identified as needing additional support will receive intensified and side-by-side coaching directly from the Vice President of Schools. These leaders will participate in extended Get Better Faster practice labs with added modeling, rehearsal, and guided feedback. They will also engage in shadow coaching to observe real-time corrective feedback in action. To accelerate growth, they will receive increased observation and coaching touchpoints, up to two or three times per week, focused on mastering Get Better Faster competencies such as delivering precise feedback, addressing instructional misconceptions, and leading rehearsal-based development sessions. | Implementation of Get Better Faster coaching practices will be evaluated using leadership coaching logs, PLC and internalization observation forms, and real-time coaching rubrics. Look-fors will include the use of Get Better Faster coaching language (such as probe, praise, correct), evidence of live corrective feedback, rehearsal-based coaching structures, and alignment between leader feedback and teacher practice during instructional implementation. | Teachers will receive weekly informal observations with targeted feedback based on Get Better Faster coaching protocols. Priority or developing teachers will receive increased observations—up to three times per week—with real-time coaching support from instructional leaders. Daily informal power walks will be used to reinforce specific instructional strategies, and coaching corrections will be delivered in the moment to ensure immediate application of Get Better Faster practices. | Leaders will be trained to apply Get Better Faster coaching protocols to scenarios involving special populations, including SPED and Emergent Bilingual, students. Coaching sessions will model how to address instructional scaffolds, language supports, and behavior interventions during feedback and rehearsal. Administrators and teachers will receive guidance on using corrective feedback to adjust instruction for diverse learners and will collaborate with intervention teams to ensure alignment between coaching practices and student support plans.
|  | RBIS – Research-Based Instructional Strategies Provider: Region 1 Education Service Center Audience: Principals, Assistant Principals of Instruction (APIs), Regional Content Coaches Session Timeline: Description Principals, Assistant Principals of Instruction, and Regional Content Coaches will receive training from Region 1 Education Service Center on Research-Based Instructional Strategies (RBIS) in Reading and Math. This training focuses on improving instructional delivery through evidence-based practices that enhance clarity, modeling, scaffolding, and student engagement. Regional Coaches will attend alongside campus leaders to ensure alignment in coaching language, modeling expectations, and walkthrough feedback. APIs will use RBIS strategies during lesson internalization meetings, side-by-side coaching, lesson rehearsals, and ongoing teacher coaching. Teachers will not attend the initial training directly but will receive the strategies through leadership-led coaching, rehearsal, and feedback cycles. RBIS will serve as a support to the Guidepost of Effective Teaching (GET) foundation for classroom expectations, strengthening lesson design, instructional delivery, and student outcomes across campuses. | Differentiation of RBIS Training for Inexperienced and/or Ineffective Teachers & Leaders Inexperienced and ineffective leaders/teachers will receive layered support in RBIS through additional modeling, scaffolded planning templates, and guided practice on core instructional strategies such as modeling, checking for understanding, and scaffolding. These leaders will participate in small-group coaching sessions with Regional Content Coaches and will rehearse RBIS moves before implementing them with teachers. Increased observation and feedback cycles will be provided to reinforce RBIS application during lesson internalization, PLC facilitation, and classroom walkthroughs. | Implementation of RBIS will be evaluated using classroom walkthrough tools, data extracted from School Status, leadership coaching logs, and student work analysis protocols. Key look-fors will include the use of modeling and guided practice, checks for understanding, scaffolding strategies, and alignment of instructional delivery to lesson objectives. Evidence of teacher adjustment based on student responses and the use of corrective feedback will also be monitored. | Teachers will receive weekly informal walkthroughs with feedback focused on RBIS implementation, including modeling, CFUs, and scaffolding. Priority or developing teachers will be observed up to three times per week to ensure consistent use of RBIS strategies in instruction. Real-time coaching and corrective feedback will be provided during planning meetings, PLCs, and classroom practice to reinforce RBIS routines and teacher execution. In addition, Assistant Principals of Instruction (APIs) will receive coaching from Regional Team members trained in RBIS to ensure continuity of practice from leader development to classroom implementation across all content areas. | Teachers and leaders will receive support in applying RBIS strategies to instruction for special populations, including EB, SPED, and 504 students. Training will include how to scaffold instruction, adjust questioning, and provide language supports within core lessons. Regional Coaches will model how to use RBIS strategies during intervention planning and student work analysis to ensure instruction is responsive to diverse learning needs. APIs and teachers will also receive guidance on integrating RBIS with MTSS interventions to strengthen support for students requiring additional academic or behavioral assistance.
|  | Cooperative Learning & Engagement Structures Provider: Vice President of School Improvement (VPSI) Audience: Principals, Assistant Principals of Instruction (APIs), Teachers Description: Principals and Assistant Principals of Instruction will be directly trained by the VPSI on cooperative learning structures designed to increase academic engagement, student interaction, and accountable talk. This training equips leaders with practical strategies such as Turn-and-Talk, Think-Ink-Pair-Share, Continuum Protocol, and Whiteboards. Leaders will internalize and model these structures during Deliberate Practice (DP), professional development sessions, and walkthrough coaching. Teachers will receive engagement strategies through direct training provided by the VPSI. APIs will be responsible for coaching teachers in selecting and embedding engagement structures during lesson planning, rehearsal, and observation feedback. This training ensures a shift from teacher-led delivery to student-centered engagement across every classroom. | Inexperienced or ineffective teachers and leaders will receive additional modeling and guided practice on engagement structures to ensure correct implementation of engagement strategies. These individuals will participate in small-group practice sessions focused on scripted cooperative structures such as Turn-and-Talk, Think-Ink-Pair-Share, Continuum Protocol, and Whiteboards. Instructional leaders will provide side-by-side coaching during lesson planning and rehearsal to support timing, partner setup, and student accountability. For those who continue to struggle with implementation, the Engaging All Students one-pager will be provided as supplemental support to reinforce expectations and offer visual guidance on Engagement engagement routines. | Implementation of Engagement strategies will be evaluated using classroom walkthrough tools and student engagement observation checklists. Key look-fors will include visible use of cooperative structures, student-to-student interaction, equitable participation, structured talk routines, and teacher facilitation of active engagement rather than passive delivery. Observers will also look for correct setup of pairs or teams, expected verbal/physical response formats, and evidence that every student is accountable for participation. | Teachers will receive weekly informal walkthroughs with feedback focused on the use of Engagement cooperative structures and student engagement routines. Priority or developing teachers will be observed up to three times per week to ensure consistent implementation of engagement strategies such as Think-Ink-Pair-Share and Turn & Talk. Daily power walks will be used to reinforce specific engagement techniques, with real-time coaching provided to adjust pacing, partner setup, or questioning during lessons. | Teachers and leaders will receive guidance on adapting Engagement structures to support special populations, including SPED, EB, and 504 students. Training will emphasize how to modify partner assignments, scaffold language supports, and embed sentence stems to ensure all learners can engage in cooperative structures. Regional Coaches will model how to use Engagement routines to increase participation for students with language or processing needs, and the Engaging All Students one-pager will be used as a resource to reinforce inclusive engagement practices.
|  | Batch Coaching for Leaders Provider: VP of Schools & Regional Coaches Audience: Principals and Assistant Principals of Instruction (APIs) Session Timeline: Sept 2025 Description: Batch Coaching sessions are facilitated by the Vice President of Schools and Regional Coaches to strengthen instructional leadership capacity among Principals and Assistant Principals of Instruction. These sessions focus on core coaching strands such as lesson internalization, Know-Do chart development, and real-time coaching, Leaders engage in practice-based learning rather than passive training, rehearsing how to deliver high-quality feedback, co-plan with teachers, and correct instructional misconceptions during live lessons. Batch Coaching provides a collaborative, small-group environment where leaders observe modeling, practice coaching moves, and receive direct feedback to sharpen their instructional leadership execution. The intent is to ensure every campus leader can coach teachers with precision, clarity, and urgency. | Inexperienced Leaders (Less than 2 Years in Role) These leaders will receive enhanced scaffolding and foundational guidance during Batch Coaching sessions, including: Pre-Work Orientation: Introduction to core coaching tools such as Know-Do Charts, lesson internalization protocols, and feedback frameworks. Model & Imitate Cycles: Direct modeling by Regional Coaches followed by structured practice with scripts. Side-by-side Coaching: Step-by-step coaching rehearsals before implementing with teachers. Ineffective or Developing Leaders Leaders who have demonstrated gaps in implementation or performance will receive high-touch, corrective support: Real-Time Coaching: Immediate feedback during practice with opportunities to retry on the spot. Micro-Coaching Cycles: Focused on one strand at a time (e.g., feedback delivery, rigor checks) until mastery is demonstrated. Accountability Checkpoints: Specific growth goals built into individual coaching logs and leadership development plans. | The following tools will be used to assess whether training practices are being implemented with fidelity: G-E-T Rubric Input (School Status) Leadership Quick Check Reports Feedback from Lesson Internalization Feedback from Student Work Analysis Protocol Implementation | Each teacher will receive ongoing observation and feedback through a layered system of daily, weekly, and formal coaching structures. The frequency and intensity of support will increase based on teacher need and priority status. Standard Frequency for All Teachers Daily Informal Power Walks with a focus on specific instructional strategies (e.g., engagement, questioning, lesson execution) Weekly Informal Observations with actionable feedback Increased Frequency for Priority Teachers (Inexperienced or Ineffective) Three observations per week (minimum), each with targeted instructional feedback Daily Real-Time Coaching using live correction, modeling, and rehearsal Increased touchpoints through lesson rehearsals to reinforce strategy execution | To build capacity in supporting students within special populations, designated school leaders will participate in specialized Point-Person Webinars focused on EB, CSI, 504, and PBIS responsibilities. These sessions provide critical updates on compliance requirements, intervention protocols, and case management practices. Leaders receive guidance on progress monitoring expectations and referral processes, including Intervention Requests, ARD procedures, and RTI documentation, ensuring accurate and timely support for students. In addition to these webinars, administrators and instructional leaders will engage in MTSS and intervention training delivered by the Regional Team and the Education Service Center. This training develops a strong understanding of tiered intervention systems for both academic and behavioral needs, emphasizing data-based decision-making through the use of progress monitoring tools. Leaders also receive support in establishing effective collaboration structures with counselors, interventionists, and SPED case managers to ensure students receive coordinated and comprehensive services.
|  | VPS Collaborations (Executive-Level Leadership Development) Provider: National Vice President of Schools Audience: Vice Presidents of Schools (VPS) Session Timeline: Description: VPS Collaborations are high-level executive leadership sessions facilitated by the National Vice President of Schools. These sessions focus on strategic leadership priorities such as Path to an A and Rigor Threats, equipping Vice Presidents of Schools with the tools to drive consistent performance across regions. The collaborative format provides space for structured problem-solving, data analysis, leadership scenario planning, and accountability alignment. VPS participants engage in reflective dialogue, share implementation challenges, and refine strategies for supporting principals and APIs. Unlike technical coaching, VPS Collaborations emphasize executive decision-making, system alignment, and large-scale instructional leadership execution. These sessions ensure a united leadership vision across the organization. | New or developing Vice Presidents of Schools will receive differentiated support during VPS Collaborations through smaller executive breakout sessions, strategic leadership case studies, and targeted coaching. These VPS leaders will receive direct coaching and support from the National Vice President of Schools and, when necessary, from the Regional Executive Director. This additional layer of support will focus on strengthening executive decision-making, system alignment, performance management, and the execution of regional priorities such as Path to an A and Rigor Threats. Follow-up executive coaching will be provided to reinforce readiness and improve leadership outcomes across regions. | Implementation of executive leadership strategies from VPS Collaborations will be evaluated using executive coaching logs, regional performance dashboards, and leadership alignment trackers. Key look-fors will include clarity of regional priorities, consistency in leadership messaging, progress toward Path to an A goals, response to rigor threats, and alignment between VPS directives and campus execution. Evidence of strategic decision-making, escalation protocols, and follow-through on leadership commitments will also be monitored. | Vice Presidents of Schools will receive executive feedback through bi-weekly strategic check-ins with the National Vice President of Schools or the Regional Executive Director. VPS leaders requiring additional support may receive weekly coaching sessions focused on leadership alignment, regional performance risks, and escalation decisions. Informal leadership touchpoints will occur during national leadership meetings and data reviews to ensure timely calibration and follow-through on organizational priorities such as Path to an A and Rigor Threats. | Vice Presidents of Schools will receive support on overseeing services for special populations through collaboration with national and regional specialists in MTSS, EB, SPED, and 504. During VPS Collaborations, leaders will analyze disproportionality data, review intervention acceleration plans for House Bill 1416 students, and align regional expectations for inclusive instructional practices. VPS leaders will be equipped to hold principals accountable for intervention implementation, progress monitoring, and the allocation of resources necessary to meet the needs of diverse learners across campuses.
|  | Principal Collab (Leadership Alignment Sessions) Provider: VP of Schools and Regional Team Members Audience: Principals Session Timeline: Sept. 18 Description: Principal Collaborations are monthly leadership alignment sessions designed exclusively for Principals to receive focused coaching, professional development, and strategic problem-solving support. Facilitated by the VP of Schools and Regional Leadership Teams, these sessions ensure principals are equipped to lead instructional implementation, manage upcoming priorities, and drive campus performance goals with clarity and coherence. Each region determines the content focus based on need, but sessions consistently include: Time to complete required Roadmaps Unpacking upcoming priorities in the Principal Playbook Previewing what’s approaching in API trainings to ensure alignment and coherence across leadership teams In addition to planning and alignment, Principal Collaborations provide space for principals to: Analyze campus data and address leadership challenges Calibrate expectations and share best practices Rehearse leadership moves such as PLC facilitation, culture resets, and feedback practices Regions are encouraged to incorporate targeted sessions, especially for new or developing principals such as: Setting Priorities and aligning master calendars Preparing Professional Development for staff Planning Schoolwide Culture Resets to reinforce expectations and climate By design, Principal Collaborations build a unified approach to instructional leadership, accountability, and campus readiness—ensuring that principals lead proactively rather than reactively as organizational priorities unfold. | Inexperienced principals (less than two years in role) and principals identified as needing additional support will receive intensified and tiered coaching during Principal Collaborations. These leaders will engage in side-by-side coaching with the VP of Schools, as well as Regional and National Leaders, to rehearse core leadership practices such as PLC facilitation, culture resets, and Roadmap execution. As an additional layer of support, they will work directly with the VP of School Improvement under a scripted plan of improvement to address specific leadership gaps. These principals will also attend Principal Academy sessions and receive targeted breakout support, leadership modeling, and scenario-based practice to build foundational readiness and ensure consistent execution. | Implementation of leadership practices from Principal Collaborations will be evaluated using leadership coaching logs, principal progress monitoring tools, and leadership observation rubrics. Key look-fors will include evidence of strategic planning through completed Roadmaps, facilitation of effective PLCs, execution of culture reset plans, data-driven leadership decisions, and the application of collaboration practices discussed during sessions. Fidelity to follow-up actions and leadership reflection will also be monitored. | Principals will engage in weekly leadership check-ins with the VP of Schools. During these sessions, the VP of Schools will monitor progress and determine whether additional support is needed from regional or national content leads. Principals identified as needing intensified support or placed on a plan of improvement will receive up to two to three coaching sessions per week, including real-time leadership feedback during PLCs, walkthroughs, and culture implementation. Daily informal leadership walkthroughs will also occur to monitor application of strategies introduced during Principal Collaborations. | Principals will receive leadership guidance on supporting special populations through targeted collaboration with regional MTSS, EB, SPED, and 504 point leads. During Principal Collaborations, leaders will participate in sessions focused on designing and monitoring intervention systems, including required intervention and acceleration supports for House Bill 1416 students. Implementation of these supports will be closely monitored by the VP of School Improvement through campus visits conducted at least twice per week, ensuring principals are applying feedback and effectively leading intervention structures. Additional assistance may be allocated from regional or national specialists to strengthen intervention planning, progress monitoring, and data review protocols for diverse learners.
|  | Depth of Knowledge (DOK) Training Provider: VP of School Improvement Audience: Principals, APIs, Teacher Leaders Description: Depth of Knowledge (DOK) training equips instructional leaders and teachers with a framework to assess and elevate the cognitive rigor of instruction and student tasks. Leaders and teachers learn to distinguish between recall-level activities and higher-level strategic and extended thinking, ensuring lesson objectives, questioning, and assignments meet the demands of standards and assessments. Classroom teachers will apply DOK during lesson planning by aligning tasks directly to the TEKS and ensuring Checks for Understanding (CFUs) either match the rigor of the standard or appropriately scaffold toward it. Principals and APIs are trained to identify DOK levels within lesson plans, walkthroughs, and student work samples, using DOK analysis during feedback cycles, planning meetings, and PLCs to push instruction beyond compliance toward deeper reasoning, synthesis, and problem-solving. | Inexperienced or ineffective leaders/teachers will receive additional support through scaffolded DOK sessions that focus on identifying and designing rigorous questions and tasks. These leaders will engage in guided practice using sample lesson plans and student work to distinguish between DOK levels and rehearse how to push instruction beyond recall. Side-by-side coaching from the VP of School Improvement will be provided to model how to integrate DOK into feedback, walkthroughs, and PLC facilitation. Leaders needing additional support will also receive exemplars and scripted question stems to strengthen their ability to coach teachers toward deeper cognitive rigor. | Implementation of DOK will be evaluated using classroom walkthrough tools, lesson plan reviews, and PLC observation rubrics. Key look-fors will include alignment of lesson objectives to TEKS, use of DOK-aligned questioning, and inclusion of Checks for Understanding that require deeper reasoning rather than recall. Observers will also monitor whether tasks are designed to meet or scaffold toward the cognitive rigor of the standard, and whether leaders are coaching teachers to push student thinking from surface to strategic and extended levels. | Teachers will receive weekly walkthroughs focused on the rigor of questioning, task alignment, and the depth of student responses. Priority or developing teachers will receive up to two to three targeted observations per week to monitor the use of DOK-aligned questioning and TEKS-based scaffolds. Real-time coaching will be provided during lesson internalization meetings and PLCs to reinforce the use of higher-level prompts and Checks for Understanding that push beyond recall. | Teachers and leaders will receive guidance on adapting DOK-aligned questions and tasks to support special populations, including EB, SPED, and 504 students. Training will include strategies for scaffolding rigor using language supports, visual cues, and structured response frames to ensure all students can access higher-order thinking tasks. Leaders will be coached on how to analyze student work from special populations using DOK criteria and how to adjust TEKS-aligned checks for understanding to promote equitable access to cognitive rigor.
|  | MTSS Leadership Training Provider: Houston Regional Team & Region Education Service Center (Region Service Center) Audience: Principals, APIs, Counselors, MTSS/Student Support Teams, Teachers Session Timeline: July 16, Sept 11 (Org. Priority) - June 2027 Description Multi-Tiered Systems of Support (MTSS) training was initially delivered by the Regional Team to establish foundational systems for identifying, monitoring, and responding to students’ academic, behavioral, and social-emotional needs. This initial phase focuses on building campus leadership competency in Tier 1 instructional supports, Tier 2 intervention protocols, and Tier 3 individualized planning. Following the Regional Team’s training, the Education Service Center reinforces and deepens campus capacity through ongoing sessions, calibration support, and technical assistance. These follow-up trainings emphasize data-driven decision-making, progress monitoring tools, intervention scheduling, and consistent documentation practices. Principals, APIs, and student support leaders apply MTSS frameworks when leading intervention meetings, collaborating with special education and counseling teams, and coaching teachers on differentiation and progress tracking. The goal is to build a sustainable, aligned intervention system that supports student growth and reduces disproportionality across campuses. | Inexperienced leaders and leaders identified as needing additional support will receive enhanced MTSS coaching through smaller cohort training, targeted intervention planning sessions, and side-by-side support from Regional MTSS specialists. These leaders will be guided through model intervention meetings and progress monitoring protocols with additional time allocated for practice and feedback. The VP of School Improvement and Regional Team members will provide individualized coaching on Tier 1–3 systems, documentation procedures, and intervention referrals to ensure readiness and accurate execution of MTSS responsibilities. | Implementation of MTSS practices will be evaluated using intervention tracking tools, campus MTSS implementation rubrics, and leadership coaching logs. Key look-fors will include evidence of scheduled intervention meetings, use of progress monitoring data, proper documentation of Tier 2 and Tier 3 supports, and alignment of services for House Bill 1416 students. Observers will also monitor academic block placement and reassignment decisions based on student need or improvement, ensuring that intervention time is data-driven and responsive. Fidelity to intervention referral processes, collaboration with counselors, SPED, and EB teams, and follow-up actions for student support plans will also be reviewed. | Leaders will receive weekly check-ins focused on MTSS implementation, with priority leaders receiving up to two to three monitoring sessions per week. During campus visits, the VP of School Improvement and Regional MTSS specialists will review intervention logs, academic block rosters, and reassignment decisions based on student need or improvement. Daily informal walkthroughs will be used to monitor Tier 1 instructional supports, including the application of lesson internalization feedback, scripting of student groupings, and scaffolds built for EB, SPED, and struggling learners. Teacher execution will also be tracked through engagement monitoring labs to ensure interventions are being applied consistently in classrooms. | Teachers and leaders will receive targeted capacity-building support focused on serving special populations through MTSS intervention planning, data analysis, and collaborative problem-solving. Regional teams will provide guidance on designing Tier 1 scaffolds, Tier 2 intervention groups, and Tier 3 individualized plans for EB, SPED, 504, and House Bill 1416 students. Ongoing support will include modeling how to incorporate language supports, behavioral strategies, and progress monitoring tools into daily instruction. Leaders will be coached on how to align intervention decisions with lesson internalization, student grouping, and academic block placement to ensure students with the greatest needs receive accelerated support.
|  | Content-Specific Professional Development (PD) Provider: Assistant Principals of Instruction, Regional Content Coaches, National Content Teams, or External Subject Experts Audience: Assistant Principals of Instruction (APIs), Teacher Leaders, Reading/Math/Science Teams Session Timeline: Description Content-Specific Professional Development focuses on deepening instructional leaders' and teachers’ expertise in core subject areas such as Reading, Math, and Science. These sessions are led by Regional Content Coaches, National Content Teams, or certified subject-area experts. Training includes standards alignment, unit internalization, assessment calibration, error analysis, and student work protocols. Leaders learn how to guide teachers in delivering content with accuracy, rigor, and clarity. APIs will integrate content training into PLCs, lesson rehearsals, and walkthrough coaching. Principals will monitor implementation through lesson observations and student outcomes. This PD ensures that instructional leadership is not generic but grounded in discipline-specific best practices. | Inexperienced and ineffective APIs and teacher leaders will receive additional support through scaffolded content sessions, extended planning labs, and guided unit internalization. These leaders will participate in small-group coaching with Regional Content Coaches to build foundational content knowledge and rehearse discipline-specific practices such as modeling, error analysis, and assessment alignment. For those who need additional support, side-by-side coaching will be provided, along with exemplar lesson models and scripted content protocols to build accuracy and confidence in leading PLCs and content rehearsals. | Implementation of Content-Specific PD will be evaluated using content walkthrough tools, PLC observation forms, and student work analysis protocols. Key look-fors will include alignment of lessons to standards, accuracy of content delivery, use of content-specific academic vocabulary, and evidence of instructional adjustments based on error analysis. Observers will also monitor teacher use of discipline-based questioning, modeling of exemplars, and integration of assessment data to inform instructional decisions. | Teachers will receive weekly informal walkthroughs focused on the implementation of content-specific strategies introduced during PD sessions. Priority or developing teachers will receive up to two to three observations per week to monitor the accuracy of content delivery, questioning techniques, and corrective modeling. Instructional leaders will provide real-time feedback during PLCs, lesson rehearsals, and classroom practice to ensure content knowledge is translated into instructional execution with rigor and clarity. | Teachers and leaders will receive support on adapting content instruction to meet the needs of special populations, including EB, SPED, and 504 students. Content PD will include guidance on scaffolding complex texts, providing language supports, and redesigning assessment items to accommodate varied learner needs. Regional Content Coaches will model how to embed accommodations and differentiation into unit plans, while instructional leaders will use student work analysis to identify gaps and adjust instruction for targeted groups. Content-specific intervention strategies will also be reinforced to align with MTSS plans and House Bill 1416 acceleration requirements.
|  | API Academies Provider: VP of Schools, Regional Leadership Teams, and National Content Teams Audience: Assistant Principals of Instruction (New APIs and Returning APIs Needing Additional Support) Session Timeline: Begins in June (BOY Academies) with Ongoing Monthly Sessions Description: API Academies are designed to build foundational leadership capacity for Assistant Principals of Instruction, ensuring they are prepared to lead instructional coaching, facilitate data-driven classrooms, and manage key academic systems. New APIs (less than two years in role) and returning APIs who require targeted development are selected to participate, with attendance determined by Vice Presidents in collaboration with campus Principals. The Academy includes three key components: Webinars + Roadmaps (½ Day Sessions): Focus on operational leadership, including GET Certification Modules, Manager Talent Reviews, EB Supports, and SAF referrals. APIs who serve as EB, 504, CSI, or PBIS point people must attend specialized point-person webinars. Intellectual Prep (½ Day Sessions): Builds APIs’ instructional coaching capacity through content knowledge development and preparation to coach key teacher skills. Full-Day Leadership Training: Equips APIs with core leadership skills such as managing time and tasks, data analysis, behavior de-escalation, and rehearsal of PD delivery. Ongoing academy sessions throughout the year deepen essential API competencies, including leading student work analysis meetings, facilitating observation feedback, and driving teacher development within PLCs. API Academies ensure that instructional leadership is reinforced through coaching, not compliance, building strong pipelines of instructional leaders across campuses. | APIs with less than two years of experience or those identified as needing additional support will receive intensified coaching through additional breakout sessions, extended rehearsal time, and side-by-side leadership support during academy sessions. These APIs will be assigned targeted coaching from Regional Leaders and the VP of Schools, focusing on foundational leadership competencies such as time management, feedback delivery, and PLC facilitation. Where necessary, APIs may also receive supplemental practice labs and leadership playbooks, and may be assigned a scripted development plan to address specific performance gaps. | Implementation of API Academy training will be evaluated using leadership coaching logs, PLC facilitation rubrics, and observation feedback tools. Key look-fors will include alignment of API-led planning sessions to content standards, delivery of precise instructional feedback to teachers, effective facilitation of student work analysis, and use of time and task management systems introduced during academy sessions. Observers will also monitor the API’s ability to lead data discussions, manage teacher accountability, and implement leadership practices reinforced in academy modules. | APIs will receive weekly leadership coaching check-ins focused on their implementation of academy competencies, including PLC leadership, lesson internalization support, and feedback delivery. APIs requiring additional support or identified as developing will receive two to three coaching observations per week from Regional Leaders or the VP of Schools, with real-time adjustments provided during planning sessions, walkthroughs, and leadership huddles. Informal leadership touchpoints will occur daily to verify execution of systems such as teacher progress monitoring, data meetings, and rehearsal practices introduced in academy sessions. Leaders will also be required to engage in self-reflection via quick checks in order to self monitor. | APIs will receive training on supporting special populations through targeted modules and point-person webinars focused on EB, SPED, 504, and MTSS responsibilities. Academy sessions will include guidance on integrating scaffolds into lesson planning, using intervention data to support House Bill 1416 acceleration requirements, and aligning teacher coaching to student needs. Regional Content Leads and MTSS specialists will provide APIs with tools for monitoring progress, facilitating intervention meetings, and ensuring instructional adjustments are applied consistently across classrooms to support diverse learners.

## Milestones
Criteria for Success
How will the strategy be implemented? -Milestones include all activities needed to fully implement the program or strategy, covering planning and implementation stages. -Milestones include all upfront capacity building, implementation action steps, and ongoing support and coaching touchpoints, and student assessment cycles. -Milestones cover, at a minimum, the two school years that the campus is required to implement the plan.
Question | List or copy and paste all SI - identified campuses below | Please share the key milestones for this strategy
Additional Instructions | List all SI campuses in the district | Timeframe is, at minimum, through end of SY 26-27 for TIP and through end of SY 27-28 for TAP.
Answer(s) | IDEA Travis Academy | Travis Academy and College Prep TIP Milestone Document

## Performance Management
Criteria for Success
Has the district outlined a performance management plan that ensures the strategy will be implemented with fidelity? -There is a plan for plan performance management, including superintendent and other key leadership review of metrics and progress at a semesterly cadence. -The response describes: +Who will review progress towards milestones, +How frequently progress is reviewed, +How progress data will be collected, and +How it is shared with district leadership and other relevant stakeholders
Question | List or copy and paste all SI - identified campuses below | Please describe how district and campus leaders will monitor the successful implementation of this plan. | Who will be responsible for reviewing progress towards the milestones described in the previous section? | How frequently will progress toward milestones be reviewed? | How will milestone progress data be collected? | How will milestone progress data be shared with district leadership and other relevant stakeholders?
Additional Instructions | List all SI campuses in the district
Answer(s) | IDEA Travis Academy
|  | During the “Just a Goal ‘G’ Meetings,” campus principals, assistant principals of instruction, counselors, and assistant principals of operations presented their school improvement goals, strategies, and progress monitoring milestones to the Regional Superintendent, Vice President of School Improvement, Regional Executive Director, Vice President of Schools, Regional Director, and regional instructional coaches. The purpose of these meetings was to receive targeted feedback on the quality and alignment of goals and strategies. | Stakeholders responsible for reviewing progress toward milestones through this mechanism include the Regional Superintendent, Vice President of School Improvement, Regional Executive Director, Vice President of Schools, Regional Director, and regional instructional coaches. | Through this annual mechanism, milestones are presented and reviewed as part of the goal and strategy presentation process. | Milestone progress data will be collected through multiple monitoring systems, including observation and feedback trackers, coaching logs, PLC documentation, interim assessment results, and MTSS intervention progress reports. The principal will follow up with each lead team member during weekly check-ins and tactical meetings to ensure action plans are being implemented with fidelity. Progress Toward Goal (PTG) meetings will be held after Quarter 2 and Quarter 3 to review collected data, evaluate milestones, and adjust plans based on evidence of progress and student outcomes. | Milestone progress and data will be shared during Progress Toward Goal Meetings, where campus leaders and regional/national leadership teams reconvene to review data aligned to the campus’s academic and cultural goals. Progress toward goals, milestones, and milestone checkpoints will serve as key indicators of progress and success.
|  | On September 23, 2025, the campus participated in an IDEA School Review that met the requirements of TEC 39A.053 for a comprehensive local diagnostic. This annual School Review, conducted for priority campuses, serves as a formal quality audit and is used as the local diagnostic process in the 2025–2026 school year. Findings from the School Review established the baseline for school improvement and directly informed milestone development in the turnaround plan. | Progress toward milestones will be reviewed by the School Review team, which includes the Regional Superintendent, Vice President of School Improvement (VPSI), Vice President of Schools, Regional Executive Director, and regional instructional coaches. These district and regional leaders collectively analyze findings from the School Review to determine whether the campus is making sufficient progress toward its turnaround milestones. Campus principals and Assistant Principals of Instruction (APIs) are also responsible for responding to feedback and adjusting campus action steps based on the priorities identified during the review. This joint accountability between campus and regional leadership ensures that milestone progress is continuously aligned to the expectations established through the local diagnostic process. | Progress toward milestones identified in the School Review will be formally reviewed on an annual basis during the comprehensive School Review cycle, with follow-up monitoring occurring during scheduled leadership check-ins and quarterly data meetings. While the School Review establishes the baseline and priorities for the year, district and regional leaders revisit these priorities throughout the year to ensure that corrective actions are being implemented and that milestones remain on track. | Milestone progress data will be collected through the evidence gathered during the School Review process, including classroom observations, teacher and leader interviews, lesson internalization artifacts, Leadership Core Calendars, coaching and feedback documentation, and student culture systems. Review teams analyze instructional delivery, planning practices, culture implementation, and leadership systems against the priorities identified in the local diagnostic. This evidence is used to assess the extent to which the campus is implementing strategies tied to turnaround milestones and to determine whether progress is on track, stalled, or in need of targeted intervention. | Milestone progress data gathered through the School Review will be shared with district leadership and stakeholders through multiple communication and accountability structures. Formal feedback is delivered during post-review debrief sessions with campus and regional leadership, where findings and priority actions are documented and aligned to turnaround milestones. Progress updates are then revisited in leadership tactical and principal check-ins, where action steps and implementation evidence are monitored. For broader stakeholder engagement, data will also be shared during family engagement events and campus data conferences to ensure transparency around academic and cultural goals. In addition, milestones tied to instructional practice are reinforced through ongoing teacher coaching cycles, ensuring that classroom-level implementation remains aligned to expectations set during the School Review. This layered approach ensures that progress toward milestones is communicated clearly, owned collectively, and acted upon consistently across all levels of the campus community.
|  | District and campus leaders will monitor the successful implementation of this plan through structured Progress Toward Goal (PTG) meetings. During the PTG meeting, leaders and campus teams engage in a consultancy-style protocol where they present outcome data, receive feedback, and are asked probing questions to deepen their analysis and refine their strategies. | Progress toward milestones will be jointly reviewed during Progress Toward Goal (PTG) meetings by the Executive Director (ED), Vice President of School Improvement (VPSI), Vice President of Schools, campus principals, and Assistant Principals of Instruction (APIs), with oversight and support from regional and national leadership teams. | Progress toward milestones will be formally reviewed during Progress Toward Goal (PTG) meetings held after Quarter 2 and Quarter 3. These mid-year and spring reviews allow district and campus leaders to assess the effectiveness of implemented strategies, analyze outcome trends, and determine whether current action steps are sufficient to meet end-of-year goals. | Milestone progress data will be collected through the PTG pre-work and Outcomes–Causes–Solutions (OCS) analysis completed by each campus leader prior to the meeting. Leaders will gather and submit key evidence, including formative assessment results, interim data, coaching and observation logs, PLC artifacts, and implementation progress toward action steps. During PTG sessions, this data is presented, analyzed, and refined through feedback and questioning, ensuring that milestone progress is grounded in both quantitative outcomes and qualitative implementation evidence. | Milestone progress data will be shared through collaborative discussion and documentation during Progress Toward Goal (PTG) meetings, where campus and district leaders engage in a consultancy process to review Outcomes–Causes–Solutions analyses and agreed-upon next steps. Following each PTG, updated action plans and milestone adjustments will be entered into shared tactical documents and progress trackers, which are accessible to regional and national support teams. Key insights, progress updates, and required interventions will be communicated to district leadership through follow-up check-ins and tactical meetings, ensuring transparency, accountability, and ongoing support for successful plan implementation.
|  | Successful implementation of the plan will be monitored through weekly Campus Tactical Meetings, led by the principal and attended by all Assistant Principals of Instruction (APIs) and the Assistant Principal of Operations (APO). These tactical are structured, results-focused leadership meetings that review progress toward academic and operational milestones identified in the turnaround plan. During each tactical, campus leaders analyze instructional implementation, review student performance trends, and assess the status of action steps related to curriculum delivery, culture systems, and intervention supports. The principal facilitates problem-solving and alignment, ensuring that APIs and the APO are held accountable for executing their assigned priorities. Any barriers identified are assigned immediate action steps, and follow-up is monitored in subsequent tactical, creating a continuous cycle of review, adjustment, and support. This campus-based monitoring structure ensures real-time oversight and shared ownership among all members of the leadership team. | Progress toward milestones will be reviewed by the campus leadership team during weekly Campus Tactical Meetings. This team is led by the principal and includes all Assistant Principals of Instruction (APIs) and the Assistant Principal of Operations (APO). The principal is responsible for facilitating the review of milestone progress and ensuring alignment to the turnaround plan, while APIs provide updates on instructional implementation and student performance, and the APO reports on operational supports that impact execution. Together, this team collaboratively assesses whether milestones are being met, identifies barriers to progress, and determines if adjustments or additional support are needed. This shared responsibility ensures that every member of the leadership team remains accountable for driving progress toward campus goals. | Progress toward milestones will be reviewed weekly during Campus Tactical Meetings. These meetings are embedded in the campus leadership calendar to ensure a consistent cadence of monitoring and accountability. The weekly frequency allows the principal, APIs, and APO to track implementation in real time, respond quickly to emerging challenges, and adjust strategies before gaps widen. By reviewing milestones every week—rather than waiting for quarterly checkpoints—the campus leadership team maintains an active oversight cycle that supports continuous improvement and timely intervention. | Milestone progress data will be collected through a combination of instructional and operational evidence reviewed during Campus Tactical Meetings. This includes observation and feedback trackers, coaching logs, PLC documentation, interim assessment data, attendance and culture reports, and MTSS intervention progress. APIs and the APO bring updated metrics and implementation artifacts to each tactical, ensuring that discussions are grounded in current performance data rather than anecdotal input. Data dashboards that capture real-time progress toward goals are also referenced to validate milestone status. This structured evidence collection process allows campus leadership to make informed decisions, monitor the impact of strategies, and identify areas requiring additional support or adjustment. | Milestone progress data will be shared with district leadership and relevant stakeholders through the documentation and follow-up of Campus Tactical Meetings. Key action items, progress updates, and emerging barriers discussed during tactical are recorded in shared leadership trackers and escalated to regional leadership through principal check-ins and Portfolio Tactical meetings. Internally, the principal communicates updates to teacher teams during PLCs and staff huddles to ensure alignment between leadership decisions and classroom execution. When appropriate, high-level progress and adjustments are also communicated during family engagement events and data conferences to maintain transparency around academic and cultural goals. This layered communication structure ensures that milestone monitoring at the campus level is consistently connected to district oversight and stakeholder awareness.
|  | The successful implementation of this plan will be monitored through weekly leadership check-ins between the Executive Director and the Vice President of Schools, as well as with the Vice President of School Improvement when turnaround needs require intensified oversight. These check-ins are intentionally scheduled to review progress toward milestones, address challenges impacting instructional and cultural initiatives, and ensure leadership actions remain aligned to the turnaround priorities. Prior to each check-in, the VP prepares updates using a structured leadership template that includes current outcomes, barriers, and proposed solutions. During the meeting, the Executive Director provides coaching, strategic direction, and clarification of expectations to ensure that corrective actions are taken when progress is off track. This leadership monitoring structure creates a continuous accountability loop, ensuring that milestone implementation is actively managed at the executive level and immediately supported when intervention or escalation is needed. | Progress toward milestones will be reviewed by the Executive Director, who serves as the direct supervisor of the Vice President of Schools and collaborates closely with the Vice President of School Improvement. During weekly check-ins, the Vice President of Schools provides updates on campus execution, instructional leadership, and progress toward turnaround milestones, while the Vice President of School Improvement offers insight on the implementation of school improvement strategies and supports. The Executive Director evaluates this information, identifies areas requiring intervention or resource allocation, and ensures alignment between regional leadership actions and the expectations of the turnaround plan. This joint leadership review process ensures that milestone accountability is anchored at the executive level, with direct supervision and support tied to campus performance outcomes. | Progress toward milestones will be reviewed weekly through scheduled check-ins between the Executive Director and the Vice President of Schools, with the Vice President of School Improvement joining as needed to address turnaround-specific priorities. These weekly sessions ensure that progress is not monitored only at formal checkpoints, but consistently assessed in real time. When emerging challenges are identified, the Executive Director may increase the frequency of check-ins to provide intensified oversight or targeted support. This regular cadence allows leadership to make timely adjustments, deploy interventions, and ensure continuous forward momentum toward campus improvement goals. | Milestone progress data will be collected through leadership documentation and evidence reviewed during weekly check-ins between the Executive Director and the Vice President of Schools, with input from the Vice President of School Improvement when turnaround priorities are discussed. Prior to each check-in, campus and regional data are consolidated into leadership templates, which include outcome trends, implementation updates, root cause reflections, and proposed next steps. These updates draw from observation and feedback trackers, assessment data, instructional coaching logs, and campus milestone dashboards. By requiring leaders to prepare data-informed summaries in advance, the Executive Director ensures that milestone progress is evaluated using verified evidence rather than anecdotal reporting, allowing decisions to be based on current performance and fidelity of implementation. | Milestone progress data discussed during Executive Director check-ins will be shared with district leadership and key stakeholders through established leadership communication and escalation protocols. Following each check-in, key findings, risks, and next steps are documented in leadership trackers and communicated to regional teams through tactical meetings, and, when necessary, elevated to senior district leadership for resource allocation or strategic intervention. The Vice President of Schools communicates aligned expectations to principals, while the Vice President of School Improvement coordinates additional support or coaching for campuses requiring targeted assistance. This top-down and bottom-up communication structure ensures that progress toward milestones is transparent at all levels, executive, regional, and campus, allowing stakeholders to remain informed, aligned, and accountable to the successful implementation of the turnaround plan.
|  | The successful implementation of this plan will be monitored through weekly leadership check-ins between the Regional Superintendent and either the Executive Director or the Vice President of School Improvement. These check-ins are embedded in the regional core calendar and serve as a dedicated space to review progress toward milestones, assess the effectiveness of current strategies, and problem-solve any barriers hindering implementation. Prior to the meeting, the Executive Director or VPSI prepares updates using the check-in document, including current outcomes, identified gaps, and proposed solutions. During the conversation, the Regional Superintendent provides coaching, analyzes milestone alignment, and ensures that action steps remain focused on achieving turnaround goals. This consistent one-on-one accountability structure enables real-time adjustments, timely allocation of support, and continuous oversight of the plan’s execution at the leadership level. | Progress toward milestones will be reviewed by the Regional Superintendent in collaboration with the Executive Director or Vice President of School Improvement during regularly scheduled weekly check-ins. As the supervisor, the Regional Superintendent is responsible for holding the Executive Director or VPSI accountable for implementation progress across campuses, including adherence to milestone timelines and intervention strategies. During these sessions, the Executive Director or VPSI presents milestone status, implementation challenges, and leadership actions taken at the campus level. The Regional Superintendent provides guidance, determines whether progress is on or off track, and initiates additional support or escalation when necessary. This shared responsibility ensures that milestone monitoring is led by regional leadership with direct authority to adjust strategy, deploy resources, and reinforce accountability. | Progress toward milestones will be reviewed weekly through structured check-ins between the Regional Superintendent and the Executive Director or Vice President of School Improvement. Because these check-ins are built into the leadership core calendar, they provide a consistent cadence for monitoring implementation progress, assessing the impact of current strategies, and identifying emerging barriers. The weekly frequency ensures that milestone progress is not left to quarterly review, but instead monitored continuously, allowing swift intervention, adjustment of action steps, and timely deployment of support when progress is not on track. | Milestone progress data will be collected through leadership evidence reviewed during weekly check-ins between the Regional Superintendent and the Executive Director or Vice President of School Improvement. Prior to each check-in, the Executive Director or VPSI completes a structured check-in document that includes updated outcome data, progress toward specific milestones, and an analysis of root causes for any implementation gaps. This information is supported by observation and feedback trackers, coaching logs, PLC artifacts, and interim assessment data gathered from campuses. During the check-in, milestone progress is discussed using a results-based framework, ensuring that both outcome data and implementation evidence are reviewed. This systematic collection process ensures that progress monitoring is grounded in verified data rather than anecdotal reporting. | Milestone progress data gathered during weekly check-ins will be shared with district leadership and relevant stakeholders through established reporting and communication structures. Following each check-in, key updates, identified risks, and agreed-upon next steps are documented in shared leadership trackers and communicated during regional tactical meetings and executive leadership huddles. When additional resources or intervention are required, the Regional Superintendent escalates needs to senior district leadership or national support teams. Information is also cascaded to campus principals and leadership teams through coaching sessions and follow-up directives, ensuring clear alignment between regional decision-making and on-campus execution. This communication loop ensures transparency, reinforces accountability, and supports timely action toward achieving turnaround milestones.
|  | The successful implementation of this plan will be monitored through weekly manager–direct report check-ins, which are built into the core calendar between the Deputy Superintendent and the Regional Superintendent. These check-ins provide a structured space to review progress toward goals, discuss barriers, and align on next steps. Prior to each meeting, the Regional Superintendent prepares outcome updates and root cause reflections using the check-in document. During the conversation, both leaders engage in two-way feedback, analyze current implementation status, and problem-solve around any obstacles impacting milestone attainment. Because these check-ins are recurring and intentionally focused on results, they ensure continuous oversight, timely adjustment of strategies, and accountable follow-through on the commitments outlined in the turnaround plan. | Progress toward milestones will be reviewed jointly by the Deputy Superintendent and the Regional Superintendent during their scheduled weekly check-ins. As the direct manager, the Deputy Superintendent is responsible for ensuring that the Regional Superintendent maintains clear progress toward the goals and actions outlined in the turnaround plan. During these sessions, the Regional Superintendent presents current milestone status, implementation evidence, and any emerging challenges from the campuses. The Deputy Superintendent provides coaching, guidance, and escalation support when additional regional or district resources are required. This shared accountability ensures that milestone monitoring remains anchored in leadership oversight and directly tied to decision-making and support at the executive level. | Progress toward milestones will be reviewed weekly through scheduled manager–direct report check-ins between the Deputy Superintendent and the Regional Superintendent. These recurring sessions, embedded into the core calendar, ensure that leadership maintains continuous visibility into implementation status, allowing for real-time adjustments rather than delayed, end-of-quarter interventions. The weekly cadence creates a consistent accountability loop, ensuring that progress toward milestones is actively monitored, corrective action is taken promptly, and support is deployed when needed to keep turnaround efforts on track. | Milestone progress data will be collected through the structured check-in process using pre-meeting submission and review of leadership artifacts. Prior to each check-in, the Regional Superintendent completes a check-in document that includes current outcomes, identified root causes for any gaps, and proposed solutions. This data is supported by campus-level evidence such as observation and feedback trackers, PLC documentation, interim assessment results, and MTSS intervention reports. During the check-in, the Deputy Superintendent reviews this data alongside the Regional Superintendent, using the Outcomes–Causes–Solutions (OCS) framework to ensure accuracy and clarity. This systematic documentation process ensures that milestone monitoring is grounded in real-time implementation evidence rather than anecdotal reporting. | Milestone progress data reviewed during weekly check-ins will be shared with district leadership and relevant stakeholders through established communication and accountability mechanisms. Following each check-in, key updates, identified challenges, and next steps are documented in leadership trackers and cascaded into regional tactical meetings and principal supervision forums. When additional resources or interventions are required, the Deputy Superintendent escalates needs to executive leadership or national support teams. This transparent flow of information ensures that milestone progress is not only monitored at the executive level, but also translated into actionable support for campus leaders, reinforcing alignment across all tiers of the organization.
|  | District and campus leaders will monitor the successful implementation of this plan through bi-weekly Portfolio Tactical, facilitated by the Regional Superintendent. These meetings bring together the Vice President of School Improvement, Regional Executive Director, Vice President of Schools, and the assigned National Content Specialist to review the campus’s instructional status, milestone progress, and implementation of key strategies. During each Tactical, the Vice President of Schools (principal supervisor) and Regional Executive Director assess whether the campus is on track, identify barriers, and request any necessary instructional supports or resources. This continuous monitoring structure ensures that district leaders remain actively engaged in progress oversight and are positioned to make timely adjustments to sustain campus improvement efforts. | Progress toward milestones will be reviewed through the bi-weekly Portfolio Tactical, led by the Regional Superintendent and attended by the Vice President of School Improvement, Regional Executive Director, Vice President of Schools, and the assigned National Content Specialist. This bi-weekly mechanism is specifically leveraged to monitor the milestones identified in the turnaround plan, requiring active input from each of these district leaders. During these sessions, the Vice President of Schools reports on campus implementation, while the Executive Director provides leadership oversight. Based on the level of progress and implementation observed, district resources are deployed as needed, ranging from instructional materials and strategic support to direct human capital through national coaching or specialized intervention teams. This ensures that progress monitoring is immediately connected to action and accountability. | Progress toward milestones will be reviewed on a bi-weekly basis through Portfolio Tactical meetings. This consistent cadence ensures that district and campus leaders are able to frequently assess implementation progress, identify emerging barriers, and make timely adjustments to strategies. By reviewing milestones every two weeks, leadership maintains a proactive stance, allowing for rapid deployment of additional support, resources, or coaching when progress toward key outcomes is at risk. | Milestone progress data will be collected through multiple evidence streams reviewed during Portfolio Tactical meetings. Data sources will include principal reports, observation and feedback trackers, coaching logs, PLC documentation, interim assessment results, and MTSS intervention progress reports. Each of these tracking methods is supported by a real-time data dashboard, ensuring continuous visibility into implementation and student outcomes. National, regional, and campus leaders all have access to these dashboards and reports, allowing for transparent monitoring and collaborative problem-solving. In addition, Quick Check results will be used to verify the fidelity of leadership and instructional execution, further strengthening the accuracy of milestone monitoring. | Milestone progress data will be shared through collaborative discussion and documentation during Portfolio Tactical. Insights, progress updates, and required interventions are recorded in shared tactical trackers and communicated back to campus leadership during follow-up check-ins and coaching sessions. When regional or national support is required, requests and action steps are formally escalated during these meetings. This layered communication structure ensures that milestone progress is transparent, action-oriented, and aligned across all leadership levels.
|  | The successful implementation of this plan will be monitored through weekly supervisor–direct report check-ins between the Deputy Superintendent and the Chief of Staff. These sessions are built into the core leadership calendar and provide a structured space to review progress toward goals, examine barriers, and align on next steps. Prior to each meeting, the Chief of Staff prepares outcome updates and root cause reflections using the check-in document. During the conversation, both leaders engage in two-way feedback, analyze current implementation status, and problem-solve around any challenges impacting milestone attainment. Because these check-ins are recurring and results-focused, they ensure continuous oversight, timely strategic adjustments, and accountable follow-through on turnaround commitments. | Progress toward milestones will be reviewed jointly by the Deputy Superintendent and the Chief of Staff during their scheduled weekly check-ins. As the direct supervisor, the Deputy Superintendent is responsible for ensuring that the Chief of Staff, as a direct support to the Vice President of School Improvement, maintains clear progress toward the goals and actions outlined in the turnaround plan. During these sessions, the Chief of Staff presents current milestone status, implementation evidence, and any emerging challenges from across departments. The Deputy Superintendent provides coaching, guidance, and escalation support when additional regional or district resources are required. This shared accountability ensures that milestone monitoring remains anchored in executive leadership oversight and directly tied to decision-making at the highest level. | Progress toward milestones will be reviewed weekly through scheduled supervisor–direct report check-ins between the Deputy Superintendent and the Chief of Staff. These recurring sessions, embedded within the core calendar, ensure sustained visibility into implementation status and allow for real-time adjustments rather than delayed, end-of-cycle interventions. The weekly cadence creates a consistent accountability loop, ensuring that progress is actively monitored, corrective action is taken promptly, and targeted support is deployed to keep turnaround efforts on track. | Milestone progress data will be collected through the structured check-in process using pre-meeting submission and review of leadership artifacts. Prior to each session, the Chief of Staff completes a check-in document that includes current outcomes, identified root causes for gaps, and proposed solutions. This data is supported by organization-wide evidence such as observation and feedback trackers, PLC documentation, interim assessment results, and MTSS intervention reports. During the check-in, the Deputy Superintendent reviews this data alongside the Chief of Staff using the Outcomes–Causes–Solutions (OCS) framework to ensure accuracy and clarity. This systematic documentation process ensures that milestone monitoring is grounded in real-time implementation evidence rather than anecdotal reporting. | Milestone progress data reviewed during weekly check-ins will be shared with district leadership and relevant stakeholders through established communication and accountability mechanisms. Following each check-in, key updates, identified challenges, and next steps are documented in leadership trackers and cascaded into tactical meetings and principal supervision forums. When additional resources or interventions are needed, the Deputy Superintendent escalates requests to executive leadership or national support teams. This transparent flow of information ensures that milestone progress is not only monitored at the executive level, but also translated into actionable support for campus and departmental leaders—reinforcing alignment across all tiers of the organization.
|  | The successful implementation of this plan will be monitored through bi-weekly supervisor–direct report check-ins between the Superintendent and the Deputy Superintendent. These sessions, embedded in the core executive calendar, provide a structured forum to review progress toward goals, examine barriers, and align on next steps. Prior to each meeting, the Deputy Superintendent prepares outcome updates and root cause reflections using the designated check-in document. During the conversation, both leaders engage in two-way feedback, analyze current implementation status, and address challenges affecting milestone attainment. Because these check-ins are recurring and results-focused, they ensure continuous oversight, timely strategic adjustments, and accountable follow-through on turnaround commitments. | Progress toward milestones will be reviewed jointly by the Superintendent and the Deputy Superintendent during their bi-weekly check-ins. As the direct supervisor, the Superintendent is responsible for ensuring that the Deputy Superintendent maintains clear progress toward the goals and actions outlined in the turnaround plan. During these sessions, the Deputy Superintendent presents current milestone status, implementation evidence, and any emerging challenges from across regions or departments. The Superintendent provides coaching, guidance, and escalation support when additional district or national resources are required. This shared accountability ensures that milestone monitoring remains anchored in executive oversight and directly tied to leadership-level decision-making. | Progress toward milestones will be reviewed bi-weekly through scheduled supervisor–direct report check-ins between the Superintendent and the Deputy Superintendent. These sessions ensure sustained visibility into implementation status and enable real-time adjustments rather than delayed, end-of-cycle interventions. The bi-weekly cadence creates a consistent accountability loop, ensuring that progress is actively monitored, corrective action is taken promptly, and targeted support is deployed to keep turnaround efforts aligned and on track. | Milestone progress data will be collected through the structured bi-weekly check-in process using pre-meeting submission and review of leadership artifacts. Prior to each session, the Deputy Superintendent completes a check-in document outlining current outcomes, identified root causes for gaps, and proposed solutions. This data is supported by organizational evidence such as observation and feedback trackers, PLC documentation, interim assessment results, and MTSS intervention reports. During the check-in, the Superintendent reviews this data with the Deputy Superintendent using the Outcomes–Causes–Solutions (OCS) framework to ensure accuracy and clarity. This systematic documentation process ensures milestone monitoring is anchored in real-time implementation evidence rather than anecdotal reporting. | Milestone progress data reviewed during bi-weekly check-ins will be shared with district leadership and, as appropriate, communicated to the School Board to ensure transparency and alignment at the governance level. When additional actions are required at the regional or campus level, the Deputy Superintendent will provide targeted next steps and strategic feedback to the Regional Superintendent. The Regional Superintendent is then responsible for disseminating this guidance across the region to support campus turnaround efforts and ensure consistent execution of the improvement plan. This structured communication flow ensures that progress monitoring at the executive level is directly translated into actionable leadership support, reinforcing coherence and urgency across all tiers of the organization.
|  | Implementation of the school improvement plan will be monitored through quarterly maintenance audits — executive site visits conducted by the Superintendent, Deputy Superintendent, Chief of Staff, and Curriculum Officers. These progress audits allow senior leadership to directly assess the fidelity of implementation and confirm that strategies are producing measurable impact. During each visit, leaders gather both quantitative data and qualitative evidence through classroom observations, leadership team discussions, and review of instructional and intervention artifacts. These executive audits function as a high-level accountability measure to ensure alignment with district turnaround expectations. | The Superintendent, in collaboration with the Deputy Superintendent, will lead the review of milestone progress during quarterly progress audits. The Superintendent’s participation ensures governance-level oversight, while the Deputy Superintendent, Chief of Staff, and Curriculum Officers provide executive analysis of implementation status. Following the visit, strategic feedback is communicated to the Regional Superintendent, Vice President of Schools, Vice President of School Improvement, and Executive Director to direct necessary action at the regional and campus levels. | Progress toward milestones will be reviewed quarterly through formal maintenance or progress audits conducted on-site. These visits serve as scheduled executive checkpoints designed to evaluate sustained execution of turnaround strategies and recalibrate support where progress is stalled or inconsistent. The quarterly cadence ensures districts receive a comprehensive and objective assessment every nine weeks. | Progress data will be collected during quarterly audits through structured evidence protocols, including classroom walkthroughs, PLC reviews, interim assessment analysis, MTSS documentation, and leadership artifact review. Executive leadership applies an Outcomes–Causes–Solutions (OCS) framework to organize findings, ensuring that root causes are identified and tied to specific corrective actions. Data collected is objective, implementation-based, and validated through direct observation rather than self-reporting. | Following each quarterly audit, a comprehensive executive summary will be developed outlining strengths, gaps, and required next steps. Audit outcomes will be shared with district leadership, and when appropriate, reported to the School Board to ensure transparency at the governance level. The Deputy Superintendent will provide regional feedback and follow-up actions to the Regional Superintendent for dissemination to school leaders, ensuring that insights from executive audits are operationalized to drive continuous improvement across campuses.

## Resources
Criteria for Success
Has the district identified all resources needed to implement the SI strategy? -The description lists all additional costs associated with implementing the school improvement strategy (e.g., stipends, instructional materials, training/professional development costs, costs for additional staff positions created to implement the strategy, etc.) -Each cost described includes the source of funds.
Question | List or copy and paste all SI - identified campuses below | Please share the required costs to implement plan and source of funds | If the strategy is contingent on a grant funding source, what is your alternative funding or implementation plan if you do not receive the grant? How would your district still support and execute this strategy?
Additional Instructions | List all SI campuses in the district
Answer(s) | IDEA Travis Academy | To implement the school improvement plan, District-allocated School Improvement Funds have been strategically aligned to support targeted coaching, leadership development, instructional capacity, and regional talent stabilization. These investments are aligned to the Effective Schools Framework (ESF), specifically: Lever 1 – Effective Leadership and Planning Lever 2 – Strategic Staffing Lever 3 – Positive School Culture Lever 5 – Effective Instruction National Support for Academics, Lesson Internalization, Lesson Execution, Instructional Rounds, and Side-by-Side Coaching (Leadership and instructional capacity-building; targeted development of APIs and campus leaders) Cost: $51,200 for the year (includes flights, hotel stays, rental cars, and per diem for a rotation of 4 National team members traveling once every two weeks for 8 months) Rationale: Few National employees live in region; current support is limited to Teams meetings or virtual observations. The regional leadership team (ED, VPs of Schools, DOA, RDO, and RDOT) is new to IDEA and requires consistent, high-quality, in-person coaching to build skills in instruction, operations, school culture, and talent. On-the-ground presence ensures high-quality execution of lesson internalization, PLCs, instructional rounds, and leader feedback cycles. Strengthens the systems needed to stabilize operations, retain talent, improve instructional execution, and meet student growth and achievement goals. These investments strengthen leadership planning and coaching systems (Lever 1), deepen instructional capacity through real-time practice and feedback cycles (Lever 5), stabilize and develop regional and campus staffing structures through targeted support (Lever 2), and reinforce positive school culture by improving instructional consistency and leader presence (Lever 3). By ensuring National support is delivered in person rather than virtually, the region gains the expertise necessary to build strong instructional systems, accelerate leader growth, and create the conditions required for Travis Academy to meet its academic performance targets—particularly under Domain III. | To support the effective implementation of the School Improvement Plan at IDEA Travis Academy, School Improvement Funds have been intentionally allocated to strengthen three core SI strategies: Intensive Instruction, High-Quality Observation and Feedback, and Effective PLCs/Lesson Internalization. Due to the limited number of National team members living in the region—and the fact that the regional leadership team (ED, VPs of Schools, DOA, RDO, and RDOT) is largely new to IDEA—local leaders require consistent, high-quality, on-the-ground coaching to build instructional skill and drive rapid improvement. The allocated funds provide for National academic and operational experts to be physically present on campus every two weeks, supporting lesson internalization, lesson execution, instructional rounds, and side-by-side coaching of APIs, teachers, and leaders. This in-person support strengthens the observation and feedback cycles, accelerates the development of leader and teacher capacity, and ensures PLCs are grounded in high-quality content expectations and precise instructional practices. Operational and talent support further stabilize campus systems, allowing instructional leaders to focus on coaching, data analysis, and intervention planning. These funds cover flights, hotels, rental cars, and per diem—totaling $51,200 for the year—to sustain a consistent cadence of support that would not be possible through virtual coaching alone. These funds do not operate in isolation; instead, they establish an aligned system where leader development, instructional execution, and operational effectiveness reinforce one another—accelerating both proficiency and growth for scholars at Travis Academy. Funding Source Note: The district is not relying on grant funds to support this plan and is utilizing local, federal, and additional funding sources to sustain implementation and build long-term capacity.

## Additional Info
Question | List or copy and paste all SI - identified campuses below | (Optional) Please share any additional information about your strategy that was not included in the prior sections. You may also upload documents.
Additional Instructions | List all SI campuses in the district
Answer(s)